INITIAL INCEPTION REPORT

- Organization (PIA) detail : Jattu trust, Thotapalli, Parvathipuram,

Vizianagaram (Dist), Andhra Pradesh.

- Executive summary of the project / Brief description of the project

- Objective : Establishment of intensive, integrated, adoptable ½ acre Annapurna organic farm for Tribal and other poor farmers across the project villages, Provide capacity, resources and support for tribal farmers to improve their productivity, production and marketing of produces.

- Tasks : Implementation ½ acre Annapurna crop model.

- Output : To achieve the improved and substantial increase in production of agriculture and horticulture produce leading to food security and economic development for tribal and other poorest of the poor farmers.

- Activities undertaken so far

- Approval Date 	: 2012 - 13

- MoU Date		: May - 2013

- Sanction Date	: May - 2013

- Activity Schedule (Gantt Chart)

| D | Activity | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D1 | Deployment of Staff |  | √ |  |  |  |  |  |  |  |  |  |  |
| D2 | Orientation & training of staff on MKSP |  | √ |  |  |  |  |  |  |  |  |  |  |
| D3 | Finalization of clusters / villages | √ | √ | √ | √ |  |  |  |  |  |  |  |  |
| D4 | Identification of SHG members | √ | √ | √ | √ |  |  |  |  |  |  |  |  |
| D5 | Training to mahila kissans |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |
| D6 | Preparation of annapurna |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |
| D7 | Supply of seeds and saplings |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |
| D8 | Supply of neem cake |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |
| D9 | Formation of Annapurna pantala sanghas |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |
| D10 | Crops showing |  |  | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |

Description of each activity (1-2 sentences)

Reasoning for timing of activity (clarity needed)

D1. Attached Deployment of staff in annexure – I

D2. Attached Time Table in Annexure – II

D3. finalisation of clusters and villages for the year of 2013-14  Attached in Annexure – III

D4. List of SHG members in web krusheserp.com

D5. 3day time table in Annexure – IV

D6.  476 ½ acre Annapurna models grounded

D7. 540 vegetable seed kits, 10,678 Mango, 2724 Orange, 899 Pomegranate, 928 Sapota, 962             Guava, 917 Lemon, 1547 Drumstick saplings, 63100 Take stumps supplied.

D8. 17.52 tons of Neem cake supplied

D9.30 Annapurna pantala sanghas formed

D10. .  476 farmers sown crops in Kharif season

Annapurna Rain fed crops implementation is a time bounded activity, before the rainy season is the time line for sowing of seeds & plants. But some of the farmers having interest and telling that they will surviving their plants with supplying of sufficient water. so we have been giving trainings to the farmers as a yearlong activity.

E. How the individual activity will be undertaken & by whom (This how part should be explained clearly, this may also be converted as a Community Operational Manual (COM) / Training Manual (TM) for the staffs, community cadre & SHG members) HOWEVER, COM / TM will not be part of inception report.

Crop plantation and harvesting will be done by individually. The family will meet the all respective activities of sowing, inter cultivation and harvesting in alternative beds.

F. Expected Output

F.1 Expected Annual Output : Grounding of thousand Annapurna crop models. Harvesting of two season crops.

F.2 Expected Convergence : Dwma – NREGS

F.3 Month-wise expenditure plan : Enclosed as annexure - V

BUDGET TEMPLATE

Please Note:: To create the appropriate budget heads, you may refer to the budget template attached in the Mail.

Training schedule

| Sl.No | Date | No.of Farmers Trained | Duration | Participants |
| --- | --- | --- | --- | --- |
| 1 | 08.06.13 | 37 | 6days | CRP’s & C.C’s |
| 2 | 20.06.13 | 36 | 3days | Farmers |
| 3 | 26.06.13 | 38 | 3days | Farmers |
| 4 | 29.06.13 | 64 | 3days | Farmers |
| 5 | 02.07.13 | 62 | 3days | Farmers |
| 6 | 09.07.13 | 24 | 3days | Farmers |
| 7 | 05.08.13 | 68 | 3days | Farmers |
| 8 | 08.0813 | 8 | 2days | Farmers |
| 9 | 11.08.13 | 50 | 3days | Farmers |
| 10 | 19.09.13 | 56 | 3days | Farmers |
| 11 | 25.09.13 | 49 | 3days | Farmers |
| 12 | 30.09.13 | 50 | 2days | Annapurna pantala sangam |
| 13 | 19.10.13 | 54 | 3days | Farmers |