Jattu Trust MKSP/NTFP Annapurna model of Agricultural Practices

| Sl. No | Description | Target as per DPR |  |  | Achievements and Gaps in 1st Year |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year1 2013-14 | Year2 2014-15 | Year3 2015-16 | Cumulative Achievement | Gap |
| 1 | CRPs Recruited and Trained – 40 | 40 |  |  | 30 CRPs’ recruited and working. Another 50 CRPs trained |  |
| 2 | Project orientation to communities (CIGS) - 150 | 75 | 50 | 25 | 80 CIGs’ formed |  |
| 3 | Para Professionals recruited and trained – 8 | 8 |  |  | 8 Para Professionals recruited and working |  |
| 4 | Professional -Mkt Recruited and trained – 1 |  |  |  | - | No budget allotted in revised budget |
| 5 | Identification and finalization of families – 3000 | 2000 | 1000 |  | 3000 families identified |  |
| 6 | Training on Annaporna model at project level No.of women - 3000 | 1500 | 1000 | 500 | 1978 kisans trained |  |
| 7 | Training to farmers on value addition and Post harvest Management at cluster level | 1000 | 1000 | 1000 | - | 1000 |
| 8 | Annaporna model Implementation – No. Families | 500 | 1500 | 1000 | 1463 models implementing |  |
| 9 | Baseline Survey - No of families Covered | 1000 | 1000 | 1000 | 2613 families covered |  |
| 10 | Endline survey - No of Families Covered | 1000 | 1000 | 1000 | 1463 |  |
| 11 | Identification of healers on Ayurvedic medicine – Identified | 120 |  |  | 120 healers identified |  |
| 12 | Training to local healers on Ayurvedic medicine – Trained – 120 |  | 60 | 60 | - |  |
| 13 | Training Module development and print - 1. Organic fertiliser and pesticides 2. Preparation of Annapoorna 3.Leafy vegetables, tuber vegetables and nutrition values. | 3 |  |  | Printed 3 modules 1.Organic fertilizer and pesticides 2. Prep of Annapoorna in Telugu published. 1 Prep of Annapoorna module in English |  |
| 14 | Training module development : audio-visual | 3 |  |  | - modules developed - Valasapakshulu on Migrations - Importance of sustainable agriculture songs audio under development. | 1 |
| 15 | Mapping and doing need assessment of tool kits Lemon grass extraction tools at community level | 1 |  |  | 1 unit established ( Lemon oil extraction machine ) |  |
| 16 | Tools and Kits providing related to - Pest control kit, Taurpaulins | 500 | 1500 | 1000 | Provided 608 tubs for preparation of decoctions | 855 |
| 17 | Formation of CIGs | 50 | 50 | 50 | CIGs formed 80 |  |
| 18 | Cluster federations formed (8) | 4 | 4 |  | 8 Cluster federations formed. |  |
| 19 | Cluster federation leaders trained | 4 | 4 |  | 8 Cluster federations’ leaders trained. |  |
| 20 | Formation of MACS consisting of 8 clusters |  | 1 |  | - | 1 |
| 21 | Training of MACS leaders on principles and management |  | 1 |  | - |  |
| 22 | Training on Value addition & processing on AGRO / MAPS to CIG leaders.300 |  | 300 |  | - | 100 |
| 23 | Training to PRI representatives - 300 | 100 | 100 | 100 | - | 100 |
| 24 | Exposure to CRPs / para proffessoinals on NTFPs / MAPs – 2 | 48 | 48 |  | 2 exposure visits programmes organized |  |
| 25 | Training on Value addition & processing on AGRO / MAPS (38) |  | 38 |  | - |  |
| 26 | Training on Food & Nutrition security - 38 |  | 38 |  | - |  |
| 27 | Development of Various Annapoorna crop models | 4 |  |  | 4 models developed |  |
| 28 | Small Equipment to Cluster federations (8) | 4 | 4 |  | Provided SRI weeders, Markers, Power weeders, Grass cutters, oil engines, Sprinkler pipe sets, solor pump set etc.., |  |
| 29 | Establishment of Organic Outlets (6) | 1 | 3 | 2 | - |  |
| 30 | Rejuvenation of Cashew processing unit and inputs to farmers and facilitation cost |  |  |  |  | No budget provided in revised Budget |
| 31 | Two coordinators cost for facilitation of sustainable agri practices for Cashew plants and processing unit- recruited and trained |  |  |  |  | No budget provided in revised Budget |
| 32 | Identification families for willing to do the sustainable practices in Two clusters (GL Puram and Krupam | 500 | 500 |  |  | No budget provided in revised Budget |
| 33 | Cashew garden rejunavation inputs - trenches, half circle platform bund, training on Organic practices |  |  |  | - | No budget provided in revised Budget |
| 34 | Cashew Processing unit rejunavation at Durbili, Kurupam Mandal |  |  |  | - | No budget provided in revised Budget |
| 35 | Publication of Annapoorna monthly magazine and publish (no.of copies) - 75600 | 4400 | 8400 | 12400 | 3000 copies published and distributed. | 21000 |
| 36 | Study on locally available leafy vegetables and roots and its nutritional values with NIN support (Publication) | 1 | 1 |  | Study completed seeking NIN support for identification of their Nutritional values |  |
| 37 | Documentation on local healers knowledge and Publication | 1 |  |  | Documented 120 healers knowledge in telugu. |  |
| 38 | Display no.of boards for public disclosure (125) | 10 | 15 |  | 30 |  |
| 39 | Social Audit | 1 | 1 | 1 | 2 times done |  |
| 40 | Mapping the buyers and sellers in the project locations and arranging the meeting | 1 | 1 |  | - |  |
| 41 | Mahila Kissan Profiling - 3000 families | 2000 | 1000 |  | 2613 kisans base line data uploaded in krushe website & Jattu website |  |

It's gone. Undo

What was wrong with this ad?

Repetitive

Inappropriate

Irrelevant

Thanks for the feedback! Back

We’ll review this ad to improve your experience in the future.

Help us show you better ads by updating your ads settings.

Thanks for the feedback! Undo

We’ll use your feedback to review ads on this site.

Help us show you better ads by updating your ads settings.

Closing ad: %1$d