Jattu Trust MKSP/NTFP Annapurna model of Agricultural Practices

Annual Plan 2016-17 and Cumulative Achievement

| Sl. No | Description | Target as per DPR |  |  | Plan for 2016-17 (2nd year) | Cumulative Achievement as on 13.07.16 (2nd year) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year1 2013-14 | Year2 2014-15 | Year3 2015-16 |  |  |
| 1 | CRPs Recruited and Trained – 40 | 40 |  |  |  | 30 CRPs’ recruited and working. Another 50 CRPs trained |
| 2 | Project orientation to communities (CIGS) - 150 | 75 | 50 | 25 | 90 | 105 CIGs’ formed |
| 3 | Para Professionals recruited and trained – 8 | 8 |  |  |  | 8 Para Professionals recruited and working |
| 4 | Professional -Mkt Recruited and trained – 1 |  |  |  |  | No budget in revised DPR. |
| 5 | Identification and finalization of families – 3000 | 2000 | 1000 |  |  | 3000 families identified |
| 6 | Training on Annaporna model at project level No.of women - 3000 | 1500 | 1000 | 500 | 522 | 1978 kisans trained |
| 7 | Training to farmers on value addition and Post harvest Management at cluster level | 1000 | 1000 | 1000 | 2000 | - |
| 8 | Annaporna model Implementation – No. Families | 500 | 1500 | 1000 | 569 | 2431 models implementing |
| 9 | Baseline Survey - No of families Covered | 1000 | 1000 | 1000 | 387 | 2613 families covered |
| 10 | Endline survey - No of Families Covered | 1000 | 1000 | 1000 | 1537 | 1463 |
| 11 | Identification of healers on Ayurvedic medicine – Identified | 120 |  |  |  | 120 healers identified |
| 12 | Training to local healers on Ayurvedic medicine – Trained - 120 |  | 60 | 60 | 120 | Trained 30 healers |
| 13 | Training Module development and print - 1. Traditional practices on fertiliser and pesticides 2. Preparation of Annapoorna 3.Leafy vegetables, tuber vegetables and nutrition values. | 3 |  |  |  | Printed 3 modules 1. Traditional practices on fertilizer and pesticides under publication 2. Prep of Annapoorna in Telugu published. 1 Prep of Annapoorna module in English under publication. |
| 14 | Training module development : audio-visual | 3 |  |  |  | - modules developed - Valasapakshulu on Migrations - Preparations of Annapurna - Importance of sustainabl agriculture songs Audio under development. |
| 15 | Mapping and doing need assessment of tools kits Lemon grass extraction tools at community level | 1 |  |  |  | 1 unit established ( Lemon oil extraction machine ) |
| 16 | Tools and Kits providing related to - Pest control kit, Taurpaulins | 500 | 1500 | 1000 |  | Provided 608 tubs for preparation of decoctions |
| 17 | Formation of CIGs | 50 | 50 | 50 | 80 | CIGs formed 105 |
| 18 | Cluster federations formed (8) | 4 | 4 |  |  | 8 Cluster federations formed. |
| 19 | Cluster federation leaders trained | 4 | 4 |  |  | 8 Cluster federations’ leaders trained. |
| 20 | Formation of MACS consisting of 8 clusters |  | 1 |  | 1 | Macs Formed. Registration under process |
| 21 | Training of MACS leaders on principles and management |  | 1 |  |  | - |
| 22 | Training on Value addition & processing on AGRO / MAPS to CIG leaders.300 |  | 300 |  | 300 | - |
| 23 | Training to PRI representatives - 300 | 100 | 100 | 100 | 200 | - |
| 24 | Exposure to CRPs / para proffessoinals on NTFPs / MAPs – 2 | 48 | 48 |  |  | 2 exposure visit programmes organized |
| 25 | Training on Value addition & processing on AGRO / MAPS (38) to CRPs Para professionals |  | 38 |  | 38 | - |
| 26 | Training on Food & Nutrition security – 38 to CRPs Para professionals |  | 38 |  | 38 | - |
| 27 | Development of Various Annapoorna crop models | 4 |  |  |  | 4 models developed |
| 28 | Small Equipment to Cluster federations (8) | 4 | 4 |  | 8 | Provided SRI weeders, Markers, Power weeders, Grass cutters, oil engines, Sprinkler pipe sets, solor pump set etc.., |
| 29 | Establishment of Organic Outlets (6) | 1 | 3 | 2 | 6 | 2 one out let in Rythu Bajar, Vizianagaram Another was established in Thotapalli |
| 30 | Rejuvenation of Cashew processing unit and inputs to farmers and facilitation cost |  |  |  |  | No budget provided in revised DPR/Budget |
| 31 | Two coordinators cost for facilitation of sustainable agri practices for Cashew plants and processing unit- recruited and trained |  |  |  |  | No budget provided in revised DPR/Budget |
| 32 | Identification families for willing to do the sustainable practices in Two clusters (GL Puram and Krupam | 500 | 500 |  |  | No budget provided in revised DPR/Budget |
| 33 | Cashew garden rejunavation inputs - trenches, half circle platform bund, training on Organic practices |  |  |  |  | No budget provided in revised DPR/Budget |
| 34 | Cashew Processing unit rejunavation at Durbili, Kurupam Mandal |  |  |  |  | No budget provided in revised DPR/Budget |
| 35 | Publication of Annapoorna monthly magazine and publish (no.of copies) - 75600 | 4400 | 8400 | 12400 | 72500 | 3000 copies published and distributed. |
| 36 | Study on locally available leafy vegetables and roots and its nutritional values with NIN support (Publication) | 1 | 1 |  | 1 | Study completed seeking NIN support for identification of their Nutritional values |
| 37 | Documentation on local healers knowledge and Publication | 1 |  |  | 1 | Identified local healers. |
| 38 | Display no.of boards for public disclosure (125) | 10 | 15 |  | 95 | 30 |
| 39 | Social Audit | 1 | 1 | 1 | 1 | 2 times done |
| 40 | Mapping the buyers and sellers in the project locations and arranging the meeting | 1 | 1 |  | 2 | - |
| 41 | Mahila Kissan Profiling - 3000 families | 2000 | 1000 |  | 387 | 2613 kisans base line data uploaded in krushe website & Jattu website |