Tribal Economic and Food Security Enhancement through ½ acre Annnapoorna Crop Model

Detailed Project Report.

Submitted to:

Society for Elimination of Rural Poverty (SERP)

Government of Andhra Pradesh

June 2012

Jattu Trust

Parvathipuram H.O, Vizianagaram (Dt) 
Andhra Pradesh-535502

Email: jattutrust@hotmail.com      Web: http://www.jattutrust.org

Field  Office : Thotapalli, Garugubilli Mandal, Vizianagaram(Dt),  Pin:535525

Contents

Contents	2

Abbreviations	2

1	Project Background, Context and Rationale	2-41

2	Chapter 2:  Detailed Intervention Strategy and Phasing	42-54

3	Chapter 3:  Detailed Project Components	55-70

4	Chapter 4:  Implementation Arrangements	71-74

5	Chapter 5:  Implementation Schedule	7277

6	Chapter 6:  Results Framework	78-81

7	Chapter 7:  Monitoring, Evaluation and Learning	22-84

8	Chapter 8:  Budget Narrative	25-97

9.     ANNEXURE I : 3 YEARS AUDIT REPORTS

10.   ANNEXURE II : BENEFICIARY LIST

11.   ANNEXURE III: DETAILED REPORT ON ANNPOORNA MODEL

12.  ANNEXURE IV : JATTU-MKSP DETAILED BUDGET

Abbreviations

| AP | Andhra Pradesh |  | MORD MKSP MACS | Ministery of Rural Development Mahila Kisan Sasakthi Karan Pariyojona Mutual Aided Cooperative Society |
| --- | --- | --- | --- | --- |
| CMSA | Community Managed Sustainable Agriculture |  | NGO NSFDC | Non Governmental Organisation National Scheduled Castes and Scheduled Tribes Finance and Development Corporation |
| CIG | Common Interest Group |  | NTFP | Non Timber Forest Produce |
| CF | Cluster Federation |  | NABARD | National Bank for Agriculture and Rural Development |
| CRP CBO | Community Resource person Community Based Organisation |  | NRLM RTI | National Rural Livelihood Mission Right to information |
| FFS | Farmer's Field School |  | SERP | Society for Elimination of Rural Poverty |
| GAP GCC | Good Agriculture Practices Girijan Co-operative Corporation |  | ST STEP | Scheduled Tribe Sustainable Tribal Empowerment Programme |
| HH | House Holds |  | SC | Scheduled Caste |
| IKP | Indira Kranthi Patham |  | TRIFED | Tribal Cooperative Marketing Development Federation of India |
| INM | Integrated Nutrients Management |  | TRICOR | Tribes Cooperative Finance Corporation Limited, Hyderabad |
| IPM | Integrated Pest Management |  |  |  |
| ITDA | Integrated Tribal Development Agency |  |  |  |
| KVK LFA | Krishi Vignan Kendra Log Frame Analysis |  |  |  |
| MAP | Medicinal and Aromatic Plants |  |  |  |
| MGNREGA | Mahatma Gandhi National Rural Employment Guarantee Act |  |  |  |

Tribal Economic and Food Security Enhancement through ½ acre Annnapurna Crop Model

Detailed Project Report

Project Background, Context and Rationale

Demographic Profile of the Area

Andhra Pradesh is the largest state in the southern peninsular region, with an area of 2,75,100 sqkms and a coast line of 974 kms.  Based on the physical features, the State is divided into three regions - Eastern hills, the coastal plains and peninsular plateau.

The population of A.P. as per the 2011 provisional census data stands at 8.46 crores. This constitutes about 7% of the total population of the country.  Andhra Pradesh is the most populous of the 4 southern States.   The  decadal  growth  rate  of  population  in  A.P.  is  11.10,  down  from  14.59in 1991-01, whereas the all India decadal growth rate is 17.64. The rural population of the state, as given in Table 2, is 5.63 crores constituting 67% of the state’s population.  Between 2001 and 2011 urban growth has been 36.26%. The rural population of the State in 2001 is 55,223,944 compared to 48,620,882 in 1991, which shows an absolute increase  of 6,603,062, with growth rate of 13.58%

The Scheduled Areas of Andhra Pradesh, covered by the Tribal Sub-Plan (TSP) approach, are spread over 31,485 sq km in 5936 villages (11,855 habitation) in the districts of Srikakulam, Vizianagaram, Visakhapatnam, East Godavari, West Godavari, Warangal, Khammam, Adilabad and Kurnool. The 35 reported ST communities are mainly concentrated in nine districts declared as Scheduled Areas by special government order in 1950. Sixty percent of the STs live in forest areas in the Eastern Ghats, on the banks of the river Godavari. Two-thirds of the ST population in the State of Andhra Pradesh live in these areas. This constitutes 11% of the total geographical area of the state. Among the 23 districts,

Andhra Pradesh has a sizeable Scheduled Caste and Scheduled Tribe population. The 2001 census figures a three-fold increase in the number of SCs and fourfold increase of STs in the state. There were  12.3 and 5 million SCs and STs respectively comprising 16.2 and 6.6 percent of the total population.

Map of Andhra and proposed project district:

Figure 1 shows the Vizianagaram District (Black colour).

Figure 2 shows the Proposed Mandals in Vizianagaram District (Green colour).

Mandals Covered in Vizianagaram District

- Gummalakshmipuram

- Komarada

- Kurupam

- Jiyyammavalass

- Parvathipuram

- Garugubilli

Total population for Andhra Pradesh and proposed project district as per the 2010 and 2011 (Provisional) Census

|  | Total Population | Total Male population | Total female population | % of Females | Total Population | Total Male population | Total female population | % of Females |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Census of India, 2011 provisional data |  |  |  | Census of India, 2001 |  |  |  |
| Andhra Pradesh | 8,46,65,533 | 4,25,09,881 | 4,21,55,652 | 50% | 7,62,10,007 | 38,527,413 | 37,682,594 | 49% |
| Proposed Districts |  |  |  |  |  |  |  |  |
| Vizianagaram | 2,342,868 | 1,161,913 | 1,180,955 | 50% | 2,249,254 | 1,119,541 | 1,129,713 | 50% |

Sources: Census of India 2010 and Census of India 2011, Provisional tables; http://censusindia.gov.in/Dist_File/datasheet-2812.pdf

Scheduled Tribe Population in India and AP (2001 census)

| State | Total Population | ST Population | % of STs |
| --- | --- | --- | --- |
| India | 1,028,610,328 | 84,326,240 | 8.20 |
| Andhra Pradesh | 76,210,007 | 5,024,104 | 6.60 |

Source: http://www.aptribes.gov.in/bsindia1.html

Population and decadal growth rate by residence, Andhra Pradesh and proposed project district:

|  | Population 2011 |  |  | % rural population | Percentage Decadal Growth (Persons) 2001-2011 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total | Rural | Urban |  | Total | Rural | Urban |
| Andhra Pradesh | 8,46,65,533 | 5,63,11,788 | 2,83,53,745 | 67% | 11.10 | 1.64 | 36.26 |
| Proposed District |  |  |  |  |  |  |  |
| Vizianagaram | 2,342,868 | 1,852,446 | 490,422 | 79% | 4.16 | 0.85 | 18.92 |

Source: Census of India 2011, Provisional Population Totals;

data accessed at http://censusindia.gov.in/2011-prov-results/paper2/data_files/AP/5-pop-7-16.pdf on 21 Jan 2013

Vizianagaram district is the most backward district among the North Coastal Districts of Andhra Pradesh and endowed with rich natural resources especially in the sub plan areas where tribal's are living. Majority of the tribal community are small and marginal farmers depending on the rainfed agriculture, marketing of forest produce, wage employment, etc for their livelihood. They are lagging behind in indicators like education, health, economic condition and deprived of access to basic services.

In 2006 the Indian government named Vizianagaram one of the country's 250 most back ward district. It is one of the thirteen districts in Andhra Pradesh currently receiving funds from the Backward Regions Grant Fund Programme (BRGF).

As  regards  the  demographic  profile  of  the  district, the  population  of  the  district according  to

2001  census  was  22.5  lakh   of  whom 11.2  lakh   are  males  and   11.3  lakh   females. The  density

of  population  was  344  members  per  sq. km. The  share  of  scheduled  caste population   and

scheduled  tribes  population  in the  total  population of  the  district  was     around  10  per  cent(

10.6  and  9.6  per  cent  respectively).

It  has  a  geographical  area  of 6.3  lakh  hectares .  About  51  per  cent  of  the  land   area  is  used  for   agriculture  and  another   12 per  cent is  put  under non-agricultural  uses.  Further, 18  per  cent  of  the  area  of  the  district  was  covered  by  forests   and  12  per  cent  was  mainly   barren  and  uncultivable. The principal  rivers  flowing    in this  district  include Nagavali, Suvarnamukhi, Vegavati, Champavati,  Gosthani  and Kandivalasa.

The project proposed to work in 6 Mandals of Vizianagaram District.

| Sl. No. | Name of the mandals covered |
| --- | --- |
| 1. | G.L.Puram |
| 2 | Kurupam |
| 3 | J.M.Valasa |
| 4 | Garugubilli |
| 5 | Komarada |
| 6 | Parvathipuram |

Under social  mobilization,    the  district  fares  moderately- as  of  1 st    of   December  of  2009,

29888    SHGs     were   reported to  have  been  formed.

82% of the population is living in rural areas and depend on Agriculture for their livelihood. Rain fed farming is the characteristic of Agriculture, as about 80% of the cultivation is purely under rain fed conditions.

Even  the irrigated  area also  depends  up  on  the  rainfall  to  some  extent. Because  of  this  reason,   a  majority  of  the  crops  grown in the  district are  dry  crops. Paddy  is  grown   mainly  during  kharif

season   with  80 per  cent  of  the  area  under  tanks,   which  depend  up  on the    rainfall.   The  major  crops  grown  in the  district  are paddy, mesta, groundnut,  ragi,  bajra, sugarcane  and  pulses. The  net  sown  area  forms  50.15  per  cent   in the  total  geographical   area   of 6.44  lakh  hectares   and  the  cropping  intensity  is  1.34. The  net  irrigated  area    of  the  district  for 2007-08  was  1.57  lakh  ha   and     tanks  have  the  largest  share  of   54  per  cent  in  this,  followed  by   canals  33  per  cent, other  wells  16  per  cent  etc. The  area  irrigated  more  than  once  was  to  the  extent  of  18.7  per  cent  over  the  net area  irrigated.

The  district  does  not  have  any major  irrigation  projects.  Twelve  medium  irrigation   projects

working   in the  district   have  a  command  area of   44  thousand  hectares  of  land, 1065  minor

irrigation sources    have 51  thousand  hectares   and   about  nine  thousand   minor  irrigation tanks

have  72 thousand  hectares  of   land.

The climate of Vizianagaram district is characterized by high humidities nearly all the year round with oppressive summer and good seasonal rainfall. The normal rainfall of the district for the year is 1,131.0 MM . The district gets the benefit of both the South-West and North- East monsoon.

Rural Poverty and Context in the Area

In the state as per the official estimates of poverty released by the Planning Commission, poverty ratios of rural areas and urban areas of AP for 2004-05 were 11.20% and 28.00% respectively and that for the State as combined was 15.80%. The corresponding figures for All India during the same period were 28.30%, 25.70% for rural and urban areas and 27.50% for the Nation as combined. However, as per Tendulkar committee, the poverty ratio is 20.7%, 18.1% and 20.0% respectively for rural, urban and combined compared to 36.4%, 21.6% and 32.2% in rural, urban and combined respectively for India.  The difference between the estimations of the planning commission and the Tendulkar Committee is particularly stark in the case of rural poverty figures.

Number and percentage of population below poverty line, AP and all India, as per Tendulkar methodology

|  |  | Rural |  | Urban |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | % persons | No. Of persons (lakhs) | % persons | No. Of persons (lakhs) | % persons | No. Of persons (lakhs) |
| 2009-10 | Andhra Pradesh | 22.8 | 127.9 | 17.7 | 48.7 | 21.1 | 176.6 |
|  | All India | 33.8 | 2782.1 | 20.9 | 764.7 | 29.8 | 3546.8 |
| 2004-05 | Andhra Pradesh | 32.3 | 180 | 23.4 | 55 | 29.6 | 235.1 |
|  | All India | 42 | 3258.1 | 25.5 | 814.1 | 37.2 | 4072.2 |

Source: Press Note on Poverty Estimate, 2009-10, Planning Commission, Government of India;

Accessed at http://planningcommission.nic.in/news/press_pov1903.pdf on 29 December 2012

The BPL data shows that poverty in AP has come down across the years. Though this BPL data gives an indicator of poverty, and its reduction, the accepted notion of what constitutes economic development has undergone a paradigm shift in recent times. The concept of development has been extended to be more comprehensive and go beyond the mere material dimension of increase in per capita income, complemented by the non-material dimension (like levels of education, status of health and access to basic amenities). Thus development, apart from income, relates to general well-being and economic capabilities of the people.

Although even by these estimates, AP figures are  lower than the all India figures, the absolute number of persons increases significantly.  The  Government of A.P. has conducted a Participatory Identification of Poor (PIP) survey in all rural  areas of A.P. in 2002-2003.  As per this survey, the percentage of households living Below Poverty Line (BPL) Domestic Product (DDP). As per the survey 56% of Rural Households in AP are  below the official poverty line of the state.

There is a significant variation in the levels of development of districts.  Hyderabad occupies the  top position followed by Visakhapatnam in 2001, and the same ranks hold good even in 2006- 07. Srikakulam and Vizianagaram, the north coastal districts show the lowest per capita District

State -Though the performance of the State in human development is better than many other major

states in India, it lags behind the other southern states on some human development indicators. The performance is very poor when compared to Kerala which is far ahead in Human development indicators.

### Poverty and Human Development

AP has produced a Human Development Report in 2007. The APHDR estimated a revised HDI, based on the following indicators: adult(15 + age) literacy rate and school attendance rate (of 5-14 age children) for education; life expectancy and infant survival rate (ISR) for health; and inequality adjusted per-capita consumption expenditure for the economic dimension.

As per this index, The HDI value of Andhra Pradesh was lower than the all-India average, and was also lower than the other three south Indian states. The percentage change between two points in A.P. is higher than in all-India but lower than in the most backward states like Bihar and Uttar Pradesh.

Revised Human Development Index for AP

|  | Revised HDI for AP |  |  | Rank |  |
| --- | --- | --- | --- | --- | --- |
|  | 1993-94 | 2004-05 | Change | 1993-94 | 2004-05 |
| Andhra Pradesh | 0.415 | 0.503 | 21.2 | 10 | 10 |
| India | 0.416 | 0.544 | 20.6 |  |  |

Source: Human Development Report 2007, Andhra Pradesh

The report constructed a composite index at the district level using the following indicators: per capita district domestic product (PCDDP) at constant (1993-94) prices representing the income dimension; adult literacy rate(15+ age population) and school attendance rate (6 to14 age group) for the education dimension; and  infant mortality rate (IMR) for the health dimension. The early 1990s are period I and early years of this decade as period II.

Revised Human Development Index by district, AP

| SNo | District | Index Value |  | Rank |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Period I | Period II | Period I | Period II |
| 1 | Srikakulam | 0.269 | 0.453 | 21 | 21 |
| 2 | Vizianagaram | 0.236 | 0.402 | 23 | 22 |
| 3 | Visakhapatnam | 0.383 | 0.553 | 15 | 11 |
| 4 | EastGodavari | 0.411 | 0.586 | 11 | 6 |
| 5 | WestGodavari | 0.448 | 0.607 | 7 | 4 |
| 6 | Krishna | 0.510 | 0.623 | 2 | 2 |
| 7 | Guntur | 0.490 | 0.599 | 3 | 5 |
| 8 | Prakasam | 0.409 | 0.532 | 12 | 14 |
| 9 | Nellore | 0.452 | 0.565 | 4 | 8 |
| 10 | Chittoor | 0.451 | 0.558 | 6 | 10 |
| 11 | Kadapa | 0.447 | 0.536 | 9 | 13 |
| 12 | Anantapur | 0.343 | 0.458 | 19 | 20 |
| 13 | Kurnool | 0.327 | 0.473 | 20 | 19 |
| 14 | Mahabubnagar | 0.249 | 0.397 | 22 | 23 |
| 15 | RangaReddy | 0.452 | 0.610 | 5 | 3 |
| 16 | Hyderabad | 0.591 | 0.717 | 1 | 1 |
| 17 | Medak | 0.385 | 0.550 | 13 | 12 |
| 18 | Nizamabad | 0.383 | 0.504 | 14 | 16 |
| 19 | Adilabad | 0.361 | 0.488 | 16 | 17 |
| 20 | Karimnagar | 0.448 | 0.573 | 8 | 7 |
| 21 | Warangal | 0.349 | 0.514 | 18 | 15 |
| 22 | Khammam | 0.420 | 0.559 | 10 | 9 |
| 23 | Nalgonda | 0.360 | 0.481 | 17 | 18 |

Source: Human Development Report 2007, Andhra Pradesh

The human poverty index is constructed for two points of time - 1991 and 2001 - to trace the decline in the level of deprivation. Relative position of many districts did not change. The three most backward districts and relatively the most deprived ones were Vizianagaram, Srikakulam and Mahabubnagar. Hyderabad, Ranga reddy, Krishna and Guntur were districts that were the least deprived.

The literacy rate of A.P. is 60.47 in 2001 as against 44.08 in 1991. The literacy rate of the state is lower than that of all India. The female literacy rate had gone up by about 50 percent, from 33percent in 1991 to 51 percent in 2001. There was an increase in dropout rates for all children in rural areas in the same period.  The dropout rates among boys and girls were respectively 11.9 and 15.6. Below tables shows in Andhra Pradesh District wise - dropout rate of Scheduled tribes

Drop-out Rates of Scheduled Tribes (2005-06)

| Sl. No. | District | Class I – V |  |  | Class I - VII |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Boys | Girls | Total | Boys | Girls | Total |
| 1. | Srikakulam | 27.80 | 32.90 | 30.34 | 63.80 | 68.73 | 66.20 |
| 2. | Vizianagaram | 15.13 | 24.05 | 19.52 | 58.20 | 68.83 | 63.46 |
| 3. | Visakhapatnam | 46.90 | 52.88 | 49.82 | 59.99 | 70.07 | 64.98 |
| 4. | East Godavari | 27.95 | 26.44 | 27.22 | 57.01 | 56.55 | 56.78 |
| 5. | West Godavari | 34.12 | 28.27 | 31.20 | 59.10 | 58.10 | 58.61 |
| 6. | Krishna | 33.21 | 39.83 | 36.49 | 62.71 | 70.98 | 66.89 |
| 7. | Guntur | 50.22 | 53.85 | 52.00 | 69.89 | 81.11 | 75.40 |
| 8. | Prakasam | 46.84 | 51.18 | 48.97 | 79.96 | 85.62 | 82.66 |
| 9. | Nellore | 41.89 | 38.52 | 40.27 | 78.03 | 79.69 | 78.82 |
| 10. | Kurnool | 32.07 | 33.54 | 32.77 | 58.68 | 57.77 | 58.25 |
| 11. | Anantapur | 17.80 | 20.74 | 19.25 | 46.78 | 50.10 | 48.37 |
| 12. | YSR Kadapa | 24.50 | 26.89 | 25.64 | 53.64 | 61.17 | 57.17 |
| 13. | Chittoor | 13.42 | 15.72 | 14.55 | 51.40 | 58.14 | 54.65 |
| 14. | Ranga Reddy | 53.15 | 60.00 | 56.48 | 75.88 | 81.21 | 78.31 |
| 15. | Hyderabad | 23.02 | 48.50 | 35.95 | 35.46 | 48.11 | 41.93 |
| 16. | Nizamabad | 58.91 | 62.69 | 60.71 | 80.23 | 87.23 | 83.41 |
| 17. | Medak | 66.37 | 73.10 | 69.48 | 80.19 | 86.73 | 83.00 |
| 18. | Mahabubnagar | 63.54 | 71.07 | 67.04 | 82.84 | 90.99 | 86.45 |
| 19. | Nalgonda | 58.37 | 68.13 | 63.06 | 77.89 | 84.19 | 80.74 |
| 20. | Warangal | 62.80 | 65.75 | 64.28 | 81.04 | 85.24 | 83.09 |
| 21. | Khammam | 32.86 | 35.27 | 34.05 | 61.62 | 66.60 | 64.09 |
| 22. | Karimnagar | 46.21 | 51.35 | 48.69 | 70.52 | 73.67 | 71.99 |
| 23. | Adilabad | 39.02 | 45.14 | 42.10 | 77.78 | 83.01 | 80.38 |
| Andhra Pradesh |  | 47.46 | 52.13 | 49.73 | 72.16 | 77.50 | 74.71 |

Source: Directorate of Economics and Statistics, Hyderabad.

http://www.aptribes.gov.in/bsdropout0506.html

Deprivation is also reflected through indicators of malnutrition, school drop-out, migration, etc. As per a report in the Hindu 6 May 2010, Andhra Pradesh has a high malnutrition rate of 53 per cent among boys and 35.6 per cent among girls, a dropout rate of 25 per cent among girls, 55.4 per cent girls married before they turn 18.

Vizianagaram district  is  relatively   backward in so  far  as  education  is  concerned.   The  literacy

rate      according  to  2001  census  was 51.07   per  cent  as  against  an   average  of  61.55  per  cent

for  the  entire  state  of  Andhra  Pradesh.   Out  of  34  mandals in the  district, only  11  mandals

have  the  literacy  rate  above  the  district literacy rate.  There  is  a  wide  gap  in the  literacy  rates

of  males and  females- 62.4  and 40.0  respectively.

Source: Director of Census Operation, Hyderabad and accessed  http://vizianagaram.nic.in/cpohandbook/Population.htm

In the state 11 districts had lower levels of human development as compared to the index value for the state of 0.537. Out of these, five districts (Warangal, Nizamabad, Adilabad, Nalgonda and Mahabubnagar) are in Telangana, three (Kadapa, Kurnool, Anantapur) in Rayalaseema and three (Srikakulam, Vizianagaram and Prakasam) in North and South Coastal Andhra.

Challenges and Opportunities for poverty alleviation:

A paper on Inclusive growth in Andhra Pradesh: challenges in agriculture, poverty, social sector, and regional disparitiestraces the growth of GDP in AP and suggests, that growth may be higher in thelast two decades but inclusive growth or equitable development has been missing. Important elements of inclusive growth are: agricultural growth, employment generation and poverty reduction, social sector (health and education) and reduction in regional and other disparities. There seems to be some 'turn around' in the gross state domestic product (GSDP) of A.P.in the last five years. The average annual growth rate was 6.9% during 2002-07 and 7.8%during 2003-07. However, there are problems in the four elements of inclusive growth. Growth of agriculture particularly crop sector is very low. Employment growth in the post reform period (1993-94 to 2004-05) is the lowest in the country. The recent data shows that literacy levels are also low as compared to many other states. The National Family Health survey (NFHS III) indicate that A.P.'s rank for infant mortality is 11 out of 17 states in

the year 2005-06.

Growth rates in district domestic product (DDP) and per capita DDP shows that 7 districts of Telangana (Ranga Reddy, Nizamabad, Khammam, Hyderabad, Mahbubnagar, Warangaland Medak) and 2 districts of North Coastal (Visakhapatnam and Srikakulam) recordedhigher growth rates than that of state average. On the other hand, all the districts in SouthCoastal and Rayalaseema and three districts of Telangana and one district of NorthCoastal showed lower growth than that of state average. However, one has to see the quality of growth in Telangana and Rayalaseema districts4.

Andhra Pradesh is known for introducing innovative poverty alleviation programmes. Apart from the general economic policies and bold policy initiatives, the targeted poverty alleviation programmes like Indira KranthiPatham (IKP) for women’s empowerment and ITDA Programme, Girijan Co-operative Corporation (GCC) undertook the guardianship of the tribals (Girijans) of Andhra Pradesh, INDIRAMMA programme for providing housing and other infrastructure, pensions, land distribution and health insurance (Arogyasri) are the other important programmes helping the poor in various dimensions. Besides increasing the budgetary  allocations, effective monitoring and improving delivery systems in poverty alleviation programmes help reduce the severity of poverty. Details of some of these programmes are presented in Section 1.7.

### Vulnerabilities

- Household Vulnerabilities

Dev (2007)4 identifies five problems of the social sector that contribute to household vulnerabilities.

First, the levels of social sector indicators in A.P. are much lower and progress has been slow than many other states particularly Southern states. The 61stRound NSS Survey provides literacy rates at state level for the year 2004-05. It shows that Andhra Pradesh literacy levels are very low as compared to other states in India. Among 20 states, A.P. has the lowest literacy level for rural males. The ranks of A.P. for rural females, urban males and urban females were respectively 16th, 17thand 17th ranks among 20 states. On the other hand, the rank of Tamil Nadu for rural females and urban females were respectively 5th and 6th ranks.

The general education level of population in A.P. indicates that 74% of rural males and 86% of rural females were either illiterate or literate or educated upto primary level only (Table 21). Only 7% of rural females were educated upto secondary and above.

Percentage of Population by General Education Level,  2004-05

|  | Andhra Pradesh |  |  |  | All India |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rural Male | Rural Female | Urban Male | Urban Female | Rural Male | Rural Female | Urban Male | Urban Female |
| Not Literate | 44.2 | 60.9 | 23.3 | 37.5 | 36.4 | 55.0 | 19.5 | 30.7 |
| Literate &upto primary | 30.0 | 25.0 | 28.9 | 28.6 | 36.1 | 29.3 | 30.0 | 29.4 |
| Middle | 12.5 | 7.4 | 13.5 | 12.1 | 14.0 | 8.9 | 16.0 | 14.4 |
| Secondary & above | 13.3 | 6.6 | 34.3 | 21.8 | 13.4 | 6.7 | 34.5 | 25.5 |
| All | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |

Source: 61st Round NSS Survey, Report no.515

Regarding health indicators, infant mortality declined from 70 per 1000 in 1992-93 to 53 per 1000 in 2005-06. Inspite of decline, the rank of A.P. ininfant mortality is only 11 among 17 states in the year 2005-06. The levelof infant mortality in A.P. (53) is much higher than Kerala (15), Tamil Nadu(31) and Karnataka (43). In fact, the progress in Karnataka is much fasterthan A.P.

Infant Mortality at State Level, 2005-06

Though the  IMR of the state declined from 106 in 1971 to 54 in 2007, it is still at an  unacceptably high level.  Further, it is still the highest amongst the other southern states.

In the case of malnutrition among children, the percentage of underweight children declined from 45% in 1992-93 to 37% in 2005-06. Similarly there was some decline in stunting also. But the progress has been slow. The rank of A.P. in malnutrition among children is 6th out of 17 states.

Regarding incidence of malnutrition among women, it is 33.5% for the general population in Andhra Pradesh and 38.4% among SC/ST. The levels of A.P. are lower than Karnataka but higher than Tamil Nadu and Kerala. There are significant regional, social, rural-urban and gender disparities in social sector indicators.

Third one is low public expenditures in health and education. Allocation of funds to  social sector expenditure is lower in the post-reform period as compared to pre-reform period.

Fourth, it is true that delivery systems are in bad shape in both education and health. Infrastructure and the quality of services are poor in both thesectors. The most difficult thing is to ensure good quality of instruction. A study facilitated by NGO Pratham has found 38% of the children whohave completed four years of schooling at all India level cannot read a small paragraph with short sentences meant to be read student of class II. About 55% of such children cannot divide a three digit number by a one digit number (GOI, 2006). Similar problems can be seen in A.P. also. Also quality of secondary and higher education have to be improved

PDS off-take is another other indicator of household vulnerability. The percentage share of different components in the rice & wheat basket of BPL respondents from Andhra Pradesh in a 2005 performance evaluation of the targeted public distribution system was 31.1. Market purchase was 61.6, own production was 2.1 and other sources was 5.2. The report goes on to show that the market price  as percentage of PDS (as declared by BPL respondents) in Andhra Pradesh for rice-2001 was 160.7% and for wheat-2001 was 116.7%. The effective income gain for BPL household was ₹605.03 in Andhra Pradesh.

According to estimations in NFHS III (2005-2006), in AP, about 42.7%, 12.2% and 32.5% of children below 5 years of age were respectively characterized as stunted, wasted and underweight while the all

India averages were 48.0%, 19.8% and 42.5%. Close to 10% children under the age of 5 were severely malnourished in AP. Malnutrition among women is also a matter of concern for the state.   About 24% women suffer from anemia in the state which is far higher than the national average of 17% as per NFHS II.

The largest percentage-(73%) of female headed households are headed by Widows. It may also be noted that over 30% of the household are headed by women over the age of 60.  This indicates the necessity of creating safety nets such as pensions for the older women in addition to productive livelihood options for the younger women in order to enable them to support their families.

- District/ State Level Vulnerabilities

Andhra Pradesh, given its size, population and large coast line is vulnerable to many natural hazards.

Andhra Pradesh (AP) being 4th largest state in India by area of 2,75,608 km²and 5th largest in population with over 100 million and a density of277 persons/km2 is spread over 23 districts.The state has a coast line of 1030 kms and 2482 villages are along the coast line having the population of

3,15,70,722. The estimated loss during the cyclones is in crores. Nine out of 23 districts in AP suffer from severe drought frequently. These districts have a population of about 30 million and they account for about 70% of state-wide crop production loss due to drought. Though AP is in peninsular India it has experienced considerable earthquakes of magnitudes greater than 5.0. the other major concern for the state is the long coast line along the Indian ocean has very active faults. Many fire accidents are occurring in the state resulting in loss of life and property also. The tsunami occurred on 26th December 2004 has effected 9 districts along the coast line see the list below in the table.

Nearly 29 million people are vulnerable to cyclones and their effects in coastal AP, 3.3 million of people belong to the communities located within five km of the seashore.

Drought: Andhra Pradesh is one of the states in India which has historically been most severely affected by drought. The failure of monsoons has had a disastrous affect on the states’ sizable agriculture sector and a large share of the population dependent on agriculture for livelihood7. Of the project district not vulnerable to droughts.

Health: Vector Borne diseases: Vizianagaram district is vulnerable to malaria; overall state is vulnerable to Dengue and Chikanguniya.

Vulnerabilities affecting tribal populations

Tribal populations in Andhra Pradesh are more vulnerable that the general population. Data shows that tribal areas fare worse on all socio-economic indicators than general areas, as reflected in Table 14

Comparison of demographic, socio-economic indicators between general and tribal areas

Source: Tribal Welfare Department AP, April 2006

AP has chosen social mobilization and inclusiveness as methods of addressing poverty alleviation and promotion of livelihood interventions.  ‘Society for Elimination of Rural Poverty

(SERP), was established by the Government of AP as a sensitive support structure to facilitate

social mobilization of the rural poor women. SERP implements the ‘Indira Kranthi Patham (IKP)’

which aims at social mobilization to enhance livelihoods and employment generation

opportunities for the poor.

SERP has relentlessly worked towards the inclusion of socially backward sections of the society into the SHG movement to improve their livelihoods.  The result is that, as on today, SCs and STs have been able to enjoy the benefits of SERP. There are about 10 lakh women SHGs in Andhra Pradesh covering

nearly 1.1 Crore rural poor women. An amount of Rs. 5070.51 crores  has accumulated as  corpus among these groups and these SHGs have an accumulated Savings Rs. 3383.10 as on March, 2011.

Context of Social Inclusion and Social Mobilisation

Andhra Pradesh, one of India's poorest states, has used development self-help groups (SHGs) extensively as a primary tool of poverty alleviation and empowerment. National and state government initiatives, as well as NGO efforts, have used SHGs to implement poverty alleviation programs in Andhra Pradesh since 1979. Self-help groups also empower poor women, more than 4.8 million of whom are mobilized into SHGs. Early programs sought to provide self-employment, empower, and incorporate rural poor women into the development process.

Following on successes in earlier programs, which were modified to make them more meaningful, the state has promoted significant increases in SHGs using a social mobilization approach. The state-sponsored Velugu program working in over 860 mandals (sub-district geographical unit) in 22 districts, aims to reach 2.9 million of the poorest of rural poor. Both the number and structure of self-help groups in Andhra Pradesh has been scaled up. The state established an independent support organization to implement poverty elimination projects which aim at social mobilization to enhance livelihoods and employment generation opportunities of the poor. Self-managed grassroots institutions have been federated into village level and sub-district level groups. These groups provide an organizational identity to help SHGs realize the benefits of a larger organization without losing the advantages of small organization. Federations of SHGs are fast becoming powerful voices expressing the social and economic needs of the poor.

A number of social issues including gender and family, child labour, disability and health related to poverty alleviation need to be addressed in the context of SHGs. SHG formations largely take place around women since women are seen as more credit-worthy than men. But the process of empowerment and poverty alleviation can be more sustainable when all the members of the family are involved. Hence women's groups are taken as an entry point for the formation of men's groups, youth groups, children groups, and groups for the physically challenged. Innovative, action research interventions using folk theatre have addressed family issues related to gender division of labour in the house, son preference and relationships between mothers-in-law and daughters-in-law. Velugu addresses child labour and high dropout rates through regular campaigns to sensitize parentsespecially mothers, youth, other community members and school teachers about the importance of education and its long-term implications for child welfare and poverty reduction. Velugu also aims to directly address the problems of the disabled by organising them into mutual support groups. Velugu plans a holistic approach to community based primary health care to empower people and communities to take care of their own health and take responsibility for the community's health.

There is absolutely no doubt that SHGs have lead to an expansion in the economic spaces of members. However the composition of the members reveals that the coverage of the poorest of- the-poor is low, while the coverage of non-poor is considerable. The financial status of households and savings capacities has improved due to improvement in access to formal credit institutions, since SHGs are linked with banks. Access to credit has enabled women to undertake economic activities, which tend to be an expansion or strengthening of existing traditional activities. A smaller proportion of women have taken up new occupations. The diversification of occupation to non-agricultural activities has enhanced the quality of income of the households by reducing the dependency on risk-based agriculture. Increases in income have been spent on better nutrition for the children and on health care for the family.

IKP-SERP continued sustained efforts, coupled with a very high level of participation of the communities have resulted in mobilization of more than 90% of eligible rural households into the project fold. Table below depicts the status of Social Mobilization highlighting the focus on SC/STs and the Persons with Disabilities (PwDs), indicating the social inclusiveness approach adopted by the Project.

In Andhra Pradesh, the linkages between different approaches towards development, poverty reduction and empowerment must be considered. It is not enough to address the economic indicators of poverty. While incomes have to be augmented through livelihood generation interventions, for which credit is an important component, determinants of human poverty in terms of health and education requirements require attention. Likewise, social poverty, which manifests in the presence of corrosive evils like caste taboos, norms of dowry, adherence to vices such as alcohol and drugs have to be woven into empowerment programs. The primary lesson learned from the Andhra experience is that there is value in using self-help groups as a conduit for poverty alleviation initiatives. However one has to understand the limitations of this use and gauge the ways in which these can be surpassed to get more out of such an approach.

Context of Financial Inclusion

The SHGs in AP constitute 25% of all SHGs in the country. The SHG-Bank linkages is a great success story in AP. 25 Commercial Banks, 16 Regional Rural Banks and more than 4,000 branches are participating in the programme. Bank lending has dramatically increased from ₹197.7 crores in 2001-02 to ₹5,882.79 crores in 2007-08. AP leads the country in SHG-Bank Linkage programme with 50% of all bank loans given to SHGs in India and recovery of SHGs loans is above 98%.

SERP has relentlessly worked towards the inclusion of socially backward sections of the society into the SHG movement to improve their livelihoods. The result is that, as on today, SCs and STs have been able to enjoy the benefits of SERP. Brief details of social inclusion at SERP are given in Table below- Social Category wise beneficiaries of IKP 2010-11.

Table below give the details of savings and loans disbursed amount to SHGs. Table 18 shows that AP performs well in repayment by SHGs.

Progress under Microfinance – Savings of SHGs with Banks Region-wise / State-wise / Agency-wise position as on 31 March 2012 (in₹lakh)

|  | Commercial Banks |  | Regional Rural Banks |  | Cooperative Banks |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. of SHGs | Saving Amount | No. of SHGs | Saving Amount | No. of SHGs | Saving Amount | No. of SHGs | Saving Amount |
| Andhra Pradesh | 10,62,591 | 1,14,991.38 | 4,05,904 | 31,827.84 | 27,409 | 2,196.34 | 14,95,904 | 1,49,015.56 |
| All India | 46,18,086 | 4,15,298.04 | 21,27,368 | 1,30,013.93 | 12,14,895 | 1,09,829.49 | 79,60,349 | 6,55,141.45 |

Source: Status of Micro-Finance in India 2011-12, NABARD; accessed at http://www.nabard.org/departments/pdf/Status%20of%20Microfinance%202011-12%20full%20book2.pdf  on 29 December 2012

Progress under Microfinance - Bank Loans disbursed during the year Region-wise/ State-wise/ Agency-wise position during the year 2011-12 (in₹lakh)

|  | Commercial Banks |  | Regional Rural Banks |  | Cooperative Banks |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. of SHGs | Loans disbursed Amount | No. of SHGs | Loans disbursed Amount | No. of SHGs | Loans disbursed Amount | No. of SHGs | Loans disbursed Amount |
| Andhra Pradesh | 2,56,040 | 5,38,466.73 | 1,15,843 | 2,65,267.56 | 6,643 | 13,407.76 | 3,78,526 | 8,17,142.05 |
| All India | 6,00,807 | 9,94,204.49 | 3,04,809 | 5,02,605.15 | 2,42,262 | 1,56,667.23 | 11,47,878 | 16,53,476.87 |

Source: Status of Micro-Finance in India 2011-12, NABARD; accessed at http://www.nabard.org/departments/pdf/Status%20of%20Microfinance%202011-12%20full%20book2.pdf  on 29 December 2012

Progress under Microfinance - Non-Performing Assets against Bank Loans to SHGs

Amount ₹ lakh

|  | Private Sector Commercial Banks |  |  | Public Sector Commercial Banks |  |  | Regional Rural Banks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Loan Amount O/S against SHGs | Amount of Gross NPAs against SHGs | NPA as %age to Loan O/S | Loan Amount O/S against SHGs | Amount of Gross NPAs against SHGs | NPA as %age to Loan O/S | Loan Amount O/S against SHGs | Amount of Gross NPAs against SHGs | NPA as %age to Loan O/S |
| Andhra Pradesh | 919.22 | 63.55 | 6.91% | 1116555.60 | 40289.19 | 3.61% | 409352.54 | 12306.33 | 3.01% |
| All India | 140371.51 | 7436.73 | 5.30% | 2440657.35 | 158104.83 | 6.48% | 861357.81 | 42634.18 | 4.95% |

|  | Cooperative Banks |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Loan Amount O/S against SHGs | Amount of Gross NPAs against SHGs | NPA as %age to Loan O/S | Loan Amount O/S against SHGs | Amount of Gross NPAs against SHGs | NPA as %age to Loan O/S |
| Andhra Pradesh | 7344.90 | 440.78 | 6.00% | 1534172.26 | 53099.85 | 3.46% |
| All India | 191613.51 | 13097.44 | 6.84% | 3634000.18 | 221273.18 | 6.09% |

Source: Status of Micro-Finance in India 2011-12, NABARD; accessed at http://www.nabard.org/departments/pdf/Status%20of%20Microfinance%202011-12%20full%20book2.pdf  on 29 December 2012

During 2003, APMAS conducted a study on SHG – bank linkage in Andhra Pradesh covering a sample of 400 bank linked SHGs. The study clearly indicated that the repayment rates were high and that the bank linkage made difference in the lives of the SHG members.  However, the study also pointed out certain issues that require attention.  These include adequacy of loan size, timeliness of credit and also the need for branch manager or the promoter undertaking a rating before the SHG is bank linked.  The following were the major findings of the study:

- Average Savings per SHG – ₹23,000, average loan size ₹31,000.

- 50% of SHGs practice equal distribution of bank loan.

- Only 50% SHGs felt that the loan size was adequate and 54% studied SHGs were first time linked.

- 69% of SHGs got RLF, some got from multiple sources.

- It takes more than four months for an SHG to get a bank loan.

- No post linkage follow up by banker and others.

- 66% of bank linked SHGs are A grade as per CRI

- Only 22% of bank linked groups are appraised by banker, etc.

- Idle fund of  bank linked SHGs average – ₹5,300

- Leaders dominate and have 30% loan on them.

- 12% SHG default to banks – repayment problem.

- 10% SHGs reported that they were forced to take loan.

- High percentage of SHGs participate in Government Programs.

- Bankers attitude is still an issue.

Insurance and Pension

Insurance and pension services by the GoAP are under the Social Security Pension, Abhaya Hastam, Indira Jeevitha Bima Pathakam and loan insurance schemes.

The Society for Elimination of Rural Poverty in AP (SERP), established by GoAP, seeks to enable the disadvantaged communities perceive possibilities for change and bring about desired change by exercising informed choices through collective action. It has implemented various insurance and pension schemes to support poor and vulnerable communities.

| S.No | Mandal | S.T(No.) | S.T(%) | S.C(No.) | S.C(%) | B.C(No.) | B.C(%) | O.C(No.) | O.C(%) | Min(No.) | Min(%) | N.A(No.) | N.A(%) | Total Pensioners |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Komarada | 2,097 | 34.64 | 855 | 14.13 | 2,831 | 46.77 | 267 | 4.41 | 3 | 0.05 | 0 | 0 | 6,053 |
| 2 | Gummalakshmipuram | 3,922 | 89.77 | 217 | 4.97 | 133 | 3.04 | 97 | 2.22 | - | 0 | 0 | 0 | 4,369 |
| 3 | Kurupam | 3,459 | 71.61 | 331 | 6.85 | 706 | 14.62 | 322 | 6.67 | 12 | 0.25 | 0 | 0 | 4,830 |
| 4 | Jiyyamma Valasa | 1,322 | 18.38 | 711 | 9.89 | 4,741 | 65.93 | 416 | 5.79 | 1 | 0.01 | 0 | 0 | 7,191 |
| 5 | Garugubilli | 157 | 2.49 | 685 | 10.86 | 5,200 | 82.41 | 261 | 4.14 | 7 | 0.11 | 0 | 0 | 6,310 |
| 6 | Parvathipuram | 953 | 15.41 | 698 | 11.29 | 4,067 | 65.78 | 459 | 7.42 | 6 | 0.1 | 0 | 0 | 6,183 |
|  | Total | 23,295 | 8.65 | 24,683 | 9.17 | 2,03,786 | 75.7 | 16,321 | 6.06 | 1,102 | 0.41 | 0 | 0 | 2,69,187 |

Government of Andhra Pradesh introduced Pension and Insurance Scheme for the Indira Kranthi Patham(Rural and Urban) SHG women in November 2009 to provide income security in their old age. The aim was to provide security to all enrolled SHG women with dignity in their old age.

n addition to SHGs, micro-finance institutions also serve the financial needs of the communities.

Statistics on MFIs in AP, as on 31 March 2012

Total no. of MFIs operating in the state= 40

Banks providing microfinance services=46

(Public Banks=20, Private Banks=4, RRBs=5, DCCBs=17)

Total no.of SHGs under SBLP (SHG Bank Linkage Programme) in the state=14,66,225

Total savings - client outreach=2,05,27,150

Total SHG - savings with banks(in lakhs)=1,30,780.22

Total credit - client outreach=2,74,33,360

(MFIs=37,20,272, Banks= 2,37,13,088)

Total portfolio outstanding(in lakhs)= 17,51,141

(MFIs=4,14,228.71, SHG=13,36,912.29)

No. of districts served by MFI= 23

Out of which no. of poorest districts= 19

Source: "The Bharat Micro Finance Report - Quick Data 2012" - as on 31 March 2012

Challenges of financial inclusion

Andhra Pradesh has medium level of financial inclusion.

Despite the noteworthy accomplishments of SHGs certain issues, such as, inadequate outreach in many regions, delays in opening of SHG accounts and disbursement of loans, impounding of savings by banks as collateral, non-approval of repeat loans by banks even when the first loan was repaid promptly, multiple membership, borrowings by SHG members within and outside SHGs, adverse consequences of unhealthy competition between NGO promoted SHGs and Government promoted/subsidy oriented SHGs and limited banker interface and monitoring continued to affect the programme in many areas.

For MFI's, the conceptual framework underlying MFIs requires a change, more so in the context of serious challenges the sector faces in post Andhra crisis phase. These institutions have to revisit their business models to support the income earning ability of the borrowers and, at the same time, themselves remain economically viable. MFIs will have to work hard in pursuit of transparency and responsible finance, shaking off the perception that their motto is profiteering at the cost of the poor but not profitability for sustainable and viable growth. MFIs will also have to take initiatives to retool the product redesign for garnering new customers and acquiring more share of the market. At the same time they need to re-engineer the customer responsive processes so as to create a favourable climate for doing business. MFIs will have to revisit the mission and business strategy and reinvent the sector to remain relevant in the system. Creation of a new category of MFI-NBFC under the framework prescribed by the Malegam Committee, more nuanced appreciation by the financing banks of the difficulties being faced by some of the MFIs despite having responsible and sustainable business model, greater sense of responsibility in the sector as evident from the code of conduct being voluntarily accepted by the MFIs and the Microfinance legislation which is in the offing, possibly hold key to future success and sustainability of the MFIs.

Lastly, the coverage of tribal communities under financial security needs to be strengthened.

Livelihood Context

The economy and livelihood practices of the tribals are closely associated with the ecological factors and habitats which they inhabit. Tribal livelihoods have been changing in recent years, mainly due to external factors which have displaced tribals from their lands, or made traditional livelihoods unviable or illegal. Tribals are traditionally hunters and gathers, subsisting on the bounties of the forest - also known as Non-Timber Forest Produce (NTFP). For instance, in the proposed project district the forest dwelling tribes traditionally tap gum (gum karaya), Tamarind, Amla, Adda leaves for sales to earn their livelihood. The gum collectors need to trek deep into the forests as these trees are found in the wild and only on the hill slopes.

The tribal economy, however, is in a state of transition. The complete isolation of the past has long since passed; interaction with and dependence on the outside is gradually increasing. However, being backward and illiterate, the tribals are ill-prepared to deal with the outer world, and thus fall easy prey to exploitation by the non-tribal traders. Due to low productivity and lack of food security, the tribals have become dependent on the traders. But price manipulation and indiscriminate money lending has led many tribals into a debt trap from which they cannot escape. This has been due to the deterioration in the tribal eco-system which means that the former survival strategies have become less sustainable. Thus, the tribals are in a transition phase from a forest centered lifestyle to a rural, settled cultivation lifestyle, but the production from agriculture is not commensurate with the food requirements, whilst the scope for supplementation by way of intake of natural foods is diminishing due to depletion of the forests. The tribals are caught in a situation where they are on the one hand losing command over the natural resources, and are unable to take command over the new resources at their disposal on the other13.

In addition, tribes also engaged in shifting, slash and burn cultivation, traditionally known as podu cultivation. This cultivation has been critical for their food security, but has been a contentious issue between the communities and authorities (forest departments).

Large development projects have displaced tribals from their lands. Displaced tribals have to leave their forests and lands which are their livelihoods and have few skills to take up other work.

The economy of the tribals in AP is a consumption-subsistence economy with its main occupations being settled agriculture, podu (shifting) cultivation and collection of Non-Timber Forest Produce (NTFP), which totally comprise 88% of their occupation status. A vast variety of food grains, millets, pulses like rice, ragi, maize, jowar, legumes, vegetables and fruits are cultivated in the valleys and uplands/hills most of which are consumed domestically.

The challenge to livelihoods of tribal communities in the proposed project area is that main workers among the STs are declining Chitoor and East Godavari districts, and marginalisation is increasing significantly across all the proposed districts. This points to the economic vulnerability of the STs, who had worked less than 6 months in the period of reference. This economic marginalisation would have implications on food security, health and education.

District-wise Scheduled Tribe Workers according to activity status in Andhra Pradesh as per 1991 and 2001 census

|  | 1991 |  |  |  |  | 2001 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Culti-vators | Agriculture Labourers | Manu-facturing Households | Total Main Workers | Total Marginal Workers | Culti-vators | Agriculture Labourers | Manu-facturing Households | Total Main Workers | Total Marginal Workers |
| Andhra Pradesh | 8,77,806 | 9,92,358 | 55,786 | 21,30,981 | 1,38,132 | 8,80,153 | 8,98,214 | 61,326 | 21,46,002 | 5,59,634 |
| Proposed District |  |  |  |  |  |  |  |  |  |  |
| Vizianagaram | 38272 | 52837 | 2838 | 100623 | 10501 | 31302 | 51291 | 3046 | 96317 | 27862 |

Source: http://www.aptribes.gov.in/bsworkers9101.html

### Non-Timber Based Forest Produce:

Non Timber Forest Products (NTFPs) contributing to rural livelihoods and alleviating rural poverty is well known. It is estimated that about 100 million people especially communities living inside and on the fringes of forest areas depend on NTFP for food, shelter, medicine, cash income etc. In many states NTFPs contribute major proportion of the revenue of the State Forest Departments, for instance, during the last 5 years more than 70 percent of the revenue of Orissa Forest Department was contributed by NTFP. The states of Madhya Pradesh, Chhattisgarh, Orissa, Maharashtra and Andhra Pradesh account for more than 75 percent of traded NTFP in India.

NTFPs are an important source of livelihood for large sections of rural communities; particularly those living in forest fringe villages. The Government revenue realised  from NTFPs is in the order of Rs 20 billion per year. However the returns to  communities from collection of forest produce is typically very low as compared to  value of the final products.

The tribal communities across the country are largely dependent on Non Timber Forest produce (NTFP) collection as a major source of their livelihoods. Almost round the year, NTFP (also known as Minor Forest Produce or MFP) collection, though often insufficiently remunerative, remains a regular economic activity for them. In fact NTFP collection moderates the seasonality of income for the poor tribal community by providing income during slack seasons. Lack of choice makes the dependence of tribal communities on NTFP collection almost irreversible phenomenon. It is also a well acknowledged fact that the involvement of women in this particular livelihoods activity is extremely high in India.

Tribals depend on NTFP for their livelihood. Survey in Andhra Pradesh shows that on an average, tribals derive 10- 50 percent of their income from NTFP. Beedi leaves, gum, karaya, adda leaves, broom, tamarind, soap nuts, are among the important NTFP available in the state .

The NTFP dependent population per hectare of forest cover probably have remained almost constant or might have even gone up in the last quarter of a century. With dwindling forest cover and without any significant decrease in the number of poor dependent on NTFP collection, the issue of alleviating the livelihoods of the poor especially the tribal women engaged in NTFP collection becomes extremely challenging. The existing regulatory framework though underwent some remarkable changes in recent times at national and state level, still, due to various factors, does not help much to the cause. Government policies over a period of time have only created a large monopoly without really addressing the key issues plaguing the poor NTFP collectors. Ownership, price fixation, value addition and marketing of NTFP remain key issues and the NTFP collectors have hardly any role in determining these thus subjecting them entirely to the mercy of external factors without any bargaining power. Though NTFP collectors are the most important and critical actors in the NTFP value chain, they have no control over the NTFP value chain. Besides, one of the biggest challenges still is how to address the over exploitation of the forest resources again compounded by the unsustainable collection practices prevailing in most part of the country. One hand the livelihoods of some of the most vulnerable groups of the society is under threat and on the other sustaining the bio diversity and preserving the eco system remains a major cause of concern.

Today the biggest challenge in NTFP value chain is the complete asymmetry of knowledge and information. This calls for dedicated efforts to address imperfections in NTFP value chain at various levels- regeneration, collection, value addition & marketing- keeping the interests of the poor NTFP collector at the centre. 2 NTFP Collectors are tribal communities mostly from Central India and maximum NTFP resources are located in LWE areas. With lack of Technology and Market information/access the tribal communities are unable to realize major part of total value realized. Although NTFP sub-sector has a growing market with ₹3200 Crore as current exports, only around 25% of this value is reaching the NTFP collectors at present. This is despite the fact that only 30% of total NTFP export is value added. NTFP value chain in India is still a 1st generation issue in India. We are also importing large quantity of NTFP commodities. Clearly the potential for unlocking the value for NTFP collectors is immense. Critical linkages between production and use should be worked out in favour of NTFP collectors. Entire NTFP sector is unorganized and needs to be organized for higher efficiency.

Effective use of ICT has helped the agriculture sector immensely. Farmers can now know the market prices real time seating in their villages with the help of mobile based technology. Dissemination of knowledge and information has become less challenging due to the extensive use of ICT. There are now many more models like e-choupals that are bringing all the services, extension, price information, best practices at the farmers’ door steps. Promoting the ICT to deliver similar services to the NTFP collectors will be a key to make a significant impact in their lives.

Encouragingly, there are many interventions, initiated during last two decades in various parts of the country have yielded significant positive results on both the account. Some of these interventions could address market imperfections through interventions on different points of the NTFP value chain; some of them were extremely successful in regeneration and some in both. But what is common in all these interventions is the strong focus on building the institutions of the NTFP collectors especially women. The SHGs of women whether in Odisha, MP or AP have demonstrated the capacity of poor women to play very strong role in the NTFP value chain starting from regeneration of species to marketing of value added products. These SHGs federated into higher level institutions like village organizations and even block and district level federations.

These institutions of poor women could become a sustainable singular platform to address many pressing issues, from women empowerment to economic empowerment. Moreover these institutions could address acute food insecurity during lean seasons by effectively implementing interventions like rice credit line where women could borrow on a favourable terms from their groups for buying food grains. This could also help them avoid distress sale.

State policy on NTFP is also inconsistent with the goal of tribal protection. NTFP policy of individual states is not consistent with this. For instance, in the State of Andhra Pradesh, Girijan Co-operative Corporation (GCC) was set up to give monopoly to the state over NTFP under a law called A.P. Scheduled Areas Minor Forest Produce (Regulation of Trade) Regulation, 1979. These regulations impose restrictions on the purchase, sale, curing, processing, storage and transport of any NTFP. Another factor also adversely affects the price procured by the tribals in Andhra Pradesh - the influx of similar types of stocks from border areas of neighbouring states such as Orissa, Chhattisgarh and Madhya Pradesh. Tamarind and adda Leaves from Orissa and Madhya Pradesh have increased the supply of the products resulting in a fall in the price.s

The women SHG federations also have become precursor to the building of strong livelihoods organizations around NTFP collectors. These livelihoods collectives with enhanced bargaining power could negotiate better with market forces ensuring higher prices and could also take up various value addition activities in moderate scale. They got involved in better and sustainable harvest practices and hygienic 3 post-harvest practices fetching them better realization from their produce. All these ensured that the economic activities around NTFP became remunerative.

One of the most significant outcomes of the process has been the emergence of a cadre of confident and smart community persons who are the best practitioners and could take lead in scaling up the interventions in situ.

These interventions have successfully demonstrated that an intervention designed around strong institutions of the poor NTFP collectors driven from within by the community resource persons can help building sustainable livelihoods around NTFP and MAP.

### Agriculture and Allied Activities (horticulture, etc.)

Agriculture is the main livelihoods of the rural community in AP. Andhra Pradesh grows mainly four crops, cotton, paddy, maize and groundnut, all through the year. In fact, according to government statistics, these crops make up for 70% of the state's total cultivable land. Capturing the largest share of land are cotton and paddy, most of them genetically developed breeds, which cover almost 104 lakh acres of the area. So much so that AP, as per national records, now produces 80% of the country's hybrid rice.

Area under rice mostly depends on the monsoon pattern and availability of water in reservoirs.  Area under rice was high during 2008-09 (43.87 l.ha) and lowest is in 2002-03 (28.22 l.ha). There is no scope for increasing area under rice and rice area is replaced by some profitable dry crops due to in sufficient water.  Rice is grown in 28% of gross cropped area and 50% of area under food crops round the year in all the districts. Though there is a rise and fall of area and production of rice based on water availability, but there is a constant increase in productivity. In the context of food security such decline in area and production is not good to meet the future rice requirement. In the coastal districts the area under rice is declining because of aquaculture activities.

The tribals in the state, in general, belong to small and marginal farm categories. The total number of tribal holding as per 1985-86 Agricultural Census is 7,648, which constitutes less than 8% of the total holdings in the state. In terms of area, the STs operate 17,234 thousand hectares which is a little more than one-tenth of the total operated area in the state. Transition phase from a forest centered lifestyle to a rural, settled cultivation lifestyle, but the production from agriculture is not commensurate with the food requirements, whilst the scope for supplementation by way of intake of natural foods is diminishing due to depletion of the forests.

Land Utilisation in the project district - Vizianagaram given below in the table.

| Sl. No. | Category | Area in Hectares |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2006-07 | 2007-08 | 2008-09 |
| 1 | Total Geographical Area | 6,53,900 | 6,44,076 | 6,53,900 |
| 2 | Forests | 1,19,303 | 1,19,303 | 1,19,303 |
| 3 | Barren & Uncultivable Land | 76,104 | 67,658 | 73,858 |
| 4 | Land put to Non-Agricultural uses | 77,320 | 76,509 | 77,320 |
| 5 | Cultivable Waste | 4,163 | 4,432 | 3,826 |
| 6 | Permanent pastures and other grazing lands | 5,760 | 8,683 | 4,899 |
| 7 | Land under Miscellaneous tree crops & Groves not included in net area sown | 7,898 | 6,342 | 10,607 |
| 8 | Current Fallows | 24,004 | 17,387 | 37,590 |
| 9 | Other Fallow lands | 27,677 | 20,526 | 24,574 |
| 10 | Net area sown | 3,11,602 | 3,23,167 | 3,01,923 |
| 11 | Total cropped area | 4,12,541 | 4,42,588 | 4,05,544 |
| 12 | Area sown more than once | 1,00,939 | 1,19,421 | 1,03,621 |

source: Chief Planning Officer, Vizianagaram; http://vizianagaram.nic.in/cpohandbook/Agriculture.htm

Land use pattern in Tribal Sub-plan area of Andhra Pradesh and in the Project District.

| District | Total Geographical Area | Forests | % of Forests to total Geographical Area | Barren and Un-cultivable land | Land put to non-agri-cultural use | Permanent pastures and Grazing lands | Miscella-neous, trees, crops and groves | Cultivable waste land | Other fallow lands | Current fallows | Net area sown | % of net area to the total geographical area |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vizianagaram | 2.85 | 1.77 | 62.19 | 0.32 | -- | -- | 0.02 | 0.14 | 0.09 | -- | 0.5 | 17.54 |
| AP | 85.87 | 53.3 | 62.07 | 3.66 | 2.25 | 2.12 | 1.61 | 3.21 | 2.06 | 2.52 | 15.14 | 17.63 |

Source: TCR & TI, Hyderabad; http://www.aptribes.gov.in/bslandusepattern.html

Agriculture is one of the livelihoods sources of tribals. However, most tribals have marginal and small land holdings.

District-wise Number of Operational Holdings and Area Operated by Scheduled Tribes (2005-06) - in hectares

| District | Marginal (upto 1.0 Hect) |  | Small (1.0 - 2.0 Hect) |  | Semi Medium (2.0 - 4.0 Hect) |  | Medium (4.0 - 10.0 Hect) |  | Large (upto 10.0 and above) |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. | Area | No. | Area | No. | Area | No. | Area | No. | Area | No. | Area |
| Andhra Pradesh | 5,12,390 | 2,47,894 | 2,31,753 | 3,26,492 | 1,37,073 | 3,59,826 | 42,454 | 2,33,725 | 3,071 | 44,020 | 9,26,741 | 12,11,956 |
| Vizianagaram | 25221 | 11161 | 7626 | 10594 | 3101 | 8246 | 881 | 4891 | 59 | 807 | 36888 | 35699 |

Source: http://www.aptribes.gov.in/bsholdings0506.html

ANNUAL RAINFALL, STATION-WISE - in the Project Locations

| Sl. No. | Name of the Mandal | Normal | Actual |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2006-07 | 2007-08 | 2008-09 |
| 1 | Komarada | 1283 | 1654.1 | 1240.6 | 700.7 |
| 2 | G.L.Puram | 1201 | 1818 | 1525.3 | 944 |
| 3 | Kurupam | 981 | 1045.9 | 893.9 | 508.2 |
| 4 | Jiyyammavalasa | 1190 | 1417.9 | 1123.9 | 928.4 |
| 5 | Garugubilli | 1239 | 1608.5 | 1372.8 | 876.6 |
| 6 | Parvathipuram | 1228 | 1631.8 | 1511.6 | 1219.9 |

| Vizianagaram District and AP distribution of Scheduled Tribe holdings receiving Irrigation - Source-wise - 2001 census |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Total Holdings |  | Canals |  | Tanks |  | Wells |  | Tube Wells |  | Other Sources |  | Excl. No. of Holdings Receiving Irrigation | Net Irrigated Area |
|  | No. | Area | No. | Area | No. | Area | No. | Area | No. | Area | No. | Area |  |  |
| Vizianagaram | 34568 | 35517.9 | 1187 | 880.02 | 4714 | 2301.93 | 298 | 104.12 | 864 | 684.09 | 4174 | 3107.92 | 11169 | 7078.07 |
| AP | 862738 | 1185996.7 | 57493 | 36780.48 | 79365 | 50503.83 | 36269 | 31539.56 | 77670 | 65341.83 | 65338 | 65276.47 | 305253 | 249441.96 |
| Source: Directorate of Economics and Statistics, Hyderabad; http://www.aptribes.gov.in/bsirrigation5.html |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Majority of the tribal farmers grow the paddy crop in wetlands during kharrif season.  Mixed cropping pattern (pulses, millets and oil seeds) is a dominant feature in both dry and podu cultivation.  Draft animals drawn wooden plough is the major technology used in both dry and wet cultivation.  Cattle dung and green manure are used for fertile the soil in these two types of farmings.  The tribals still use the local variety of seeds and seedlings in all kinds of farms.  Weeding is done manually.  In the harvesting of the crops, the tribals use the sickle to cut the stalk.  The thrashing is done with the help of draft animals  or manually.  The food grains are stored in bamboo bins or in big clay  pots for future use.

In Andhra Pradesh state, shifting cultivation is extensively practised in the districts of Visakhapatnam, Srikakulam, Vizianagaram, East Godavari, West Godavari, Warangal and Khammam and sparsely in Adilabad district17.

Andhra Pradesh with high geographical diversity, seven agro-climatic zones, varied soil types and good irrigation resources is better placed for production of various horticultural crops. Horticulture contributes to approximately 4% of the state GSDP. Horticulture crop covers 13% of the gross cropped area in the State. The area under Horticulture is 16 lakh Ha, with an annual production of 118 lakh tonnes.

Production Summary of Horticulture crops, AP

| Crop Category | Area (In Ha) | Production (In M.T’s) |
| --- | --- | --- |
| Fresh Fruits | 6,55,968 | 75,80,172 |
| Plantation Crops | 2,94,498 | 2,07,695 |
| Tuber Crops | 23,367 | 4,56,748 |
| Vegetables | 2,25,184 | 26,91,901 |
| Flowers – Loose | 11,500 | 49,152 |
| Cut Flowers | 1,401 | 60.96 Lakh Nos |
| Spices | 3,67,246 | 5,82,795 |
| Medicinal & Aromatic Plants | 2,893 | 4,050 |
| TOTAL | 15,97,263 | 118,23,487 + 60.96 Lakh Cut Flowers |

Source: National Horticulture Mission, Action Plan for Andhra Pradesh, September 2005. Accessed at http://nhm.nic.in/ActionPlan/ActionPlan_AP.pdf on 30 December 2010

Horticulture is one of the livelihoods options for tribal communities. Mainly horticulture and Medicinal crops are cashew, Amla and recently mangao, chikku and  other fruits plans being introduced in the area. Most of the tribal households having the cashew plants, amla. There are challenges related cultivation practices and marketing of produces.

### Livestock

Livestock is an important livelihoods source for small, marginal and land-less farmers. With its livestock resources and gradual enlightenment of the farmers along with dedicated and  sustained efforts over the years, the State has elevated to a prominent position in the Country  in the Livestock Sector. The State rose to number one position in Poultry and Egg Production in  the Country. From a humble beginning of backyard poultry, it has grown to a stage of dynamic  industry producing 183446 lakh eggs per annum. The milk production has increased from 18.08  lakh tonnes in 79-80 to 95.70 lakh tonnes in 2008-09 and is in 2nd position in India. The meat  production has increased from 96,320 tonnes in 79-80 to 6,04,000 tonnes in 2008-09 and stands first in the country. AP is well known for its livestock wealth.

Livestock Population - 1956-2007 - Andhra Pradesh (Figures in Lakhs)

| Sl.No. | PARTICULARS | 1956 | 1961 | 1966 | 1972 | 1977 | 1983 | 1987 | 1993 | 1999 | 2003 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | CATTLE |  |  |  |  |  |  |  |  |  |  |  |
| a | Males | 48.42 | 52.79 | 54.07 | 54.91 | 54.01 | 52.15 | 54.2 | 52.48 | 49.15 | 39.71 | 43.45 |
| b | Females | 37.62 | 40.75 | 41.54 | 42.31 | 41.14 | 43.78 | 35.64 | 30.26 | 29.23 | 29.24 | 35.5 |
| c. | Young Stock | 26.72 | 29.91 | 27.81 | 27.85 | 25.26 | 36.27 | 33.9 | 26.73 | 27.64 | 25.29 | 33.28 |
|  | Total | 112.76 | 123.45 | 123.42 | 125.07 | 120.41 | 132.2 | 123.74 | 109.47 | 106.02 | 94.24 | 112.23 |
| 2 | BUFFALOES |  |  |  |  |  |  |  |  |  |  |  |
| a | Males | 11.02 | 14.09 | 14.6 | 13.41 | 12.75 | 11.01 | 9.22 | 6.56 | 6.52 | 5.39 | 4.75 |
| b | Females | 28.76 | 31.51 | 32.19 | 35.01 | 36.68 | 43.45 | 44.75 | 48.23 | 51.7 | 59.22 | 70.32 |
| c | Young Stock | 19.9 | 23.89 | 21.12 | 22.15 | 22.2 | 32.58 | 33.6 | 36.74 | 38.36 | 43.07 | 57.64 |
|  | Total | 59.68 | 69.49 | 67.91 | 70.57 | 71.63 | 87.04 | 87.57 | 91.53 | 96.58 | 107.68 | 132.71 |
| 3 | Total Bovines | 172.44 | 192.94 | 191.33 | 195.64 | 192.04 | 219.24 | 211.31 | 201 | 202.6 | 201.92 | 244.94 |
| 4 | SHEEP | 78.46 | 83.63 | 80.04 | 83.43 | 70.64 | 75.19 | 68.72 | 77.87 | 97.43 | 210.15 | 255.39 |
| 5 | GOAT | 36.93 | 42.47 | 37.58 | 43.8 | 43.64 | 54.59 | 48.76 | 43.29 | 52.13 | 64.27 | 96.26 |
| 6 | PIGS | 6.21 | 5.93 | 5.82 | 6.9 | 7.55 | 7.86 | 7.24 | 6.48 | 7.48 | 5.49 | 4.39 |
| 7 | Other Livestock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0.47 | 0.37 | 0.77 |
| 8 | Total Livestock | 294.04 | 324.97 | 314.77 | 329.77 | 313.87 | 356.88 | 336.03 | 329.12 | 360.11 | 482.2 | 601.75* |
| 9 | POULTRY | 147.37 | 162.48 | 147.15 | 190.47 | 216.09 | 323.92 | 390.51 | 498.83 | 633.96 | 1005.8 | 1239.85 |

Source: Department of Economics and Statistics, Govt. of AP, Hyderabad upto Livestock Census-1999 accessed at http://ahfd.ap.nic.in/ISSSR0910.pdf on 31 December 2012

Trends in livestock population

- During the period from 2003 to 2007, Cattle Population increased by 19.09%. There is an increase of61.69% in Crossbred cattle population and 26.63% in non-descript cattle.  Adult female crossbred cattle have increased by 63.75% between 2003 to 2007.

- During the period from 2003 to 2007, Buffalo Population increased by 23.25%. There is an increase of83.06% in Graded buffalo population and 39.13% in non-descript cattle.  Adult female Graded buffaloes have increased by 35.48% between 2003 to 2007.

- The Sheep and Goat population increased by 21.53% and 49.77% respectively.

- The Poultry increased by 23.27% between 2003 to 2007.

District-wise Estimated Milk Production during the years 1996-97 to 2004-05 in Andhra Pradesh ( '000 tons)

|  | 1999-2000 | % | 2000-01 | % | 2001-02 | % | 2002-03 | % | 2003-04 | % | 2004-05 | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Andhra Pradesh | 5151.643 | 100 | 5521.476 | 100 | 5813.744 | 100 | 6583.165 | 100 | 6958.810 | 100 | 7256.83 | 100 |
| Proposed District |  |  |  |  |  |  |  |  |  |  |  |  |
| Chittoor | 397.944 | 8 | 533.031 | 10 | 465.910 | 8 | 508.000 | 8 | 539.906 | 8 | 646.24 | 9 |
| East Godavari | 352.627 | 7 | 374.139 | 7 | 426.000 | 7 | 482.995 | 7 | 535.924 | 8 | 459.711 | 6 |
| Visakhapatnam | 217.969 | 4 | 240.045 | 4 | 227.001 | 4 | 314.000 | 5 | 320.983 | 5 | 365.508 | 5 |
| Kurnool | 191.284 | 4 | 210.704 | 4 | 287.100 | 5 | 358.997 | 5 | 365.125 | 5 | 291.775 | 4 |
| Khammam | 201.196 | 4 | 169.872 | 3 | 240.913 | 4 | 310.008 | 5 | 329.652 | 5 | 276.055 | 4 |
| Warangal | 137.822 | 3 | 156.610 | 3 | 124.990 | 2 | 158.698 | 2 | 161.914 | 2 | 165.968 | 2 |

Source: Sample Survey reports of Department of Animal Husbandry , AP

Dairy accounted for 11% of agricultural GDP in the state. According to 17thQuiquennial livestock census 2003, the total population of cattle and buffalos in the state was 106.3 lakhs and 93 lakhs respectively. Milk production in the state in1980-81 was 2.01 million tons and increased to 7.257 million tons in 2004-05(Table 28) registering a growth rate of 3.74% per annum raising the per capita availability of 263 gms. According to the sample survey report of Department of Animal Husbandry, AP 2006-07, the average milk yield per animal in milk was only1.888 Kgs, 2.84 Kgs, 7.147 Kgs and 6.541 kgs per day for non-descript cows, non-descript buffalos, crossbred cows and graded murrah buffalos, respectively.

Performance of NREGA in the State

Andhra Pradesh has been an important centre of research and evaluations for NREGA implementation. It has been acknowledged for best documentation of implementation and hence is known for its transparency in implementation. It has an average of 22.2 person days per rural household which is on a higher side and around 60% participation of women, which is again amongst the top scores. With an average wage of Rs 83 per day, it has a biggest chunk of wages being disbursed through post offices (around 60% of total wages), as compared to all other states. As analyzed by PrabhuGhate, “AP has the advantage of relatively good quality of lower level field staff, has the advantage of managing the programme through mandals, which are smaller than blocks and therefore closer to the ground. It is unique in having institutionalized the social audit process through an autonomous state unit which makes a huge difference to the quality of the programme, has a good MIS (designed by TCS), and is spending more than 4 percent on administration of the programme, using its own resources to pay for the excess amount.”

The latest data on NREGA implementation in 2012-13 is given in Table 29

Employment Generated During The financial Year 2012-2013

|  | Cumulative No. of HH issued jobcards (Till December 2012) |  |  |  | Cumulative No. of HH demanded employment (Till December 2012) | Cumulative No. of HH provided employment (Till December 2012) |
| --- | --- | --- | --- | --- | --- | --- |
|  | SCs | STs | Others | Total |  |  |
| Andhra Pradesh | 29,18,453 | 13,81,339 | 77,33,097 | 1,20,32,889 | 52,57,899 | 52,57,899 |
| Proposed Districts |  |  |  |  |  |  |
| Vizianagaram | 60,363 | 62,636 | 392,491 | 515,490 | 319,279 | 254,016 |

|  | Cumulative Persondays generate (Till December 2012) |  |  |  |  | Cumulative No. of HH completed 100 days (Till December 2012) | No. of HH which are beneficiary of land reform/IAY | No. of Disabled beneficiary individuals |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SCs | STs | Others | Total | Women |  |  |  |
| Andhra Pradesh | 5,43,48,822 | 3,25,98,048 | 13,75,97,890 | 22,45,44,760 | 13,00,26,779 | 3,72,639 | 15,11,258 | 99,285 |
| Proposed District |  |  |  |  |  |  |  |  |
| Vizianagaram | 8,540 | 16,041,858 | 2,436,769 | 2,148,650 | 15,395,175 | 19,980,594 | 11,709,905 | 52,712 |

Source: http://nrega.nic.in/netnrega/mpr_ht/employeementstatus_mpr.aspx?lflag=local&state_code=02&page=S&month=Latest&fin_year=2012-2013&state_name=ANDHRA+PRADESH&Digest=SlGY0fA0YqTMJ82zunmI3g

NREGA in Andhra Pradesh - Field Diary, July 2009, IFMR Blog; accessed at http://www.indiadevelopmentblog.com/2009/07/nrega-in-andhra-pradesh-field-diary.html on 2 January 2013

The position of AP among all states improved from 20 in 2006-07 to 2 in 2009-10. The composition of works undertaken was such that the highest share of works- around 70% was related to common property resources for strengthening dry land agriculture.

Existing Livelihood Initiatives and Social Sector Initiatives in the Selected Area (by State Government, NGOs, Externally Aided Projects)

Describe briefly successful existing livelihood Initiatives and social sector initiatives in the State implemented by the State government, NGOs and externally aided projects

The Constitution of India made definite provisions for the welfare and upliftment of the tribal people throughout the country. A review of the tribal situation would indicate that the strategy for development would require an intensive approach to the tribal problems in terms of their geographic and demographic concentration, if faster development of the community is to take place. The special programmes for tribal development have been implemented in our country and state to benefit the tribal population under the backward classes sector from First Five Year Plan. These schemes left concrete impact on tribal development.

The Second Five Year Plan (1956-61) envisaged welfare programmes of STs based on the understanding of their culture and traditions, for their socio- economic upliftment. Fourty-three Special Multi-Purpose Tribal Blocks (SMPTBs) were created for about 25,000 people as against 65,000 in a normal block, which is an important landmark during this plan. The Third Five Year Plan (1961-66) followed the approach of equity of opportunity and to bring about reduction in disparities. The approach of the Fourth Five Year Plan (1969-74) was to increase the standard of living of the STs. Special development projects in the agency areas of AP, Bihar, MP and Orissa were set up for targeted development of tribal areas, besides combating political unrest and left wing extremism.

The Fifth Five Year Plan (1974-78) marked a shift in the approach with the launching of Tribal Sub-Plan (TSP) for the comprehensive development of the tribals. The TSP stipulated that the funds of the State and Centre should be quantified on the ST population on a proportional basis, with budgetary mechanisms for the welfare and development of the STs. For implementing the TSP strategy, Integrated Tribal Development Projects (ITDPs) were delineated in the tribal concentrated States.

During the Sixth Five Year Plan (1980-85) emphasis was more on family-oriented economic activities rather than infrastructure development schemes. A “Modified Area Development Approach” (MADA) was adopted for tribal concentrated pockets of 10,000 populations with at least half of them being STs.

During the Seventh Five Year Plan (1985- 90), there was substantial increase in the flow of funds. Two national-level institutions - Tribal Cooperative Marketing Development Federation (TRIFED) as an apex body for State Tribal Development Cooperative Corporations, and National Scheduled Castes and Scheduled Tribes Finance and Development Corporation (NSFDC) - were set up to provide remunerative price for the Forest and Agriculture Produce of tribals and credit support for employment generation and skill development.

The approach of the Ninth Five Year Plan (1997-2002) envisaged advancement of STs through a process of: (i) Social Empowerment; (ii) Economic Empowerment; and (iii) Social Justice for socio-economic development. An exclusive Ministry of Tribal Affairs was set up in 1999 for a focused approach to the development and welfare of the tribals in the country. The Tenth Plan (2002-07) continued the approach of Ninth Plan of Social Empowerment through promotion of new educational development schemes, Economic Empowerment through employment-cum-income generation activities and Social Justice through elimination of all types of discrimination.

The government, both at Centre and State, has not only formulated a number of policies to safeguard the interests of the tribals but also has initiated a number of development schemes for the welfare and upliftment of the tribal communities.

Ten Integrated Tribal Development Agencies (ITDAs) have been created for the development of tribals in the tribal Schedule Areas in order to provide single line administration so as to deliver prompt and accessible government services. Legal provisions such as special agency courts were also set up to give speedy justice to the tribals. The main schemes implemented by ITDAs include minor irrigation, soil conservation, horticulture, fisheries, sericulture, health and infrastructure for social support services. Centrally sponsored schemes are also being implemented to tackle special problems, namely, malnutrition, adult literacy and rehabilitation of shifting cultivators. Tribal administration vastly improved after these institutions were created; The ITDAs are in operation in eight districts, viz., Srikakulam, Vizianagaram, Visakhapatnam, East Godavari, West Godavari, Khammam, Warangal and Adilabad.

Indira KranthiPantham (IKP), the local name for the Andhra Pradesh Rural Poverty Program, is the longest running livelihoods program financed by the World Bank in South Asia. IKP is a poverty reduction project to enable the rural poor to improve their livelihoods and quality of life through their own organizations. It aims to cover all the rural poor households in the state with a special focus on the 30 lakh poorest of the poor households. It is implemented by Society for Elimination of Rural Poverty (SERP), Dept of Rural Development, Govt of AP. SERP is an autonomous society registered under the Societies Act, and implements the project through District Rural Development Agencies (DRDAs) at the District level. The Chief Minister of Andhra Pradesh is the Chairperson of the Society. IKP builds on more than a decade long, statewide rural women’s self-help movement. The focus is on deepening the process, providing an institutional structure and developing a framework for sustaining it for comprehensive poverty eradication.

In order to give greater focus and achieve convergence between the Indira Kranti Patham and the Integrated Tribal Development Agencies (ITDAs) in the project districts, under the overall framework,

the government has developed a tribal development strategy with exclusive implementation arrangements. The following implementation arrangements are ordered in the TSP areas. In the TSP areas, the Project Officer, ITDA, has the responsibility of implementing the Project. A separate Tribal Project Management Unit (TPMU) is being set up to work under the administrative control of Project Officer, ITDA. The TPMU’s mandate is social mobilization and empowerment of tribal communities in the TSP areas. The TPMU shall be provided with necessary support staff and functional specialists by the SERP. The TPMU’s day-to-day functioning shall be the responsibility of Additional Project Director who works under the Project Officer, ITDA, and under technical control of Project Director, Indira Kranthi Patham.

At the state level, there shall be a State Tribal Management Unit (STMU) as part of State Project Management Unit of SERP for effective implementation of Tribal Development Plan. The STMU shall function under close guidance and coordination of Commissioner, Tribal Welfare.

IKP works with 4,76,930 Self Help Groups federated into 28,080 Village Organizations (VO) and 700 Mandal Samakhyas (MS). The project mandate is to build strong institutions of the poor and enhance their livelihood opportunities so that the vulnerabilities of the poor are reduced. Community Investment Fund (CIF) is the major component of the project, which is provided to the SHGs/ VOs/ MSs to support wide range of activities for socioeconomic empowerment of the Poor.

Due to the efforts put in by TPMUs, 40,842 Self-Help Groups (SHGs) have been mobilized in tribal area with about 5.22 lakh ST women as members. So far, 2995 Village Organisations have been formed and they have federated into 77 Mandal Samakhyas in tribal areas. So far 18,129 Self-Help Groups have been provided with an

amount of Rs.68.38 crores under Community Investment Fund for taking up microprojects for gainful employment, thereby, benefiting 1,97,546 ST women13.

Self-help group bank linkage

Self Help movement through savings has been taken up as a mass movement by women. There are about 5.79 lakh women SHGs in Andhra Pradesh covering nearly 74.58 lakh rural poor women. The SHGs are not only resorting but are also taking small loans out of the corpus available with the group. An amount of Rs. 2385.98 crores is mobilized as corpus among these groups.

INDIRAMMA (Integrated Novel Development in Rural Areas & Model Municipal Areas)

The objective of this programme is to saturate the basic needs in respect of the identified activities in all the Villages and Towns over a period of Three years. Such development model will ensure overall development of the Villages/Towns in a transparent manner covering additional areas every year. This process will remove the uncertainty and skepticism in certain quarters with regard to coverage of all eligible beneficiaries and the infrastructure needs since all the villages/towns are covered over a period of three years.

The primary aim of this programme is to provide in every village pucca houses, drinking water supply, individual sanitary latrines, drainage, power supply to every household, Road facilities for transport, pensions to eligible old age persons, weavers, widows and the disabled, primary education to all, special nutrition to adolescent girls/pregnant and lactating women and better health facilities in all the villages over a period of three years in a saturation mode, This shall improve the living standards of the people significantly.

Rajiv YuvaKiranalu:

Rajiv YuvaKiranalu is conceived by the Govt. of Andhra Pradesh to build job specific skills among the unemployed and place them in appropriate private jobs. Vision of RYK is to Convert large no. of non-literate, school drop-out, unskilled and unemployed youth into productive workforce by building their skills thereby promoting inclusive growth. The mission proposes to employ 15 lakh youth in jobs in the private industry by 2014. The implementation shall be on a mission mode. To operationalise the programme, Government have constituted.

Indira JalaPrabha

'Indira JalaPrabha' is the flagship programme of Govt. of Andhra Pradesh with NABARD and MGNREGS with a view to consolidate the gains made in the Land Development Project of the later programme and to ensure sustainable and comprehensive development of the land securing livelihoods. The project aims at providing assured source of irrigation to the 10 lakh acres of fallow and uncultivable land belonging to the 6 lakh SC/ST farmers of the state. This will act as a welfare measure in terms of enhancing the productivity of the lands thus maximizing their incomes.

GCC:

Girijan Co-operative Corporation (GCC), started in 1956, has its headquarters at Visakhapatnam and undertakes procurement of minor forest produce (MFP) and agriculture produce from tribals at remunerative prices, undertakes public distribution in remote tribal areas, provides seasonal agricultural credit to ST farmers. The GCC is having (1,408) employees with a network of (1) regional office, (10) divisional offices, (43) GPCMS and (839) DR depots. During 2005-06 the turnover of the Corporation was Rs.194.49 cr. During 2006-07 (upto 31-12-2006) the turnover is Rs.153.44 cr. The GCC in recent years has focused on (10) major MFP species and expanded retail marketing aggressively from a sale of Rs.1.50 cr. in 2000-01 to Rs.8.41 cr. in 2005-06. GCC is also focusing on training to tribals, regeneration of NTFP, R&D initiatives and exporting.

TRICOR:

The Andhra Pradesh Scheduled Tribes Cooperative Finance Corporation Limited, Hyderabad (TRICOR), established in October, 1976, is coordinating various economic support schemes for the economic development of the STs in the state. Among the various steps taken by government to accelerate the pace of economic development of the STs, establishment of the Andhra Pradesh Scheduled Tribes Cooperative Finance Corporation is a major landmark. The corporation coordinates implementation of SGSY (ST component), Special Central Assistance, CMEY, PMRY, NSTFDC etc., by providing margin money and identification to the beneficiaries.

IFAD (International Fund for Agricultural Development):

Government of Andhra Pradesh has started IFAD-assisted programme for the comprehensive development of tribals in the interior agency areas of the state. The first phase of the IFAD programme for the coastal districts like Srikakulam, Vizianagaram, Visakhapatnam and East Godavari was started in 1991 and was completed in 1999, with a total expenditure of Rs.165 crores. Under the IFAD programme, apart from taking up schemes like irrigation, horticulture, land development, health and education; a lot of emphasis is being given for beneficiary participation.

Adivasi Mahila Sashaktikaran Yojana:

Upliftment of tribal women has been a prime focus of the NSTFDC. It is felt that tribal women can contribute significantly to the process of economic development of the STs. With this object in view, National Scheduled Tribes Finance Development Corporation (NSTFDC) introduced an exclusive concessional scheme for the economic development of eligible ST women titled “Adivasi Mahila Sashaktikaran Yojana”.

Janashri Bhima Yojana:

The Government of India has introduced a new scheme called “Janashri Bhima Yojana” during 2004-05. It is a group insurance scheme to provide life insurance protection to the rural and urban poor persons below poverty and marginally above poverty line, such as workers engaged in forest products and leaf collectors in forest.

Jawahar Gram Samrudhi Yojana (JGSY):

This scheme launched in 1999 aims to enable the village community to strengthen the village infrastructure through creation of durable assets as per the local needs. The works taken up provide gainful employment to the rural poor. Further, 22.5 percent of the State Budget is marked exclusively for the benefit of SCs/STs.

Joint Forest Management (JFM):

During 1990s, the Government of India (GOI) issued a circular enabling community participation in Forest Protection and Management. The Government of Andhra Pradesh (GOAP) adopted this in 1992. From then onwards there has been a major shift in Forest Management. The local village communities that depend on the forests for meeting their needs were made partners in Forest Management through the concept of Joint Forest Management (JFM). The experience of JFM in AP has proven to be a success. During 2002, the Government of Andhra Pradesh launched Community Forest Management (CFM) as an improvement over JFM. While JFM was a partnership between the forest dependent communities and the GOAP, CFM is a democratic process through delegation of the decision-making process.

Below table captures the - Tribal welfare during 1981- 2001:

NATIONAL RURAL HEALTH MISSION

NRHM seeks to facilitate increased access and utilization of quality health services by all; forge a partnership between the Central, State and the local governments; set up a platform for involving the Panchayati Raj Institutions and community in the management of primary health care programs and infrastructure; establish a mechanism to provide flexibility to the States and the community to promote local initiatives; develop a framework for promoting inter-sectoral convergence for promotive and preventive health care.

The mission objectives are:

- Reduction of Infant Mortality Rate, Maternal Mortality Rate, and Total Fertility Rate.

- Access to integrated comprehensive primary health care.

- Prevention and control of communicable and non-communicable diseases, including locally endemic diseases.

- Achieve population stabilization, gender and demographic balance.

- Revitalize local health traditions and mainstreaming AYUSH

- Promotion of healthy life styles.

In addition to the regular maternal health care and child health care services, NRHM also had additional services to strengthen the health services in the tribal areas

- 8500 Community Health Volunteers are working in tribal areas.

- Initiatives under RCH-II from 2005-06 onwards:

  - A package of RCH services have been introduced in the tribal areas (193 tribal PHCs) including shandy level RCH medical camps weekly once at every shandy.

  - 3,500 shandy clinics were conducted during 2005-06 and 7,000 shandy clinics were conducted during 2006-07.  The expenditure under this scheme is Rs.79,26,640/-

  - 43 Emergency Health Transport vehicles are functioning in tribal areas to provide the transport to emergency cases at free of cost.

  - 92 Mobile Medical Units are functioning in all the tribal areas to provide the services at the door step of the tribal people.

  - Birth waiting homes: Tribal area birth waiting homes are being constructed to enable women from distant and interior habitations to reach the delivery care institution a couple of days before the expected date of delivery as to prevent the complications of arrival in late labour.

AP has many schemes of the Tribal Welfare Department on education. These can be accessed at http://www.aptribes.gov.in/html/schemes-others.htm

CARE-Sustainable Tribal Empowerment Programme (STEP):

CARE-Sustainable Tribal Empowerment Programme (STEP)  implemented  in north Andhra and East Godavari with the support of  EU. The budget for the project is Euro 13 million. The goal of the  CARE-STEP project was, To improve the quality of life of most disadvantaged persons of tribal society in northern Andhra Pradesh on sustainable basis through Community empowerment.

PIAs Prior Experience in Developing the Prototype for Proposed Intervention

### Basic PIA Information

| 1 | Name of PIA | Jattu Trust, Parvathipuram. |
| --- | --- | --- |
| 2 | Legal Status (NGO / Network NGO / CBO / Producer Co. / Section-25 Co. / Pvt. Co/ Other – Please specify) | NGO |
| 3 | If Network NGO, number of partners being supported? | NA |
| 4 | Registration No. & Date of Registration | 6 of BK 4/98 of 1.5.1998 |
| 5 | Name of Donors in the past 3 years, if any (give max3) | Society for Elimination of Rural Poverty(Govt. of A.P), NABARD, and Centre for Environment and Education |
| 6 | Name with Size (Budget in INR) of relevant projects handled in the past 3 years (give max 3) | - Community Managed Sustainable Agriculture-Rs. 28.91 lakhs - Maathota Programme Rs.248.94 lakhs - Community Managed Education Services 25.37 lakhs |
| 7 | Annual Revenue of PIA for the most recent audited financial year | 55.61 lakhs |
| 8 | List ongoing projects (max 3.) and their Size (INR) | - MaathotaProgramme-Rs.248.94 lakhs - UNDP-MCG Project 20.9 Lakhs - Community Managed Education Services 25.37 lakhs |
| 9 | Completion of last project (MM/YY) | Health & Nutrition Programme, 31-3-2011 CMSA 2012 |
| 10 | Total value of assets available with the PIA? | One Crore plus generated from community |
| 11 | Experience of working with - Women SHGs/Groups (Y/N)- 1(a) in Appraisal Sheet - Agriculture based livelihoods with existing women groups (Y/N)- 1 (b) in Appraisal Sheet | Yes Yes |
| 12 | In the proposed project, what % of the implementation will be undertaken by existing capacities and what % will be leveraged from external community based organizations in the project area? – 1 (d) in Appraisal Sheet | Existing - 100% External –Nill, Going to hire the technical agency for NTFP and Marketing |
| 13 | Human Resource (Give details of staff with relevant experience proposed for deployment towards the proposed project. Details should also include availability of Community Resource Persons with relevant knowledge deployed under the project. Answer to this question may be put as Annexure. - 1(e)in the Appraisal Sheet |  |
|  | Name; Sex (M/F); Position; Education qualification; Relevant Experience (Years + Sectors). |
| 14 | Please attach following as Annexure - - Last three years audited financial statements Description of training resources and infrastructure available with the organization which is proposed to be deployed for the MKSP project e.g. brochure, training material, training hall, trainers etc)- 1 (f) in the Appraisal Sheet | Attached in Annexure - I |

- Assets, Equipments and other Infrastructure:

Please enclose information in the following format

- Fixed Assets (Capital)

| Sr.No | Type | Number | When Purchased |
| --- | --- | --- | --- |
| 1 | Land | 4 Acres of Land | 1999 and 2010 |
| 2 | Buildings(Dhyanamandiram, Training centre, Childrens dormitory Childrens Class rooms, Oldage Home, Library, Office Rooms, Kitchen and Dining hall, Handmade paper unit building) | 6 | Constructed on 2005 and 2011 |
| 3 | Furniture and Fixtures | 100 Chairs, 8 tables and 3 Almeria’s | 2006 to 2011 |

Equipment, Plant & Machineries

| Sr.No | Type | Number | When Purchased |
| --- | --- | --- | --- |
| 1 | Desktop computers | 2 | 2010 and 2011 |
| 2 | LED TV | 1 | 2012 |
| 3 | Projector | 1 | 2012 |
| 4 | HP laser jet printer | 1 | 2009 |
| 5 | Note book PC | 1 | 2012 |
| 6 | Sony Video Camera | 1 | 2009 |
| 7 | Sony digital camera | 1 | 2011 |
| 8 | Inverters | 2 | 2011 |

Past experience of Jattu Trust in the Proposed Area:

Jattu is registered under Trust Act on 1 May 1998 by Core group and  work with Jatapu, Savara, Gadaba, Kondadora tribes and others backward classes of Vizianagaram Dt, Andhra Pradesh, India. From the inception Jattu working with tribes and other backward classes with the aims to sustainable development.  Details of the projects ongoing and completed are provided below.

Ongoing Projects:

| Sr.No | Name of the Project | Geographical area of Operation | Duration of the Project | Target Group |
| --- | --- | --- | --- | --- |
| 1 | Maa Thota | G.L.Puram Mandal, Vizianagaram District | 2011 to 2018 | ST communities |
| 2 | Rythu Clubs | Garugubilli, Jiyyammavalasa, Kurupam and G.L.Puram Mandals of Vizianagaram District | 3 years from date of formation | Farmers |
| 3 | Natueco Farming | Biyyalavalasa village of Kurupam Mandal vizianagaram District | 2010 to 2013 | ST Farmers |
| 4 | Pre schools District Resource Center | Garugubilli, Kurupam, G.L.Puram, Jiyyammavalasa, Gantyada, Gurla, Merakamudidam and Pusapatirega Mandals of Vizianagaram District. | 2010 to 2013 | 3 to 5 years old childrens in rural areas. |
| 5 | Environmental Education | 63 Z.P.H. Schools of Vizianagaram District | From 2004 onwards | Schools and Community in Rural and Urban areas |
| 6 | Nutrition Re-habilitation Center | Kurupam and Saluru | From 2011 | Pregnant, Lactating women and 1 to 5 years aged children’s of Savara and Gadaba tribes who are suffering from mal nutrition |
| 7 | UNDP-Micro Capital Grant Project | Jattu Trust Operational Area | From 2012 | NGO Strengthening |

Completed  Projects:

| Sr.No | Name of the Project | Organization | Geographical area of Operation | Duration of the Project | Target Group |
| --- | --- | --- | --- | --- | --- |
| 1 | INHP (Integrated Nutrition and Health Programme) | CARE- Andhra Pradesh | Kurupam, Jiyyammavalasa and G.L.Puram Mandals of Vizianagarm District | 1998 to 2000 | Tribal communities |
| 2 | CARE/STEP (Sustainable Tribal Empowerment Project) | CARE – India | Kurupam, Jiyyammavalasa and G.L.Puram Mandals of Vizianagarm District | 2002 to 2007 | Tribal communities |
| 3 | Mobile Medical Units | Health &Family welfare Department, A.P. | Kurupam, Jiyyammavalasa and G.L.Puram Mandals of Vizianagarm District | 2006 to 2008 | Tribal communities |
| 4 | VISHWAS | Netherland Embassy | Parvatipuram, Kurupam and G.L.Puram Mandals of Vizianagaram District | 2005 to 2006 | Rural and Urban Areas |
| 5 | District Poverty Initiatives programme | Society of Elimination of Rural Poverty | Kurupam, Jiyyammavalasa and G.L.Puram Mandals of Vizianagarm District | 2000 to 2002 | Tribal communities |
| 6 | Non - Pesticide Management |  | Komarada, Parvathipuram, Garugubilli, Kurupam, Jiyyammavalasa and G.L.Puram Mandals of Vizianagaram District | From 2006 onwards | Farmers |

Chapter 2:  Detailed Intervention Strategy and Phasing

Objectives of the Project

The aim of the Project is to improve  the economic and food security of the Tribal's and other communities through 1/2 acre "Annapoorna" Model of  forest-dependent tribal women and other poorest of the poor (POP) women by promoting Annapoorna Model. The strategy is  to promote 1/2 acre Annapoorna model including  the NTFP and MAP collection and processing, by enabling 3,000 women farmers/ entrepreneurs in 6 mandals of Vizianagaram District.

- Vision of Success

The vision is to "Improve the quality of life of the tribal and other vulnerable families especially women in Vizianagaram district of Andhra Pradesh. This project is being built on the based on the experience from Jattu Trust implementing the Annapoorna model for Tribal and other families in Vizianagaram District.  Jattu trust addressing the issues through  enabling community institution of  tribal and other families;   These will include capacities and resources to reduce expenditure on healthcare, improved food and nutritional security through Annapoorna model.

Goals

The project goal is to create "improved tribal economic and food security enhancement through 1/2 acre Annapoorna crop model and medicinal plants for 3, 000 Tribal and other Women Households in Vizianagaram District of Andhra Pradesh". The aim is to support and strengthen the 3000 tribal and other families to have sustained food and nutritional security besides the economic security.

Components are:

- Community Institutions:

  - Identifying the eligible families in each village; short listing the families who are willing to adopt the "Annapoorna" model

  - Mobilising the "Annapoorna" model  farmers  in to common interest group in each village; Building their capacities on the model.

  - Building the cluster level federation and project level Apex federation Will facilitate demand generation for seeds, ensuring accessing the quality of inputs and remunerative markets.

- Capacity building for Productivity enhancement:

  - Strengthening the farmers capacity through best practices in Annapoorna model and sustainable agriculture practices for enhancing the productivity and food security

  - Providing training the Annapoorna cultivating /cashew  families on NTFP/MAP, Scientific way of cultivation and harvesting for enhancing the productivity through Annapoorna Model.

- Processing and Value Addition:

  - Strengthening the farmers on grading and packing of vegetables

  - Building the women farmers on processing and value addition of NTFP/MAPs/Agri/Horticulure such as lemon grass to lemon grass oil, hill broom stick, tamarind and cashew processing and selling

- Marketing:

  - Supporting the MACS to establish the outlets for selling the vegetables, fruits and other NTFP/MAPS produces.

  - Providing the information to women on market and linking them to some suppliers and buyers

Project framework diagram is below mentioned, it will provide the brief about the project goal, output and activities.

Vision of Success

Improve the quality of life of the tribal and other vulnerable families especially women in Vizianagaram district of Andhra  Pradesh

Project Framework

Objectives

Improved Tribal economic and food security enhancement through ½ acre Annapoorna crop model including medicinal plants for 3000 Tribal and other women households in vizianagaram district of Andhra Pradesh

Activities

Outputs

| COMMUNITY INSTITUTIONS | ESTABLISHMENT OF ANNAPOORNA MODEL | ENHANCEMENT OF QUALITY AND PRODUCTION | PROCESSING, VALUE ADDITION AND MARKETING | HEALTH | KNOWLEDGE MANAGEMENT & SHARING |
| --- | --- | --- | --- | --- | --- |
| Evolved Women Annapoorna common interest groups, cluster federations(8), one project level MACS and developed community level Annapoorna resource persons | Intensive, Integrated Organic Farming model; Inputs for improving food and nutrition security | Quality of Agriculture, NTFP and MAP products | Capacity for value addition of Agriculture products, NTFP and Medicinal plants; Establishment of Outlets; Market information and Linkages | Traditional health practices and Service providers and promotion of locally available leafy and tuber vegetables | Documentation Annapoorna and Sharing the success stories through Annapoorna monthly Magazine |
| Mobilising and sensitizing women; group strengthening; formation of apex bodies; establishing cadre of CRPs, Periodical assessment of the Groups and linking them for various services | Promotion of ½ acre Annapoorna model including medicinal plants. Training and establishment various demos on annapoorna model.CRP training on good practices; support through local team and experts | Assessment of practices in Agriculture and NTFP; Supply system for vegetables and NTFP; CRP training on good practices; support through local team and experts | Storage infrastructure; Training on processing and value added products; Assessment of the value chain and market operators; Bringing in a set of new/additional traders so that market competition is ensured; Sharing market information periodically | Build capacities of tribal families and traditional healers on traditional health care practices and effective use of these and documenting the best practices. Identification and documentation of traditionally used leafy and tuber vegetables. Will identify the nutrition value of these vegetable with the help of National Institute of Nutrition. | Documentation of day to day incomes and sharing good practices through Annapoorna monthly magazine, meetings, seminars, Television and cultural programmes. |

Andhra Pradesh State; 1 District; 6 Blocks;  150 Habitations; 3000 Households

Coverage

- Key Outputs/Result of the project:

- Community Institutions (Producers’ Organisations):

    - 150 common interest group (CIG) of Annapoorna Model cultivating tribal and other families

    - 8 Cluster Federations

    - One MACS with 3000 tribal and other families promoted and functional at the project level

    - 40 Community resource persons (CRP), 8 Para professional and 2 Professional with MACS

Establishment of Annapoorna Model:

    - 3,000 tribal and other families implementing the intensive, integrated and adoptive organic farming model Annapoorna for improvement in food and nutritional security either rain fed/irrigated.

- Enhancement of Production in NTFP/MAPs/Cashew:

  - Strengthening of production in NTFP/MAPS/CASHEW, adopting Scientific practices for improving the production, quality and harvesting.

    - Drudgery reduction for women through use of gender friendly tools/technologies

    - All the families will be trained Increased levels of skills and performance of women engaged in livelihoods

- Processing, Value Addition and Marketing:

  - Building the capacities of the tribal and other families on processing, value addition and marketing;

    - Establishment of Six outlets at different clusters/Mandal for marketing of organic fruits and vegetables; processed and value added products of NTFP and MAPs

    - Linkages for marketing of Agriculture/NTFP/MAPs

- Health   -  Revitalising Traditional Health Care to Reduce Expenditure and Better Health Status

    - 120 Traditional healers Identified and trained

    - Promoting MAPs part of the Annapoorna model

    - Documenting practices of traditional health care

    - Training of local health healers and beneficiaries and formation of healers’ network

    - Linkages to sales outlets

- Knowledge Management and Sharing:

  - Documentation of Annapoorna Model best practices and sharing widely for scale-up to improve the food and nutritional security

    - Monthly  news letter on Annapoorna model capturing good practices and sharing with wider audience

    - Identified locally available leafy vegetables and tuber vegetables and documented their Nutritional values

Convergency with existing SHG’s/Samakhyas : Convergence aim is to- Establish linkages for the CBOs with variety of stakeholders to leverage support in finance and other services.

    - Linkages for credit with local level SHGs, village level organisation, Mandal Samakya and Zilla Samakya

    - All members of the CBOs assessed on the eligibility and level of access to schemes  and entitlements

    - CBOs have received credit and insurance services from Banks and formal financial institutions

    - CBOs have received support through schemes and other support for technical and institutional development

These outputs will ensure the following key benefits:

- All the 3,000 families have intensive, integrated organic farm model Annapoorna and provide food and nutritional security for the households;

- Increased access to market and market information for better marketing of their products

- Drudgery reduction for women through use of gender friendly tools/technologies

- Improved opportunities for employment and business environment for community to take up entrepreneurial activities in tribal areas

- Reduction in health expenses

- Enhanced capacities and availability of localised community management service providers, and established linkages with key players in the value chain

- Significant improvement in poverty indicators of health and food security

Key Guiding Principles and Values of the Project:

The following are key principles that will guide the project strategies:

- Women focussed and women-led, family centric;

- Empowering process, and not as a service delivery;

- Community Institutions as a key base for building ownership and ensure sustainability;

- Convergence and leveraging existing bases and programmes – from community, government, market;

- Participatory bottom-up approach in planning and monitoring;

- Special focus on vulnerable groups;

- Appropriate use of technology – for production, information, and others as applicable;

- Environmental Sustainability, promoting sustainable agriculture, scientific  and non-exploitative practices

Project  Key Strategy

The project strategy has to be based on scaling up of PIA’s previous experience and other best practices.

The proposed project area is covered with poorest of the poor tribal and other families having cultivated/uncultivated land with low productivity located in tribal areas with low literacy levels, lack of skills, knowledge, poor forward and backward market linkages, exploitation by the intermediaries in the market place, poor extension system and  lack of nutritional security. The proposed project addresses the above issues by organizing Livelihood Organizations to increase their food and nutritional security.

Jattu experience in Annapoorna model

Jattu has already developed and demonstrated successful innovative household level food security model. This model has been initiated in the year 2010 with 60 tribal families in three Mandals in Vizianagaram district. The Apoorna Model developed at Jattu campus, Thotapalli, in half acre in irrigated conditions has been generated Rs.1,10,000/-from ½ acre. After seeing this model, many progressive farmers have come forward to promote Annapoorna model in other villages of the district. This model also implemented successfully in rain-fed conditions at Thotapalli village, wherein they have successfully harvested 2 crops in a year besides ensuring soil moisture in the summer for horticulture plants and the growth of the plants have been satisfactory. The rain-fed Annapoorna model generated an amount of Rs. 30000 per annum. Keeping this in view and potential for generating significance incomes to the poor tribal households, Jattu would like to scale up the programme to 3000 families.

Main components in Annapoorna model are preparation of land, preparation of beds, designing crop pattern, harvesting and marketing, organic farming practices, farm pond and alternative livelihoods. (Detailed report given in annexure – III)

Based on the previous experience of Jattu, overall strategy for improving the economic and food security is through 1/2 acre Annapoorna model.

Overall Strategy for the project:

- Promoting the community based organisation for sustainability

- Promotion of 1/2 acre Annapoorna model for food security, Nutritional security and economic development

- Technical support to pre and post harvest technologies to increase the productivity and adopt sustainable practices in CASHEW, NTFP and MAPs

- Processing, Value addition and Marketing of produce by the MACS

- Revitalisation of traditional health care through working traditional healers and documentation of practices

- Knowledge Management and Sharing about the Integrated Organic Farming Model-Annapoorna for a scale

These strategies in combination are expected to achieve not only the outputs and goal of the project, but sustain the benefits much beyond the project period.

Brief of each of these strategies are given below. Detailed components are explained in the next section.

- Strategy 1:  Community institutions:

Jattu Trust works with two types of community institutions– generic institutions of women (women SHGs) and livelihood institutions.  As this proposal addresses food security and economic development through the organic farming model by forming Common Interest Group(CIG), Cluster Federations (CF) and Producer Orgnisation-MACS (PO).  These institutions will be strengthened to manage the production, processing, value addition and marketing of organic products. At the same time, Jattu Trust facilitate these institutions to work very closely with the existing SHG-Federations promoted and  nurtured by SERP so that linkages for credit, mutual help, investment funds and other support is leveraged on a long-term. The linkage between the generic Women SHGs and the livelihood groups are planned at various levels to synergise efforts and ensure multiple services.

- Strategy 2:  Establishment of Annapoorna Model:

The aim is to improve the food security and economic development through agriculture and horticulture and MAPs; The strategy will be – (a) implementing of an intensive, integrated, adoptable 1/2 acre organic farming model (Annapoorna); and this will be leverage some support under Community managed sustainable agriculture(CMSA-SERP), convergence with NABARD(TDF)

- Strategy 3:  Enhancement of Production in Organic Cashew:

Improving the organic cashew production using sustainable agriculture practices and try to establish cashew processing units in tribal area to provide employment and marketing facilities.

- Strategy 4:  Processing, Value Addition and Marketing:

Building the capacities of the farmers in processing, value addition and marketing. The strategy is -(a) Building the capacities of the farmers and the institutions to identify the Horticulture, NTFPs and MAPs for processing and value addition and marketing; (b) Establishing the Six outlets for marketing of organic produces, and value added products of CASHEW, NTFP and MAPs. and also establishing the linkage for marketing of produce with various agencies so that higher margins are obtained. With GCC for Produce that are exclusively handled by GCC (monopoly produce of GCC), and with other market players for Produce that are not covered by GCC (non-monopoly items).

- Strategy 5: Health:

The aim is to improve the capacities of the traditional healers on traditional health care practices and effective use of these and reviving and strengthening traditional health care delivery system in the project area. The strategy is Special emphasis will be on identification and documentation of locally available medicinal plants, traditional healing practices and traditional healers in the project. Working with traditional healers and building their capacities to provide effective health care in the project villages. It is also proposed to identify and document nutrition values of traditionally used leafy and tuber vegetables with the help of NIN to improve food security and health reduction among tribal and other vulnerable families.

Strategy 6: Knowledge Management and Sharing:

Knowledge Management is the important strategy to share the best practices and learning to various agencies and organisation for taking up the Annapoorna model. Project will have systems to extract and share knowledge, being accountable and transparent. Under this there are three components are planned - (a) Monitoring and evaluation, (b) Monthly news letter on Annapoorna model and (c) Public disclosure policy. The project will work through multi-media approach which combines formal, informal, print-based and online to effectively share knowledge and provide regular updates to and between all parts of the communication chain

Strategy 7 : Convergence and Partnership building:

Another strategy convergence and partnership building is the key to ensure that all services are facilitated to the communities and the benefits are sustainable. The project is going to work with different stakeholders wherein each stakeholder in this has a role to play in addressing the quality of life of the tribal households.  A detailed convergence matrix capturing all the key stakeholders, the kind of support and the type of engagement is given later under the section ‘Convergence with MGNREGA and others’.

Community Institutions Architecture

Past experience in forming / nurturing women based groups and /or collectives:

Jattu Trust has been working for tribal economic empowerment since 1998.  Jattu Trust works with tribal community for promotion of tribal livelihoods, education, health etc for integrated development. It follows a strategy of promoting Community Based Organisations (CBOs) namely women Self Help Groups (SHGs) and Sasyamithra Sanghams, Village Tribal Development Associations (VTDA), Farmer's Clubs (FC) to empower the community for achieving overall socio-economic development of tribals.

Jattu in collaboration with Society for Elimination of Rural Poverty (SERP), Govt. of Andhra Pradesh had formed 1000 above tribal SHGs in tribal sub plan area of Parvathipuram, Vizianagaram District since the year 1999 - 2000. They are able to generate two crores of rupees as their savings and actively undertaking internal lending besides accessing bank linkages. They have also taken up socio-economic issues like laying of roads, construction of Anganwadi buildings, School buildings and irrigation structures on their own. The SHGs fought against illicit liquor and afforestation in tribal area of Parvathipuram and succeeded to a large extent. The SHGs are able to access government programmes like horticulture, marketing, income generation programmes for their overall development.

Jattu Trust also promoted Ushoday Mahila Cluster Samakhya  MACS Limited  in Vizianagaram district. The Jattu also supporting to women SHGs for forest resources conservation in general and NTFP/MAPs based livelihoods in particular by creating awareness and skill development programmes on harvesting and post harvesting management processes. NTFPs such as gum karaya, tamarind, honey, Broomsticks are important NTFPs being procured and marketed by the tribal families.

Jattu Trust has been putting conscious efforts in a convergence approach with Girijan Cooperative Corporation, ITDAs, SERP, donors for leveraging funds, services, technology and markets for benefitting the targeted stakeholders.

Good Practices in Group Promotion and Adoption of Practices:

Jattu Trust has been focusing on tribal empowerment by forming Women SHGs, Village Tribal Development Agencies (VTDAs), Sasyamithra Sanghams, etc, which are active and vibrant in its operational areas. The Women SHGs are strong force and collectively they are striving to achieve their felt needs and concerns. Women SHGs have been federated at various levels. The women federations are looking into the issues of value addition of horticulture, agriculture and NTFPs and also market linkages.

Ex: Established Cashew processing unit at Durbili, Ragi powder unit at Manthinivalasa, Turmeric processing unit at Valasaballeru.

Jattu developed resource material uses and have been conducted  Kalajatha programmes for social mobilization and capacity building programmes. Women SHGs have taken up social and economic issues for their overall development.

Since most of the SHG members are having agriculture as prime occupation, Jattu is extending technical support for the same under CMSA programme. As part of this programme, various crop models at Jattu resource centre as well as in field areas have been developed and implemented, which are considered as replicable models by other agencies and farmers by themselves.

One of the crop models developed by Jattu is Annapoorna, a food security model for household by cultivating half an acre in an irrigated/un- irrigated condition. This enabled to have vegetable food grains and cash income to the dependent families round the year. All the good practices are regularly identified, documented and disseminated thorough meetings, trainings and exposure visits

Women are sensitized, supported and organized into SHGs and linked to banks, line departments and Inidira Kranthi Padham (IKP) for accessing credit besides promoting thrift and credit activities within the groups.

### Proposed Plans and Strategies:

The project will facilitate communities to identify right beneficiaries so that they have both

aspirations and potential to be a part of this initiative and ensure success. Some of the key parameters

that will be used for selection of the women for the Annapoorna model and NTFP/MAP support are:

- Permanent resident of the Village

- Have record of land holding and willing to allocate the land for Annapurana model

- Member of a SHG, or willing to join in a Common Interest Group (CIG) of Annapoorna model

- Having aspiration for undertaking and following up income generation activities

- Have family agreement for support in working around Annapoorna model

- Acceptability within the group, without any previous defaults and involvement in local level issues

Overall Community Institutional Strategy CIGs/SHGs and Apex Bodies:

Key output expected from this strategy is that women are mobilised, organised into groups, linked to capacitated CRPs and appropriately federated to enable women to access services and control over resources and help them to sustain these services. To achieve this, the project will form at least one Women Group per Village with a local community resource person. The key is to build on already existing women SHGs promoted by IKP-ITDA-SERP and other programmes. The CBOs structure is largely looking at capacity building, arranging input supplies, financial inclusion, etc. Marketing and processing through higher level community groups/federations and Apex body is planned. The Project is conceived with CBOs i.e. Self-Help Groups and Common Interest Groups (CIGs).

COMMUNITY LEVEL APEX BODY  STRUCTURE

JATTU TRUST

MACS(supported by Two Professionals)

APEX BODY

Cluster Federations (8)  (supported by 8 para professionals  (CC’s))

CIGs (150) (Supported by 40 CRPS)

Mahila Farmers 3000

Village level Common Interest Group: In each village identified 20 to 30 beneficiaries grouped in to common interest group(CIG). The CIG will be supported by the Community resource person, he/she will organise the meeting and build their capacities on various aspects of Annapoorna model cultivation, sustainable agriculture practices and also building their capacities on pre and post harvesting techniques in NTFP/MAPs. Project will promote 150 CIGs.

Cluster level Federation: Grouping the CIGs at the cluster level in to federation. This federation will monitor, supervise the activities at the village level. From each CIG, will nominate the representative to cluster federations. This federation would work as an apex body for decision making depending on the strength of the individuals, and in turn provides them the platform to raise their collective voices at a higher level of decision making. Each of the cluster federation would have the Para professional(cluster Co-ordinator), who supports them in their operation.

Apex level Organisation: The apex level organisation will be promoted at the project level. All the 3000 project beneficiaries will have direct membership with the MACS.  At the MACS level skilled  professional will be there to support the operations of the MACS. He/She organise the meetings and maintain the records at the MACS level.

- Periodical meetings at the village/cluster/ district level of the SHG representatives for peer review and learning processes. This will happen every month and also reflection every six months. Cross exposure visits are also planned as a part of the capacity building.

- The periodical CRPs review and learning processes will also help in sharing good practices and challenges across the groups and finding common solutions. These will be taken back to the groups.

- The training that are planned at the start of the project and later during the project implementation will use resource persons from Jattu, kovel Foundation and outside, including experts in Sustainable practices, NTFP/MAPs pre and post harvesting techniques and cultivation. These training will be used to share the good practices across the country and across different SHGs/CIGs and help in the project SHGs/CIGs to adopt the same.

Building Common Interest Group, Cluster Federations and Producer Organisation for sustaining collective action

As given earlier under the Strategy 1, i.e. building and strengthening community institutions at three levels envisaged under this project.

The structure of the federated community based institutions is given above, reflecting levels.  The roles of these at different levels of federated structure are:

Common Interest Groups (CIG)

- Conducting trainings in collaboration with CRP to producers

- Establishment of Annapoorna Model

- Conducting meeting -discussion on best practices and learning's;

- Project Implementation and Money management

- Facilitating and ensuring collection of produce from the members & payment based on quality & quantity

- Mapping resources, planning procurement,  regulation

- Handling Grievances and

- Documentation

Cluster level federation

- Conducting trainings in collaboration with Paraprofessional to CRP to producers

- Supervising and guiding the CIG/CRPs in establishing the Annapoorna model

- Project Implementation and Money management - establishing the systems

- Collection of produce from the CIGs & payment based on quality & quantity

- Conducting trainings in collaboration with CIGs

- Convergence with various agencies and SERP promoted groups for credit and other supports

- Selling the produce and value added products  to Stores and other market players

- Identifying and finalising the products for processing and value additions; Establishment of processing centre

- Coordinating with Producer organisation

Producer Organisation (MACS) at Project Level:

- Conducting trainings to cluster level federations

- Providing management support to the CFs along with regular supervision of their activities.

- Supervising and guiding  the Cluster level federations

- Project Implementation and Money management - establishing the systems

- Procurement of produce from the CFs & payment based on quality & quantity

- Providing input services to the CFs

- Arranging for common purchase of raw materials used by CFs and CIGs

- Convergence with various agencies and SERP promoted groups for credit and other supports

- Selling the produce and value added products  to Stores and other market players

- Conducting training on Cooperative Development, conducting specialised skill development & Leadership Development training for CFs’ staff & Management Committee members

- Coordinating with Producer organisation

Role of community resource person, Para professional and Professional

In the project there are two types of community resource persons being developed, at three different levels – CIG, CF and MACS levels. Their roles are given below:

| Level | Type of Producer Groups | Resource Persons for Supporting Producer Organisations |  |
| --- | --- | --- | --- |
|  |  | Type | Roles |
| Village | Common Interest Group (CIG)(150) | Community Resource Persons (CRP)(40) | Capacity building of producers, estimating production, regeneration, group management, documentation, coordination with Para Professional, linking for convergence and with women SHGs; Participation in project implementation |
| Cluster | Cluster Federations (CF)(8) | Para Professional (8) | Capacity building of CRPs, monitoring them, training of producers, management of procurement, ensuring convergence as required; Coordinating all the activities in the cluster; |
| Project Level | Producer Organisation – MACS Society(1) | Professionals(2) | In overall charge of MACS, marketing and training – in coordination with the project; Building the capacities of Para Professional, Establishment of processing and value addition centres as required; |
|  |  |  | Supervising the Cluster federations, participating in CF meeting; Convergence facilitation, logistic support |

The CRPs will be identified and selected through a community processes (at CIG level and above).  The profile that will be selected for this will be defined by the community groups.  The CRPs are the main information carrier and disseminator in the area. Thus, while selecting and promoting CRPs, following aspects would be taken into consideration. He/she should:

- Be a resident of the area (village/ cluster/ districts);

- Be literate enough to understand the various work procedures;

- Be/was a practicing agriculture/Horticulture operator (particularly at the village/ mandal levels)

- Good understanding of Agriculture/Horticulture

- Be aware about the social, economic and geographical condition of the area;

- Be sensitive towards the local problems at the grassroots level;

- Be well-known to and versed with the community;

The CRPs will be accountable to the CIGs, CF and MACS. The honorarium will be paid to the CRP by the Project for a year, once the CIG and cluster level federation(CF) get strengthened, it will make the payment and review the progress of the CRPs at each level.

Control of CBO over the Fund Flow Mechanism

There are four types of funds envisaged in the operations, and these will be handled through different transparent and accountable system in the entire operations:

- Project funds:  These are funds from MKSP (Central MKSP-NRLM and from state SERP) for the implementation of the project. The project accounting system (detailed through the financial manual) will address the accountability of this.

  - The kind of expenses spent by Jattu trust are  will include Institutional building, training, exposure visits, tools kits  and administrative expenses; the feedback from community for these processes will be obtained.

  - The registered CBO Ushodaya Mahila Cluster Samakhya  which was promoted by Jattu Trust during the year 2006-2007 will be given programme fund especially the community investment support - inputs to establish the Annapoorna model.

- Revolving funds:  There is some quantum of funds earmarked for the working capital of the operations. These will be transferred to the MACS/respective federations and managed within those, with full control of the community and MACS facilitated by Jattu Trust.

- Transaction funds:  These are monies generated out of the supply chain transactions at district level and these will be collected by the federations and accounted in their books of accounts. The entire control of these transactions will be with community, but facilitated by Jattu Trust.

- Savings and capital funds:  These are funds generated by the producers through their savings at various levels and these are kept within their organisations/ levels and fully controlled by the members.

Convergence funds: These are monies generated out of the convergence support at various levels and these will be received by the producer organisations at various levels and accounted in their books of accounts. The entire control of these transactions will be with community, but ably facilitated by Jattu Trust support.

Chapter 3:  Detailed Project Components

Details of the Proposed Action

This section details out the project components under each of the key strategies adopted.  While detailing out these, the key principles of MKSP/NRLM have been explained in the text in appropriate portions (such as plans for promoting food security, sustainable practices, drudgery reduction, value chain development, access to credit).  At the end of this section, it captures these in an consolidated form.

- Strategy 1:  Community institutions:

Jattu Trust works with two types of community institutions– generic institutions of women (women SHGs) and livelihood institutions.  As this proposal addresses food security and economic development through the organic farming model half acre Annapoorna producers by forming Common Interest Group(CIG), Cluster Federations (CF) and Producer Orgnisation-MACS (PO).  These institutions will be strengthened to manage the production, processing, value addition and marketing of organic products, NTFP and MAPs. At the same time, Jattu Trust facilitate these institutions to work very closely with the existing SHG-Federations promoted by nurtured SERP so that linkages for credit, mutual help, investment funds and other support is leveraged on a long-term. The linkage between the generic Women SHGs and the livelihood groups are planned at various levels to synergise efforts and ensure multiple services.

The linkage between the generic Women SHGs and the livelihood groups (common interest groups for Annapoorna model farmers and NTFP/MAP is explained below).

Generic Institutions (Women SHGs and Federations)

The Women SHGs which are functioning in the proposed project locations will be enhanced through the provision of training and capacity building programmes. This will serve to upgrade their knowledge, skills and management practices besides strengthening book keeping, meeting efficiency and regular savings and help them to achieve a higher level of financial self-sufficiency.

The project will also help to identify any unorganized women members and help promote and facilitate new SHGs so as to ensure every woman within the project area can be part of SHGs. The PIA will make conscious efforts to ensure that there is community ownership and community management through providing and promoting leadership development and good governance norms/systems.

This will be done in collaboration with Society for Elimination of Rural Poverty (SERP) and building capacities of the CRPs by organizing Training of Trainers program on SHGs. At the start of the project, in every village, complete mapping of the existing generic institutions, their status and people who left out, etc. will be collected. Based on this information, strengthening of each of these groups will be taken up in coordination with SERP.

Overall Community Institutional Strategy CIGs/SHGs and Apex Bodies:

Key output expected from this strategy is that women are mobilised, organised into groups, linked to capacitated CRPs and appropriately federated to enable women to access services and control over resources and help them to sustain these services. To achieve this, the project will form at least one Women Group per Village with a local community resource person. The key is to build on already existing women SHGs promoted by IKP-ITDA-SERP and other programmes. The CBOs structure is largely looking at capacity building, arranging input supplies, financial inclusion, etc. Marketing and processing through higher level community groups/federations and Apex body is planned. The Project is conceived with CBOs i.e. Self-Help Groups and Common Interest Groups (CIGs).  The institutional architecture shown in section 2.3.1.

Village level Common Interest Group: In each village identified beneficiaries are grouped in to common interest group(CIG). In one village only one group will be there. The CIG will be supported by the Community resource person, he will organise the meeting and build their capacities on various aspects of Annapoorna model cultivation, sustainable agriculture practices and also building their capacities on pre and post harvesting techniques in NTFP/MAPs. Total in 8 cluster project will promote 153 CIGs.

The main functions of the CIG will be as follows:

- Conducting trainings in collaboration with CRP to producers

- Establishment of Annapoorna Model

- Conducting meeting -discussion on best practices and learning's;

- Project Implementation and Money management

- Facilitating and ensuring collection of produce from the members & payment based on quality & quantity

- Mapping resources, planning procurement,  regulation

- Handling Grievances and

- Documentation

Cluster level Federation: Grouping the CIGs at the cluster level in to federation. This federation will monitor, supervise the activities at the village level. From each CIG, will nominate the representative to cluster federations. This federation would work as an apex body for decision making depending on the strength of the individuals, and in turn provides them the platform to raise their collective voices at a higher level of decision making. Each of the cluster federation would have the para professional, who supports them in their operation. The main functions of the CF will be as follows:

- Conducting trainings in collaboration with Paraprofessional to CRP to producers

- Supervising and guiding the CIG/CRPs in establishing the Annapoorna model

- Project Implementation and Money management - establishing the systems

- Collection of produce from the CIGs & payment based on quality & quantity

- Conducting trainings in collaboration with CIGs

- Convergence with various agencies and SERP promoted groups for credit and other supports

- Selling the produce and value added products  to Stores and other market players

- Identifying and finalising the products for processing and value additions; Establishment of processing centre

- Coordinating with Producer organisation

Apex level Organisation: The apex level organisation will be promoted at the project level. All the 3000 project beneficiaries will have direct membership with the MACS.  At the MACS level two para professional will be there to support the operations of the MACS, organise the meetings and maintain the records at the MACS level. The main functions of the MACS will be as follows:

- Conducting trainings to cluster level federations

- Providing management support to the CFs along with regular supervision of their activities.

- Supervising and guiding  the Cluster level federations

- Project Implementation and Money management - establishing the systems

- Procurement of produce from the CFs & payment based on quality & quantity

- Providing input services to the CFs

- Arranging for common purchase of raw materials used by CFs and CIGs

- Convergence with various agencies and SERP promoted groups for credit and other supports

- Selling the produce and value added products  to Stores and other market players

- Conducting training on Cooperative Development, conducting specialised skill development & Leadership Development training for CFs’ staff & Management Committee members

- Coordinating with Producer organisation

There are three mechanisms in which the Project will ensure that the women groups learn from other

groups within the project area and beyond:

- Periodical meetings at the cluster/ district level of the SHG representatives for peer review and learning processes. This will happen every month and also reflection every six months. Cross exposure visits are also planned as a part of the capacity building.

- The periodical CRPs review and learning processes will also help in sharing good practices and challenges across the groups and finding common solutions. These will be taken back to the groups.

- The training that are planned at the start of the project and later during the project implementation will use resource persons from Jattu, kovel Foundation and outside, including experts in Sustainable practices, NTFP/MAPs pre and post harvesting techniques and cultivation. These training will be used to share the good practices across the country and across different SHGs/CIGs and help in the project SHGs/CIGs to adopt the same.

Linkage between Generic Women SHGs and Livelihood Producers Organisations:

To ensure good coordination and multiple support services, there is a need to work together between these two organisations. While the generic SHGs are promoted by SERP, the livelihood groups by the project. The project will work closely with SERP and the group at various levels to ensure synergy in operations.

Linkage between generic and livelihood organisation starts at the Village Organisation (VO) levels, where CIGs and VOs come together periodically, look at the needs and priorities in Annapoorna model including MAP and take joint decisions related to convergence, community investment funds, credit, regulations, etc.  Monthly meetings of each of these institutions are the institutional mechanisms in which this will take place (mostly monthly).  The roles for each of these groups are given below:

- Generic Women SHGs:  Savings, Credit, Mutual Help, Community Investments, Convergence with Departments, Women Empowerment

- Producers Organisations:  Annapoorna model and NTFP/MAP - Capacity Building, Regeneration, Procurement, Processing, Marketing, Related Working Capital

Reflecting the similar arrangements, at the higher level too (i.e. Mandal/ Cluster), the engagements between Mandal Samakhya and Cluster Federations of the producer organisations will be facilitated.  It is aimed that both these organisations working together will ensure that all required support services are available (credit to mutual help to livelihoods) building on the strength of each of these institutions, and at the end ensuring empowerment of women and the tribal households.

To ensure this, continuous capacity building of both these organisations, their institutional development processes, and linking up with capacitated community resource persons are planned. Details of these are explained later under the Capacity Building sections.

- Strategy 2:  Establishment of Annapoorna Model:

The aim is to improve the food security and economic development through agriculture and horticulture and MAPs; The strategy will be – (a) implementing of an intensive, integrated, adoptable 1/2 acre organic farming model (Annapoorna);

Thus ‘Annapoorna’ model is an intensive, integrated, adaptable organic farming model that ensures food and nutritional security will be followed by 3000 farmers in 153 villages in six mandals of  Vizianagaram district.

- Strategy 3:  Enhancement of Production in CASHEW:

  - Improving the cashew production through sustainable agriculture practices - project will support 1000 farmers to implement the good agriculture practices

- Strategy 4:  Processing, Value Addition and Marketing:

Building the capacities of the farmers in processing, value addition and marketing. The strategy is -(a) Building the capacities of the farmers and the institutions to identify the Horticulture, NTFPs and MAPs for processing and value addition and marketing; This will be done in collaboration with Kovel Foundation for NTFPs and for MAPs with individual entrepreneurs and also in convergence with SERP, ITDA. (b) Establishing the Six outlets for marketing of organic produces

Produces from the organic farm will be linked to the outlets being established in Mandal headquarters or towns; and also will be linked to Rythu bazars and other buyers as well.

  - Processing and value addition will be done for following products - Establishing cashew processing unit at Durbili village of Kurupam Mandal; Hill Broom unit at Gorada village of GL Puram Mandal; Turmeric bulking up and selling and also possibilities of processing at Durbilli village of Kurupam Mandal; Lemon grass oil extraction unit establishing in all the 8 clusters; The funding for this needs to be mobilized;

- Strategy 5: Health:

The aim is to improve the capacities of the traditional healers on traditional health care practices and effective use of these and reviving and strengthening traditional health care delivery system in the project area. The strategy is Special emphasis will be on identification and documentation of locally available medicinal plants, traditional healing practices and traditional healers in the project. Working with traditional healers and building their capacities to provide effective health care in the project villages. The majors outputs of this strategy are;

  - 120 Traditional healers identified and built their capacities on reviving traditional health care in the project villages;

  - Reduction in health expenditure among the tribal families in the project villages

  - Treating specific health problems of women and children

  - Promotion and regeneration of medicinal plants in the project villages

- Strategy 6: Knowledge Management and Sharing:

Knowledge Management is the important strategy to share the best practices and learning to various agencies and organisation for taking up the Annapoorna model. Project will have systems to extract and share knowledge, being accountable and transparent. Under this strategy there are three components are planned;

- Monitoring and Evaluation System – to track progress, process quality, outputs and impact

- Knowledge Management System – to share good practices and enabling adoption within in and outside project  through publish Sustira Annapoorna Monthly Magazine.

- Public Disclosure Policy – to establish policy and system for ensuring public disclosure as per the requirements under RTI and NRLM/SERP project requirements.

Each of these components are explained in detail under the “Monitoring and Evaluation”. The project will work through multi-media approach which combines formal, informal, print-based and online to effectively share knowledge and provide regular updates to and between all parts of the communication chain.

Level of adherence and synergy with the MKSP/NRLM Principles and Good Practices:

- Plans for promoting and enhancing food and nutritional security for women farmers?

The Project aims at addressing the food and nutritional security of the tribal women, children and their households in the following ways:

- The project has a clear component of promoting sustainable production through Annapoorna Model. This will lead to more availability of food grains and diversity of food for the households, particularly women and children.

- Increases in incomes through better management of farm and NTFP/MAP collection and harvest, giving more returns and incomes to households.

- The members will be provided support for MAPs which can provide primary cure locally thereby reducing their overall health status.

- The project have a clear vision to identify the traditionally used leafy and tuber vegetables and also identify the nutritional values of them with the help of NIN.

- Strategies addressing sustainable/evergreen/regenerative practices

The following are sustainable and regenerative practices that the project has envisaged:

Pre harvest , harvest and post harvest protocols development

Community protocols will be developed by integrating traditional and scientific knowledge in identification of adoptable organic farming. The project will train the Annapoorna farmers and NTFP/MAPs collectors and cultivators on best practices and provide improved tool kits to the trainees.

Use of indigenous knowledge

The project will make use of rich indigenous knowledge and technologies in traditional health practices, NTFPs identification, harvesting, processing, regeneration etc for sustainable use of resources for enhancement of tribal livelihoods and health security.

Suitability of technology to the local agro-ecology

The existing practices and technologies will be studied , validated and community consultation will be facilitated to assess the suitability of technology for adoption before introducing.

Resilience to climate change – Integrated Natural Resource Management

The project is promoting NTFPs/MAPs and Annapoorna model in organic methods which would enable to protect the natural resources and leading to positive impact. The project also focusing on increasing the number of NTFPs/MAPs by promoting plantations thereby augmenting the production and increasing the green cover in the years to come.  All these initiatives will have reasonable resilience to climate change factor.

- Targeting:

The proposed project area is covered with poorest of the poor tribal families having uncultivated land with low productivity located in tribal areas with low literacy levels, lack of skills, knowledge, poor forward and backward market linkages, exploitation by the intermediaries in the market place, poor extension system and  lack of nutritional security.

The proposed project addresses the above issues by organizing tribal Women SHGs as well as Livelihood Organizations to increase their food and nutritional security.

The Project aims at addressing the food and nutritional security for the women in the following ways:

- Establishment of Annapoorna model for the identified beneficiaries, that will increase the availability of the vegetables and medicinal plants The crops will be selected with priority for domestic consumption to meet the food and nutritional needs of the family. ; This will contribute to the family food and nutritional security;

- Increases in incomes, and particularly incomes in the hands of women is an important element of the project that is highly likely to contribute to better food availability of the family. Incomes will help the households in helping them to buy food and reduce the number of hungry days.

- The awareness building for the CIG members will also include the need to have diversity of foods and balance their nutrition, particularly for the women and children. This, along with the incomes in the hands of women will help women to choose right kind of food for the households.

Then proposed project will be implemented in six mandals of Vizianagaram district. The below table provides the details of project location details.  (Annexure – II)

- The Action Plan on the major interventions and time line

The project will adopt a phasing in strategy to reach the intended numbers, building on its scale up plans.  While the presence of the project will be there from day 1 in terms of the teams and community engagement, the plans for introduction of all the elements will be in phases.  As can be seen in the budget later, the grass-root level presence and the project organisational structure will be in place in all the locations from the first month onwards.  The phasing of all the project components is provided in the below table.

| Sl.No | Particulars of the Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1 | CRPs Recruited and Trained - 40 | 40 |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Project orientation to communities (CIGS) | 25 | 25 | 25 | 75 |  |  |  |  |  |  |  |  |
| 3 | Para Professionals recruited and trained – 8 | 8 |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Professional -Mkt Recruited and trained – 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Identification and finalisation of families - | 500 |  |  | 1500 |  |  | 1000 |  |  |  |  |  |
| 6 | Training on Annaporna model at project level No.of women | 500 |  |  | 1000 | 500 |  |  | 500 | 500 |  |  |  |
| 7 | Training to farmers on value addition and Post harvest Management at cluster level |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  |
| 8 | Annaporna model Implementation – No. Families |  | 250 | 250 |  | 1000 | 500 |  |  | 500 | 500 |  |  |
| 9 | Baseline Survey - No of families Covered | 1000 |  |  |  | 1000 |  |  |  | 1000 |  |  |  |
| 10 | Endline survey - No of Families Covered |  |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |
| 11 | Identification of healers on Ayurvedic medicine - Identified | 120 |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Training to local healers on Ayurvedic medicine - Trained |  | 120 |  |  |  |  |  |  |  |  |  |  |
| 13 | Training Module development and print - 1. Organic fertiliser and pesticides 2. Prep of Annapoorna 3.Leafy vegetables, tuber vegetables and nutrition values | 1 | 2 |  |  |  |  |  |  |  |  |  |  |
| 14 | Training module development : audio-visual | 1 | 2 |  |  |  | 0 |  |  |  |  |  |  |
| 15 | Mapping and doing need assessment of tools kits Lemon grass extraction tools at community level |  |  |  | yes |  |  |  |  |  |  |  |  |
| 16 | Tools and Kits providing related to - Pest control kit, Taurpaulins |  | 500 |  |  | 1500 |  |  |  | 1000 |  |  |  |
| 17 | Formation of CIG | 50 |  |  |  | 50 |  |  | 50 |  |  |  |  |
| 18 | Cluster federation formed |  | 4 |  |  |  | 4 |  |  |  |  |  |  |
| 19 | Cluster federation leaders trained |  | 4 |  |  |  | 4 |  |  |  |  |  |  |
| 20 | Formation of MACS consisting of 8 clusters |  |  |  |  |  |  | 1 |  |  |  |  |  |
| 21 | Training of MACS leaders on principles and management |  |  |  |  |  |  | 1 |  |  |  |  |  |
| 22 | Training on Value addition & processing on AGRO / MAPS to CIG leaders |  |  |  |  |  | 150 |  | 150 |  |  |  |  |
| 23 | Training to PRI representatives |  | 100 |  |  |  | 100 |  |  | 100 |  |  |  |
| 24 | Exposure to CRPs / para proffessoinals on NTFPs / MAPs | 48 |  |  | 48 |  |  |  |  |  |  |  |  |
| 25 | Training on Value addition & processing on AGRO / MAPS |  |  |  |  |  |  |  |  | 38 |  |  |  |
| 26 | Training on Food & Nutrition security |  |  |  |  |  | 38 |  |  |  |  |  |  |
| 27 | Development of Various Annapoorna crop models | 4 |  |  |  |  |  |  |  |  |  |  |  |
| 28 | Small Equipment to Cluster federation |  | 4 |  |  |  | 4 |  |  |  |  |  |  |
| 29 | Establishment of Organic Outlets |  |  | 1 |  |  |  | 3 |  |  |  | 2 |  |
| 30 | Rejuvenation of Cashew processing unit and inputs to farmers and facilitation cost |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | Two coordinators for facilitation of sustainable agri practices for Cashew plants and processing unit- recruited and trained |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 | Identification families for willing to do the sustainable practices in Two clusters (GL Puram and Krupam |  |  |  |  |  |  |  |  |  |  |  |  |
| 33 | Cashew garden rejunavation inputs – tre nches, half circle platform bund, training on Organic practices |  |  |  |  |  |  |  |  |  |  |  |  |
| 34 | Cashew Processing unit rejunavation at Durbili, Kurupam Mandal |  |  |  |  |  |  |  |  |  |  |  |  |
| 35 | Publication of Annapoorna monthly magazine and publish (no.of copies) | 1100 | 1100 | 1100 | 1100 | 2100 | 2100 | 2100 | 2100 | 3100 | 3100 | 3100 | 3100 |
| 36 | Study on locally available leafy vegetables and roots and its nutritional values with NIN support |  |  |  |  |  |  |  |  |  |  |  |  |
| 37 | Documentation on local healers knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 38 | Display no.of boards for public disclosure |  |  |  | 10 |  |  |  | 15 |  |  |  |  |
| 39 | Social Audit |  |  |  |  |  |  |  |  |  |  |  |  |
| 40 | Mapping the buyers and sellers in the project locations and arranging the meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| 41 | Mahila Kissan Profiling - 3000 families | 1000 |  |  | 1000 |  |  |  | 1000 |  |  |  |  |

- Plans for Post-project Sustainability and Scaling-up strategies.

The Project looks at sustainability as the ability of the project to ensure continuance of benefits to the

tribal and other women's beyond the project period. The key is to demonstrate significant and tangible impacts at the women entrepreneur level and in parallel ensuring that the key components/ dimensions of sustainability in the project, i.e. technical, institutional, economic, environmental and

policy.

In terms of the benefits to the women, the proposed project will increase the incomes of the households to a minimum of Rs. 55,000(50000+5000) per annum, with least risks in irrigated Annapoorna crop model and other allied activities in case of Rain fed areas it can be Rs.30000/- income will come per annum . The project through its approach of women centric and empowerment will ensure that women receive incomes in their hands. The women and their households will experience this increase in incomes and would therefore be motivated to continue the enterprise as it is expected to deliver reasonably good amount of incomes.

Given the strategy of building local cadre of CRPs and women groups and federations, the potential for institutional sustainability is high. There are challenges to sustainability. The climate variability is one of them. The project will work with state level policy to ensure that women producers are able to take advantage of enabling policies and also wherever policy constraints are observed, these are highlighted to the policy makers at the relevant level. The combined effect of working at the grass root level for improved practices, technology adoption etc., combined with institutional interventions (women groups and apex bodies), and policy engagement is expected to ensure sustainability of benefits.

The key dimensions of sustainability are:

- Technical: The technical inputs promoted by the action, related to sustainable Annapoorna model production, organic practices are well-tested and certified for their technical feasibility and are appropriate to the local situations. A systematic skill building and development of local service providers (CRPs) to extend services to fellow women is an important component.

- Institutional: The project will support in development of women CIGs, their apex bodies at the cluster and district levels. These institutions will be capacitated at various levels and their capacities will be assessed periodically and their capacities built up. These institutions are the key to sustaining the benefits over time for the women. The CIGs will have adequate returns to support the services of CRPs even after the project period.

- Economic: The inputs to be provided for key activities such as developing the 1/2 acre model, cultivation and scientific practices, techniques, methods and sustainable agriculture cultivation as such will improve incomes within the project period to a substantial level. Efforts will be made to link the CIGs/SHGs to banks, government departments for any future investments and continuing support.

- Environmental: All the activities proposed in this project are based on sustainable cultivation practices and organic way of cultivation. Clearly these ecologically sound practices will have beneficial impact. No environmentally exploitative practices will be promoted by the project.

- Plans for Drudgery Reduction of Women

The following are the key strategies and methods that will be promoted by the Project, which are likely to reduce the drudgery faced by women.

- Promotion of 1/2 acre Annapoorna model cultivation production and processing  in the project areas, which is women-friendly,

- Promoting scientific practices, tools and techniques that are women friendly – in cultivation and management

- Potential for introducing motorisation of the processing units is being explored. Depending on the need emerging from the field, this initiative will be taken up with support from other agencies

- Plans to Intervene in Value Chains

The core strategy of the project is about value chain intervention in Agriculture, Horticulture and  NTFP/MAP produce, addressing issues across the value chain from production, procurement, processing, marketing and also regeneration.  Details of actions under each of these are given in the detailed project component under Strategy 3.

- Strategies for Dissemination Knowledge

Key to the success of this project will be the ability to share knowledge efficiently and communicate throughout the entire structure quickly and effectively. A clear strategy on communication and a formalized method for the conveyance of information will help to ensure that.  The details of this is presented under ‘Supportive Strategy – Knowledge Management’ in the Detailed Programme Components.

- Plans for Increasing Access to Credit

The project targets to mobilize all the women into Women SHGs and their federations and efforts will be made to provide inputs to streamline systems and procedures to improve their governance, transparency and accountability. All these groups linked to MMSs, banks, MFIs, for accessing credit for their consumption and productive needs fulfilment. Concentrated efforts will be made to enhance operational and financial self sufficiency level of SHGs Federations.

Apart from this, the Project is also envisaging leveraging loans for working capital for the supply chain management through mainstreamed institutions such as NABARD, SIDBI, SFAC, etc.

- Direct Incremental Income to Farmers

It is expected that results of the project will lead to benefits from different angles.  As a result of the above mentioned interventions, sustainable livelihoods will be generated and it is expected to generate incremental income of Rs.50000 from irrigated Annapoorna model, Rs.30000 rain fed Annapoorna model, Rs.5000 from adopting Rejuvenation of cashew gardens sustainable pre harvest and direct marketing through MACS .

- Income from wages for local community

- Reduction in Health expenditure

- Income from surpluses generated in the community-led enterprises (producer organisation) from their procurement, processing and marketing operations

- Income in terms of Reduced Distance and Drudgery

- Plans for Community Contribution if any

The project will ensure contributions from communities in terms of efforts, cash and in kind.  These are expected at various levels.  For the entire process of institutional development and management of project processes at community level, the efforts will be made by communities.  In-kind contributions in terms of land and building for their processing units, storage spaces, and also in regeneration plantation processes are expected.  Each of the convergence components for Annapoorna Model or other works, the community contribution through labour will be a major component.

Convergence with NREGA and other Line Departments

The plan needs to highlight what would be the plan for convergence at the state level, district level and at the level of the institutions of the poor

One of the key strategies of the project is to converge with various institutions and schemes to ensure

that the Women farmers and institutions are provided appropriate support and also they establish a

long-term engagement with these institutions. The following convergence matrix captures the

schemes and agencies that will be linked up for various support. This is indicative list and more will get

added during the mapping of these schemes and agencies as the project progresses.

| No | Title/ Name of Program | With the Agency | Type of Services/ Support | Level at which this can be accessed |
| --- | --- | --- | --- | --- |
| 1 | NREGA | Gram Panchayat | Digging of furrows, farm ponds and trenches for Annapoorna farm; the Plantation activities in Horticulture and Agriculture | Individuals, CIGs, Women SHGs |
| 2 | NABARD-Bank Credit Linkage | Local lead banks and with NABARD | Credit - Capital, Working Capital | Women SHGs, CIGs and its apex bodies |
| 3 | Commercial and Rural Banks | Various Banks in the districts - lead banks and others | Loans - long-term, working capital for the producer organisations | CIGs, Cluster Federation and Producer Organisation MACS |
| 4 | Society for Elimination of Rural Poverty | Society for Elimination of Rural Poverty | Capacity Building, Credit, Community Investment Funds, CRP Training, Leveraging ToTs | Generic Institutions of Women SHGs |
| 5 | Girijan Cooperative Corporation | Girijan Cooperative Corporation | R&D, regeneration, value addition and marketing activities; avail funds from NCDC | CIGs, Cluster Federation and Producer Organisation MACS |
| 6 | ITDA - Various Programmes | Integrated Tribal Development Agency | Welfare programmes such as health, education, etc; and enterprise promotion related to processing NTFP/MAPs; Bore well digging | Women SHGs, CIGs, Cluster Federation and Producer Organisation MACS |
| 7 | TRIFED - Various programmes | TRIFED | Capital, Capacity Building, Advocacy | Women SHGs, CIGs, Cluster Federation and Producer Organisation MACS |
| 8 | Government Departments and Schemes | Agriculture, Horticulture, Forest, Tribal Welfare, Health, Women and Child Development, Education | Enterprise and Social Welfare Support - Capacity Building, Subsidised inputs, Financial Support | Mainly at Women SHGs, CIGs, Cluster Federation and Producer Organisation MACS |
| 9 | NAFED - Various Schemes and Support | Agriculture, Horticulture, Other Miscellaneous Commodities | Linkage for processing, storage, marketing, market information and linkages | CIGs, Cluster Federation and Producer Organisation MACS |
| 10 | Various programmes and support system within MPB | Medicinal Plants Board | Plantation activities in MAP; Technical and financial support to MAP cultivation | CIG |
| 11 | NGOs - various | Various NGOs working across different domains and in the geographies | Sharing expertise, knowledge, resource persons and other resources; solidarity and advocacy of the rights and entitlements of the community | Village to Project Level and beyond |

For each of the households, their eligibility to various schemes will be collected at their respective CIGs and those will be consolidated at the village, cluster and district levels.  The CRPs will periodically facilitate this process and review the level of access to these schemes.   Periodical mapping of new schemes, their eligibility and processes for facilitation will be undertaken and updated to the CRPs and the SHGs.  This will be shared among members in their monthly meetings and followed up for support.

Training and Capacity Building of Communities

The success of any development project depends very much on the capacity of its beneficiaries to effectively utilize the benefits and the staff to execute the programme in an effective way. Continuous capacity building is necessary at all levels to ensure effective implementation of the project and ensure impact and sustainability.  The overall philosophy driving this is to ensure that communities are capacitated to address their own governance, management and technical needs.

This element in a project calls for a strong capacity building programme plan to enable both the beneficiaries and the staff to achieve the project mandate.

The capacity building plan in the context of a poverty reduction project covers through understanding of the socio-economic, cultural setting of the project beneficiaries, specific programmes required for intervention, implementation strategy, and the skills to deliver the specific outputs and manage the programme for sustainable livelihood.

Therefore, need based programme modules for generic organisation, producer organisation and to the producers in the context of the project and the staff needs to be done.

At the community level, the capacity building will be undertaken at three levels:

At the community level, the capacity building will be undertaken at different levels:

- At the generic Women SHGs groups – Organise awareness meetings to the generic women SHGs, VOs, MS and Zilla Samakhyas.

- At the producer level – on various methods, techniques, production processes, etc. and in marketing, quality assurance

- At the Producer Organisation Level – on basics of the Agriculture, Horticulture and NTFP/MAP value chain, operations, the organisational development processes, etc. This will be done at CIG, CF and MACS level.

It is important to state here that the capacity building is not restricted only to training. The methodologies to be used will include demonstration of certain practices and techniques, handholding support by CRPs at various levels, exposure visits, helping the organisations to take up two to three cycles of operations and get a sense of market and trade, etc. Participatory and community-friendly methods will be used.

The training will be mainly done through a ‘Training of Trainers’ approach with the resource persons being the community resource persons at each level (CRP, Para Professional, Traditional Healers and Professional).  To train the TOTs, Jattu Trust will engage with various agencies that provide training in technical, market, finance and management areas.

The following are some of the training at various levels.  Detailed training needs analysis during baseline study will be conducted and periodically updated.  This will guide the capacity building at various points in time.

Common Interest Group(CIG) :

- Training on 1/2 acre Annapoorna farm Establishment

- Training on Sustainable agriculture practices

- Training on food and nutrition security  Ex: Traditionally used leafy and tuber vegetables.

- Training on Technical skill development [sustainable harvesting]

- Training on value addition and processing of Agro and MAPs

- Exposure to good cultivation and harvesting practices

Cluster Level Federation and Producers’ Organisation-MACS:

- The capacities of CFs and MACS will be built by organizing series of entrepreneurship development programmes and exposure to successful business models. The overall object of the programmes will be development of high level skills for community enterprise management. There will be two sets of EDPs:

    - Entrepreneurship development programme (Generic)

    - Entrepreneurship development programme (Commodity /business specific)

- Training on developing market linkages: marketing training will be provided to the CFs and MACS. The training will include identifying opportunities; product development marketing strategies ( backward and forward linkages ;assessing markets ;making linkages to credit, technology and infrastructure support ) etc.

Training and Capacity Building of Community Professionals

Here too, continuous capacity building is a must as the agenda taken up is large requiring CRPs to operate out of their standard sphere of operations, such as working with farm, products, trade, business approaches, dealing with marketers, legal regulations, etc.  The training for CRPs will be done through professional training organisations/ institutes and Jattu Trust will engage with them to provide training in technical, market, finance and management areas.

The methodologies to be used here will be largely skill based and exposure oriented, and as much possible on the job.  It is important that the CRPs face the challenges and learn from these.

The following are some of the training at various levels.  Detailed training needs analysis during baseline study will be conducted and periodically updated.  This will guide the capacity building at various points in time.

CRPs (Community Resource Person):

- Training on Annapoorna model

- Training on Sustainable agriculture practices

- Exposure to Annapoorna food security model

- Training on leadership and community mobilisation

- Training on liaison with Line department

- Exposure visit to various processing and value added products related to Agro and MAPs

Traditional Healer:

- Training on identification of medicinal plants and its curative benefits

- Training on tradition health care service delivery

- Exposure to traditional health care delivery system

Para-professional:

- Training on management of CIGs, CFs and MACS

- Exposure to Annapoorna food security model

- Exposure to best practices in MAPs cultivation and processing

- Exposure to traditional health care delivery system

- Training on community enterprise management

For the resource persons and the para professional in the supply chain too,  training will be conducted on the procurement, quality assurance, marketing, packing, losses, costing and pricing, etc.  Similarly, the operators in stores/Outlets and MACS will be trained on respective technologies.

Chapter 4:  Implementation Arrangements

Implementation Plan

- Elements of the Implementation Process:

- Project planning and set-up: This will include establishing project office, recruiting project staff, developing management system and project launch workshop. Representatives from Jattu Trust and key stakeholders will participate in an initial meeting to develop detailed plans and clarify roles and responsibilities.

- Orientation to Project team about the Project:    District Coordinator and CEO will orient the whole team on about the project and expected from each of the staff to deliver the project effectively.

- Undertaking baseline survey to identify project participants and assess the present situation. The survey would provide inputs on which specific intervention areas for  collectivisation,  cultivation, value addition ,enterprise development, alternative health delivery system etc. would be identified

- Project Implementation -  As detailed out in the strategies for project roll-out, Jattu Trust will initiate implementation processes from first quarter in locations where it has strong presence and community level engagement.  While in other locations, this will get initiated once the project partnerships are made.  The work will include formation of CIGs, trainings on Annapoorna Crop model  training, etc. This will go for the entire period of the project (i.e. 3 years)

- Consolidation and Concretizing Linkages – Around the second year onwards, to ensure sustainability, there is  need to ensure that the linkages made with different stakeholder, generic and livelihood organisation, marketers, etc. to be finalized and appropriate mechanisms would be put in place.  While these will largely go with the project implementation, additional focus is required to ensure that the partnerships are concretized and systems established to continue the linkages and benefits.

- Training the project participants on Annapoorna model  including NTFP/MAPSand sustainable agriculture practices; It includes exposure programmes

- Formation of MACS with tribal families and other vulnerable families as main stakeholder, sub activities include:

- Formation of Common Interest Group(CIGs)

- Formation of cluster level federation with CIGs as main stakeholders

- Formation of MACS

- Establishment of Outlets of Marketing of Organic products, value added and processed NTFP and MAP products

  - Establishment of Six retail outlet/store in Mandal headquarters or in towns/Busy Junctions.

  - Linking the producers to outlets and other market players

  - Organising buyers and sellers meet

- Establishment of Processing and Value added products centres

  - Finalisation of Agro, NTFP/MAPs products - Cashew, Turmeric, Tamarind, Hill Broom and Lemon Grass

  - Doing a feasibility for setting-up of different processing and value addition centre and including preparation of business plan for each of processing and value added centres

- Analyse the rapid assessment survey for identified areas of intervention viz. identification of marketable NTFP/MAPs, volume, infrastructure, etc.

- Identify location for establishing processing units/enterprises in identified districts

- Market Research on demand, competition and opportunities

- Feasibility and scale of operation of each enterprise

- Economics of the project

- Pricing structure and relationship between each level of enterprise

- Investment and financial requirement

- Size of each level of operation

- Management systems of resource and units of production and marketing

- Trade facilitation

- Buyer profiling

- Buyer seller liaising meeting

- Retail outlets and selling at Raythu Bazars etc

- Arranging buyers visit to producers

- Evaluation, Learning and Project Completion – The last quarter of the third year these work will be undertaken. Final project evaluation, learning exercises, completion of all the accountability requirements of the project will be completed during this period.

- Internal Structure for Implementation:

A Project Management Unit (PMU) at Organization level will be established to implement and monitor the programmme on a continuous basis. Annual Work Plan (AWP) is prepared based on the project document, which will be converted into half yearly, monthly and monthly action plans for close monitoring and follow up to achieve desired results. The responsibilities of Project Management Unit (PMU) will be:

Executive Trustee

Project Co-ordinator

Finance Manager

Barefoot Botanists (3)

Cashew Rejuvenation Co-ordinator (1)

Training Co-ordinator 1

Para Professionals  (8) (Cluster Co-ordinators)

Community Resource Person (40)

Roles and Responsibilities of Staff:

Executive Trustee/CEO: Responsible for providing strategic management and leadership of the project and providing line management support to the project manager and programme coordinators.

In addition to this, other responsibilities include:

- Management of external research and evaluation

- Monitoring and evaluation

- Proposal, planning, budget, monitoring and evaluation, reporting

District Coordinator: Responsible for inputs to project, line manage project staff, implementing project in the district, planning and delivering the project on the ground ,follow up of all activities . In addition to this, other responsibilities include:

- Coordinating and provide inputs into project planning ,monitoring and evaluation

- Reporting to project management team on project progress and impact

- Leading on the development and implementation on project plan

- Leading on the day to day action plan

- Leading on day to day project financial plan

- Overall coordination and facilitation of training projects

- Achieving the overall capacity building activities

- Resource mapping and inventory preparation

- Community protocols by blending traditional knowledge with scientific knowledge

- Development of GCP ,GAP, GMP manuals & storage protocol

- Training & drudgery reduction tools/machines for adoption of best practices

- Scientific practices in pre harvest and post harvest management

- Developing linkages with key local organizations

- Liaising with stakeholders

- Scheduling training and other activities

- Documenting and monitoring the progress against activities

Finance Manager: Responsibilities include

- Providing and logistical support to day to day operations

- Compiling and submitting timely reports covering all aspects of the project

- Ensuring timely release of funds for project expenditure ,consultants and partners

Para Professional (Cluster Co-ordinator): Responsible for project implementation at cluster level, manage CRPs,  planning and delivering the project on the ground ,follow up of all activities . In addition to this, other responsibilities include:

- Survey for beneficiary identification, resource identification, community mobilization, etc.

- Submitting consolidated action plan and submitting the consolidated reports from the field

- Conducting meetings with CRPs and guiding them; Building their capacities

- Monitoring the CRPs and supervising the field level activities

- Liaising with cluster level with different stakeholders and  generic SHG federations

- Organising meeting of Cluster level federation, building the capacities of the CF leaders and supporting them to manage their books

Training Co-ordinator:

- Will responsible to organise trainings at project level

- Will co-ordinate trainings from CIG level to Cluster Level

Bare foot Botanist:

- Will identify local healers

- Will organise trainings to local healers and community/community leaders/Para workers etc.,

- Will identify locally available medicinal plants and documented their uses.

- Will identify traditionally have been used leafy/tuber vegetables and documented.

- Will promote local herbs/leafy/tuber vegetables among communities

- Will propagate the uses, the importance’s and nutrients of herbals, leafy and tuber vegetables

Cashew Rejuvenation co-ordinator:

- Will identify cashew growing farmers within the range of two three clusters of MKSP-NTFP operational area

- Organise trainings on sustainable methods to improve production of cashew gardens

- Rejuvenation of cashew processing unit already established in Durbili village of Kurupam mandal

Role of CRP

Community Resource Person: Responsible for visiting 75 to 100 target Annapoorna beneficiaries and providing on-going support at grass root level .Specific responsibilities will include:

- Functioning as first line support to producers

- Providing support to producers to work on issues identified by cluster coordinators

- Enhancing awareness on different aspects of supply chain amongst producer groups

- Supporting the cluster coordinator in delivering their responsibilities

Professional Attached with MACS: activities includes

- Conducting the meetings of Para Professionals; Building their capacities on management of CFs, monitoring of field activities and reporting

- Organising meetings of MACS, guiding them and building their capacities

- Supporting the MACS to identify and establish the retail outlets

- Supporting the MACS to identify and establish different processing and value addition related centres

- Conduct market research for existing and future products

- Analysis of current market conditions and competitor information

- Develop and implement marketing plans for new and existing products

- Manage the productivity of the marketing plans

- Monitor, review and report on all marketing activity

- Determine and manage the marketing budget

- Develop pricing strategy

- Documenting success stories and sharing with all the beneficiaries through sustainable Annapoorna monthly magazine.

Chapter 5:  Implementation Schedule

Describe the implementation activities on a gantt chart. This may capture the phasing strategy

| Sl.No | Particulars of the Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1 | Staff Recruitment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification and Selection of CRPs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification and Selection of Para professional |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification and Selection of Traditional Healers |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recruitment of Professional |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl.No | Particulars of the Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 2 | Social Mobilisation and Planning |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation Meeting and concept sharing |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification and Selection of Project participants |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Participatory planning exercise at the village level: |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Institution Building - Formation of Producer Organisation-MACS |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formation of CIG - 153 nos |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formation of Cluster level federation - 8 nos |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formation of Producer Organisations- MACS |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Goal, Structure and governance |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Financial and Non-Financial Management |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Work around production cluster with cluster level association |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Operational modality |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Integrated adoptable Organic Farming (Annapoorna)Establishment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation of Annapoorna model to Project Participants |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implementation of Annapoorna model |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provision of seeds, fruit and Medicinal plants |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provision of tool kits - pest control kit, Tarpaulin |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation of sustainable agriculture practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Supervision during the crop and harvesting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collectivisation and market linkage |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Documenting best practices |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Enhancement of Production and employment through processing of Cashew and NTFP/MAPS |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation on scientific practices of NTFP/MAPs to Project Participants |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl.No | Particulars of the Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
|  | Implementation of rejuvenation of Cashew cultivation and processing for 1000 families |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provision of pre and post harvest technology related tool kit |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Processing/Value Addition and Marketing |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification of Value products for processing/Value addition |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation on processing and value addition on Agro and NTFP/MAPs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Small equipments provided to clusters for processing/value additions |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establishment of Processing centre |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Mapping the buyers and sellers in the project locations and arranging the meeting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establishment of Retail outlet and Market linkages |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training the project team on about the Project |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training the CRPs on - Annapoorna model |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training and exposure visit to the Project participants on the Annapoorna model and sustainable practices |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training the Project participants on the scientific practices in NTFP/MAP |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Exposure visits to CRPs on Annapoorna model and NTFP/MAPs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training to PRI representatives |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training to local healers on Aurvedic medicine - Trained |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training Module development and print - 1.leafy veg, root vegetables and Nutritional values;2. Prep of Annapoorna 3. Organic fertiliser and pesticides |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training module development : audio-visual |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl.No | Particulars of the Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
|  | Training the CIGs leaders and cluster federation leaders trained |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training of MACS leaders on principles and management |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project orientation to communities |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Knowledge Management |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Documentation of best practices, Video films |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Publication of Annapoorna monthly magazine and publish |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Documentation on local healers knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Convergence |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Mapping/identification of Inst. For partnership |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Interface |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Convergence plan Preparation and Update |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Plan execution |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Follow up |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | M&E system development, review of systems |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Software development for Web-based information system |  |  |  |  |  |  |  |  |  |  |  |  |
|  | M&E Systems and Project Reports |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final Report/Process document |  |  |  |  |  |  |  |  |  |  |  |  |

Chapter 6:  Results Framework

Describe the outputs and outcomes clearly. A log frame to be put.

The Project will be guided through a result-based managed management tool – logical framework.  This captures the short-term and long-term intent and actions, along with indicators and means of verification.

The logical framework for the Project is below:

| No | Narrative Summary | Observable/ Measurable Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| A | GOAL/ IMPACT |  |  |  |
|  | Improve the quality of life of the tribal and other vulnerable families especially women in Vizianagaram district of Andhra Pradesh | Reduced hunger index among the tribal /other vulnerable households in the project area | Impact Assessment Study (baseline and endline) Secondary data from the districts and state | Natural calamities do not occur to an extent that affects the lives and livelihoods Government policies and priorities with respect to tribal development and welfare continue to be positive Conductive political environment and no hindrances from LWE |
|  |  | Reduced IMR, MMR and UMR among the households in the project area |  |  |
|  |  | Improved HDI among the households in the project area |  |  |
| B | OBJECTIVE/ OUTCOME |  |  |  |
|  | Improved targeted families economic and food security enhancement through 1/2 acre Annapoorna crop model including collective processing and marketing of Agri products for 3, 000 Tribal and other Women Households in Vizianagaram District of Andhra Pradesh | At least 75% of the HHs report increase in income of at least Rs.30000 per Annam in rain fed areas, Rs.50000/- in irrigated areas + 5000 from other allied activities (Ex: processing of NTFP/MAPS/Agri Products) reduction in health expenditure after implementation of the activities like promotion of traditional healers and promotion of locally available leafy/tuber vegetables. | Household Survey, CIG records, CRP Reports | Above assumptions relevant here |
|  |  | At least 75% of the HHs report reduction in health expenditure on curative health and in unemployment days due to morbidity. | Household Surveys |  |
|  |  | At least 80% of women report improvement in their participation and influence over decision making at household and community levels | Household Survey, FGD with SHGs and CIGs |  |
|  |  | District level MACS have recognitions and established linkages from external agencies on market linkages, credit and services | Institutional Capacity Assessment Tool and Supply Chain Records |  |
|  |  | 70% of families report drudgery reduction due adoption of effective harvesting and post harvesting technologies | Household Survey, FGD with SHGs and CIGs |  |
|  |  | At least 75% of the HHs improved food security. | Household Survey, FGD with SHGs and CIGs |  |
| C | RESULTS/ OUTPUTS |  |  |  |
| 1 | Promote new institutions to manage and govern the production, processing and value addition of Agro, NTFP/MAPS | 153 Common Interest Group(CIG), 8 Cluster Federations and 1 Producer Organisation at District, covering 3000 members established and functional | Records of Producer Organisations | There are no large scale community level disturbances. Favourable policies of government on women and tribal development, and civil society initiatives in forest areas |
|  |  | Each producer organisation at every level is linked to capacitated community resource persons (CRP, Para Profession and Professional), accountable to them | Assessment of CRP, Para professional, Records of Producer Organisations |  |
|  |  | Linkages for financial support (working capital-revolving fund, loans) established | Records of Producer Organisations |  |
|  |  | Producers’ Organisations have established linkages with Panchayat, Traders and scientific institutions for Services related to production, processing and trade. | Institutional Capacity Assessment Tool, Interviews with Linkage Partners |  |
| 2 | Establishing processing/value addition and marketing at different levels | Identified and selected the Agro, NTFP/MAPs for processing and value addition | Producer Organisations Records | Favourable market conditions Linkage with GCC - favourable and cooperating |
|  |  | Linkages for marketing established with GCC and other partners and operations taking place | Producer Organisations Records |  |
|  |  | A community managed procurement and processing system for Agriculture, Horticulture, NTFP and MAP established and functional in all villages (through CIG, CF and MACS) | Producer Organisations Records |  |
|  |  | Six retail outlet established at Mandal headquarter or in towns for selling of Organic products and processed NTFP and MAPs | Records of Producer Organisations |  |
|  |  | Community organisations are involved in most handling most of the operations on their own, with their CRPs and support from Professional attached with MACS | Institutional Capacity Assessment Tool of PO |  |
| 3 | Developed intensive, integrated adoptable organic farming model for enabling food security and economic development | All the Project participants adopted the Annapoorna model and practicing the sustainable agriculture practices | Project MIS, CIG and PO discussions | Natural calamities do not occur to an extent that affects the lives and livelihoods |
|  |  | At least 75% of the families report it improved the food security and increased income by adopting the Annapoorna model | Survey, Project MIS, CIG and PO discussions |  |
|  |  | Increase in area under cultivation for the MAP and Horticultural crops by at least 10% in the project villages | Project MIS, CIG and PO discussions |  |
| 4 | Enhanced and processed production in Cashew and NTFP/MAPs | All CIGs trained on sustainable NTFP/MAP and 1000 families trained on sustainable Cashew practices; and at least 75% adopting at least one practice | Survey, Project MIS, CIG and PO discussions | Natural calamities do not occur to an extent that affects the lives and livelihoods |
|  |  | Established processing unit for cashew and NTFP/MAPS | Project MIS, CIG and PO discussions |  |
|  |  | At least 75% of them uses the tools and techniques for pre and post harvest technologies in NTFP/MAPs | Survey, Project MIS, CIG and PO discussions |  |
| 5 | Build capacities of traditional healers on traditional health care practices and effective use of these |  | Project MIS, CIG and PO discussions | Government policies and priorities with respect to traditional medicines/ healing continue to be positive |
|  |  | At least 10 practices related to traditional healing methods/processes using MAP documented | Project MIS, CIG and PO discussions |  |
|  |  | Healers training and network established for the project area and operational, addressing capacity and operational issues of healers | Project MIS, CIG and PO discussions |  |
|  |  | At least 75% of traditional healers report, skills improved to provide traditional health care at villages | Project MIS, CIG and PO discussions |  |
| 6 | Establish linkages of the PO with variety of stakeholders including women SHGs to leverage support in finance and other services | All CBOs and CRPs have a list of schemes and entitlements, with their eligibility and updated | Project MIS, CIG and PO discussions | Budgets and policies of departments favourable |
|  |  | All members of the CBOs assessed on the eligibility and level of access to schemes and entitlements |  |  |
|  |  | At least 80% of the CBOs have received credit and insurance services from Banks and formal financial institutions | Project MIS, CIG and PO discussions |  |
|  |  | At least 80% of the CBOs have received support through schemes and other support for technical and institutional development | Project MIS, CIG and PO discussions |  |
| 7 | Establish a robust M&E system to track results and outcomes, and communicate to various stakeholders | A well rounded ME& system in place and operational across levels - Village to Project (web-based) | Project document review | NA |
|  |  | Periodical M&E Reports prepared and shared in review meetings and learning forums (monthly and annual) | M&E Reports |  |
|  |  | Transparency and public disclosure systems in place and fully complied with | Statutory reports |  |
|  |  | Prepared monthly news letter named Susitara Annapoorna model and shared to various agencies | M&E Reports, copy of the news letter |  |

Chapter 7:  Monitoring, Evaluation and Learning

The framework for Monitoring and Evaluation System:

Building on good practices in monitoring and learning systems, the proposed M&E system will focus on ‘Performance Improvement, Accountability, Learning and Action’ to ensure efficient usage of resources, effective achievement of outcomes, maximized impact and value for the money.  The overall objective of the M&E system would be four-fold:

- Understanding Performance (inputs, activities, results, process quality) and Effectiveness (outcomes and impact)

- Being Accountable (upward and downward)

- Extract Key Learning – What works well and what not?  and why, etc. and

- Feeding back the Learning to Action – Planning and Action.

The framework is called MEAL framework – with focus on learning, it is Monitoring, Evaluation and Learning (MEAL). The focus is on all the four key areas, rather than just stopping at capturing information for reporting.

The MEAL framework will be developed using the Results Framework of the Project, which is detailed out in the logical framework (LFA).   The components of the MEAL framework are:

- input-activity monitoring (human, money and material) to track progress on utilization of resources by the way of plan vs actuals, quality of inputs and timely supply; analysing reasons for variation

- process monitoring, to improve the quality of implementation of key activities;

- output monitoring, to track achievement of results and analyze reasons for under-achievements and improve;

- outputs to purpose reviews to measure the project’s progress towards purpose and contribution by each outputs;

- impact monitoring to track the visible and emerging changes among the target communities, external environment and the value for money. The system will assess both impact and attribution through Before After Control Impact (BACI) design and possibly control-treatment comparison samples.

- In addition, the system will also keep track on cross-cutting issues and risks/assumptions made in the project at periodical intervals.

- To address the downward accountability,  a community-led system of social audit will be planned.

For addressing public disclosure, the project will develop a policy and system for the same.

Key mechanisms for M&E System:

The following is the mechanism to be put in place for effective implementation of the M&E system.  This is an indicative list and the same will be fine-tuned and finalised during the first quarter of the Project.

Web-based MIS and Real Time Input-Output Monitoring at Various Levels

How would data would be collected, entered, analyzed and used for decision making

Based on the finalised M&E framework for the Project, the information will be collected at various levels – members, CIG, Cluster, District and overall for the Project level; The project proposes development of a software wherein the information pertaining to various levels could be automated and updated on the web-based MIS.

- Profile of the Village, Annapoorna farmer, CIG, Resource Mapping of farmer, NTFP and MAP

- Inputs and activities undertaken by the project – in terms of number of training, meetings, etc.

- Outputs delivered by the Project as per the logical framework

During the first quarter of the project, software development will take place which will be based on the web-based information sharing system.   The system analysis has been already done during the project development period.  Monthly update of information for the Project will be undertaken and will be available for sharing as required.

Review Mechanisms

The review mechanisms to be used by the Project will be built on the existing system at Jattu Trust.

- Village Level:

  - CIG meetings – either fortnightly or monthly – with CIG members and CRPs – to check out the progress on activities planned; to review the Annapoorna Model practices related  procurement, pricing, quality considerations, marketing, credit, entitlements, etc.

- Cluster Level:

  - Monthly Project Staff Meeting – to review the project activities and project deliverables – with Project staff at the cluster level

  - Monthly Cluster Level Federation Meeting – to review the Annapoorna, procurement, processing, pricing, quality considerations, marketing, credit, etc. – with representatives of the CIGs, CFs, CRPs, and Project staff.

- District Level/Project Level:

  - Monthly Project Staff Meeting – to review the project activities and project deliverables – with Project staff at the district level

  - Six monthly/ Annual District Level CBO Meeting – to review the Annapoorna,  procurement, processing, pricing, quality considerations, marketing, credit, etc. – with representatives of the CIGs, CFs, CRPs, and Project staff.

- Project Level:

  - Monthly PMU Meeting – to review the project activities and project deliverables – with Project staff from the district at the project level

  - Annual State Level CBO Meeting – to review the Annapoorna,  NTFP/MAP/AP procurement, processing, pricing, quality considerations, marketing, credit, etc. – with representatives of the MACS, and Project staff

Chapter 8:  Budget Narrative

The following table summarizes the total budget for three years (2012-13 to 2014-15) in INR.

| Components of the Budget | Total | NRLM | SRLM | % |
| --- | --- | --- | --- | --- |
| Project Inception | 1,50,000 | 1,50,000 | - | 0.27% |
| Institution Building | 100000 | 1,00,000 | - | 0.18% |
| Capacity Building | 1,45,63.200 | 52,05,500 | 93,54,700 | 26.29% |
| Community Investment Support | 3,44,00,000 | 3,24,00,000 | 20,00,000 | 61.31% |
| Knowledge Management | 31,05,640 | 31,05,640 | - | 5.54% |
| Monitoring and Evaluation | 11,15,000 | 11,15,000 | - | 1.99% |
| Administration Expenditure | 26,71,680 | - | 26,71,680 | 4.76% |
| TOTAL | 5,61,05,520 | 4,20,79,140 | 1,40,26,380 | 100% |
| % to Total from Sources |  | 75.% | 25% |  |

Total project investment for three years is Rs. 5.61 Crores for 3,000 households, which work out to about Rs. 18,701/- per household (i.e. Rs. 6, 233 per household per year), whereas at conservative estimates the amount of economic benefit accruing per household is about Rs. 30,000 to 50,000.  This shows the project has a benefit cost ratio of more than 2.

As per the guidelines, 75% of the budgeted amount is requested from NRLM and the balance from SERP, Andhra Pradesh.

The analysis of the budget shows that three-fourth of the total amount will be spent on community level support – mainly on capacity building, institution building and community investment support. Substantial proportion of the budget is invested in the community, both in terms of improving their capacities and also building up their enterprises.

The amount to be spent on infrastructure too is at the community level, with processing units planned at the cluster and district levels. Programme management cost is about 4.7% of the total budget, well within the guidelines of MKSP.

The phasing of the budget – year-wise:

| Funds to NGO and Federation from NRLM and SRLM | Total | 25% - Year 1 | 50% - Year 2 | 25% - Year 3 |
| --- | --- | --- | --- | --- |
| NGO-Jattu Trust | 5,61,05,520 | 1,40,26,380 | 2,80,52,760 | 1,40,26,380 |
| Total | 5,61,05,520 | 1,40,26,380 | 2,80,52,760 | 1,40,26,380 |

Worksheets:

The budget worksheet as per the MKSP format is attached, along with schedules which detail out the information for each of the items.

- Chapter 9:  Dedicated staff

| JATTU TRUST MKSP-NTFP DEDICATED STAFF STRUCTURE |  |  |  |
| --- | --- | --- | --- |
| Sl.No | Designation | Roles and Responsibilities | Remarks |
| 1 | Executive Trustee | Overall supervision and monitoring | Cost meet from the Admin expenses (Part remuneration) |
| 2 | Project Co-ordinator | Overall co-ordination of the Project | Cost meet from the Admin expenses |
| 3 | Finance Manager | Responsible for overall financial transactions | Cost meet from the Admin expenses |
| 4 | Training Co-ordinators (2 No.s) | Give training to community, PRI, Local healers on Annapoorna medicinal plants etc., | Cost meet from Training Cost |
| 5 | Para Professionals (Cluster Co-ordinators (8 No.s) | Overall co-ordination of cluster activities | Cost from the MKSP-NTFP budget |
| 6 | Community Resource Persons (40 No.s) | One CRP allotted to 75 families. They co-ordinate 75 beneficiaries each | Cost from the MKSP-NTFP budget |
| 7 | Barefoot Botanist (4 No.s) | They are identified local healers, local medicinal plants. | Cost meet from documentation on local healers knowledge budget and study on local available leafy vegetables and tubers |
| 8 | Facilitator of cashew gardens facilitator (2) | Rejuvenation of cashew gardens | Cost meet from Rejuvenation of cashew garden facilitation cost |

Human Development Report 2007, Andhra Pradesh; Accessed at http://www.aponline.gov.in/apportal/Human-Development.html on 29 December 2007

Source: from AP Human Development report 2007

Accessed at http://www.hindu.com/2010/05/06/stories/2010050659990600.htm on 29 December 2012

S. Mahendra Dev, Inclusive Growth in Andhra Pradesh: Challenges in Agriculture, Poverty, Social Sector and Regional Disparities, March 2007; Working paper no 71, CENTRE FOR ECONOMIC AND SOCIAL STUDIES, Hyderabad; accessed at http://www.eaber.org/sites/default/files/documents/CESS_Dev_2007.pdf on 29 December 2012

Andhra Pradesh Socio-Economic Survey 2011-12; accessed at http://www.aponline.gov.in/Apportal/AP%20Govt%20Information/APES%20New/APSES.html on 29 December 2012

S Mahendra Dev and Alakh N Sharma, Food security in India: performance, challenges and policies, OXFAM India working paper series, September 2010. (The data in the text is from NHFS-3)

Performance Evaluation of Targeted Public Distribution System (TPDS); Programme Evaluation Organisation, Planning Commission, Government of India, March 2005; accessed from http://planningcommission.nic.in/reports/peoreport/peo/peo_tpdsmarch05.pdf on 29 December 2012

Lakshmi Tejaswi and RamancharlaPradeep Kumar, DISASTER MITIGATION AND MANAGEMENT FOR ANDHRA PRADESH, INDIA: AN APPRAISAL, Earthquake Engineering Research Centre, International Institute of Information Technology; accessed from https://www.google.co.in/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&cad=rja&ved=0CDMQFjAA&url=http%3A%2F%2Fweb2py.iiit.ac.in%2Fresearch_centres%2Fpublications%2Fdownload%2Farticle.pdf.89638adc71c9c574.61706469736173746572732d61707072616973616c2e706466.pdf&ei=lkHgUIrDMcfHrQe_1YGgCA&usg=AFQjCNEJFSR1DiguQPpS66EmKbJoAvhewQ&sig2=a6Cxg-TnqQedrt4HRNU3Nw&bvm=bv.1355534169,d.bmk on 29 December 2012

Unless specifically mentioned, all the text in this section has been sourced from:2004, Joy Deshmukh-Ranadive, Women's Self-Help Groups in

Andhra Pradesh Participatory Poverty Alleviation in Action; accessed from http://info.worldbank.org/etools/docs/reducingpoverty/case/82/fullcase/India%20SHGS%20Full%20Case.pdf on 29 December 2012

Indira KanthiPatham, Society for Elimination of Rural Poverty, Progress report for the month of November 2009; accessed at http://www.docstoc.com/docs/23127983/Indira-Kranthi-Patham-Society-for-Elimination-of-Rural-Poverty-Indira-Kranthi-Patham-Society-for on 29 December 2012

CS Reddy, SandeepManak, Self-Help Groups: A Keystone of Microfinance in India - Women empowerment & social security, October 2005, MahilaAbhivruddhi Society, Andhra Pradesh (APMAS). Accessed from http://www.aptsource.in/admin/resources/1273818040_SHGs-keystone-paper.pdf on 30 December 2012

Dr. S. Srinivas and Mr. UmeshRao, A Promoting Forest based Livelihoods A case study on Kovel Foundation. Accessed at http://thelivelihoodschool.in/file-for-pdf/Kovel%20Foundation%201-2.pdf on 30 december 2012

source: http://www.cess.ac.in/cesshome/wp/WP_85.pdf

Source: https://www.google.co.in/url?sa=t&rct=j&q=&esrc=s&source=web&cd=2&cad=rja&ved=0CDoQFjAB&url=http%3A%2F%2Fwww.naeb.nic.in%2Fdocuments%2FReports%2FNTFP%2520Report.doc&ei=v6whUf-bIseNrgf1uIGoBA&usg=AFQjCNHT1wVxwUQbXCdd3xFUipfG-80xbw&sig2=yabGs0z3EYyRpiTruJtzxA

Source: http://forest.ap.nic.in/JFM%20CFM/CFM/Special%20Reports/NTFPs%20in%20AP%20%20by%20TERI/NTFP%20Final%20Report%20July-04.pdf

Andhra Pradesh still stuck with 4 crops; Times of India, October 4, 2012; accessed at http://articles.timesofindia.indiatimes.com/2012-10-04/hyderabad/34259005_1_bt-varieties-farmer-suicides-hybrid-riceon 30 December 2012

Dr.V.Subramanyam, Ecology, Technology And Resources Management Among The Tribes Of Eastern Ghats :  An Anthropological Study. Full  Length  Paper  Submitted  For The  Conference  “ Livelihood  Strategies  Among  Forest – Related Tribal Groups Of South India “ Mysore, October  2003.

Accessed at http://www.sasnet.lu.se/conferences/livelihood-strategies-among-forest-related-tribal-groups-south-india on 31 December 2012

http://ahfd.ap.nic.in/ISSSR0910.pdf

NREGA in Andhra Pradesh - Field Diary, July 2009, IFMR Blog; accessed at http://www.indiadevelopmentblog.com/2009/07/nrega-in-andhra-pradesh-field-diary.html on 2 January 2013

Accessed from http://www.aponline.gov.in/apportal/HomePageLinks/IndiraKantiPadham.htm on 31 December 2012

Developed by implemented in a large scale by Catalyst Management Services, a group organisation where Vrutti is a part.  http://www.cms.org.in