## Sheet1 (2)
JATTU - MKSP Month wise expenditure plan 2014 - 15
S.No | Component | Unit Description | Physical Outlay (No.of units planned) | Unit Cost | Financial Outlay | [11 empty] | Total Amount | Remarks
| Project Cost |  | Yr2 |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1 | Project Inception
a | Project orientation to community | Groups/Habitations(150) | 50 | 1000 | Financial Outlay M1: 12500; Financial Outlay M2: 12500; Financial Outlay M3: 12500; Financial Outlay M4: 12500 | 50000
A | Subtotal |  |  |  | Financial Outlay M1: 12500; Financial Outlay M2: 12500; Financial Outlay M3: 12500; Financial Outlay M4: 12500 | 50000
2 | Institution Building
2.2a | Formation of MACS | Nos(1) | 1 | 50000 | Financial Outlay M9: 50000 | 50000
2.3a | Buyers and sellers meeting | No.s(4) | 2 | 25000 | Financial Outlay M5: 25000; Financial Outlay M7: 25000 | 50000
| Subtotal | [15 empty] | 100000
3 | Capacity Building
3.1 | Training module development : Print | No.of training modules | 2 | 125000 | Financial Outlay M1: 250000 | 250000
3.2 | Training module development : audio-visual | No.of training modules | 2 | 125000 | Financial Outlay M2: 250000 | 250000
3.3a | Tool kits for annapoorna and NTFP / MAPS | Nos 3000 | 1000 | 500 | Financial Outlay M3: 125000; Financial Outlay M6: 125000; Financial Outlay M9: 125000; Financial Outlay M12: 125000 | 500000
3.6a | Training to Farmers on Annapoorna crop model including meels, snacks, accommodation,stationery, travel and resource feese. | Per Batch(50) | 20 | 60000 | Financial Outlay M2: 480000; Financial Outlay M3: 240000; Financial Outlay M6: 480000 | 1200000 | 3days @Rs 60000/- per batch of beneficiaries at project level
3.6b | Training to farmers on pre and Post harvesting Management at cluster level | Per Batch(30) | 20 | 6000 | Financial Outlay M6: 40000; Financial Outlay M7: 40000; Financial Outlay M8: 40000 | 120000 | 2 days at cluster level
3.6c | Food & Nutrition security to CIG/Community leaders | Per Batch(50) | 3 | 22500 | Financial Outlay M3: 22500; Financial Outlay M6: 22500; Financial Outlay M9: 22500 | 67500 | 1 day
3.6d | Training to local healers on Aurvedic medicine | Nos (120) | 1 | 96000 | Financial Outlay M5: 32000; Financial Outlay M6: 32000; Financial Outlay M7: 32000 | 96000 | 6days training / batch of 40. Rs 400/- per day excluding external resource person fee
3.7a | Training to Cluster Federations(CIG leaders) | Per Batch(50) | 3 | 30000 | Financial Outlay M4: 30000; Financial Outlay M7: 30000; Financial Outlay M10: 30000 | 90000 | 2days
3.7b | Training to leaders on MACS principles and Management | Per Batch(40) | 1 | 36000 | Financial Outlay M5: 36000 | 36000 | 3days
3.7c | Training on Value addition & processing on AGRO /MAPS to CIG leaders | Per Batch(50) | 3 | 30000 | Financial Outlay M4: 30000; Financial Outlay M6: 30000; Financial Outlay M10: 30000 | 90000 | 2days
3.7d | Training to PRI representatives | Per Batch (50) | 2 | 15000 | Financial Outlay M7: 30000 | 30000 | 1 day
3.8a | Exposure to CRPs / para proffessoinals on NTFPs / MAPs | Per Batch(38) | 1 | 38000 | Financial Outlay M2: 38000 | 38000 | 3 days
3.8b | Training on Value addition & processing on AGRO /MAPS | Per Batch(38) | 1 | 22800 | Financial Outlay M6: 22800 | 22800 | 2days
3.8c | Training on food & Nutrition security | Per Batch(38) | 1 | 22800 | Financial Outlay M2: 22800 | 22800 | 2days
3.9 | Exposure visit of cluster federations/MACS leaders to immersion sites | No.of Leaders Per Batch (30) | 1 | 150000 | Financial Outlay M8: 150000 | 150000 | 4 days
3.9a | Exposure to community on NTFPs/MAPs | Per Batch(35) | 3 | 35000 | Financial Outlay M9: 105000 | 105000 | 2 days
3.10a | CRPs Honorarium (village Annapoorna crop co-ordinator) | Months | 360 | 4000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000 | 30 CRPs working for 12 months @Rs. 4000 per month
3.11 | Service charge to para-professionals | No.of para-professionals (8) | 96 | 6000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 576000
B | Sub total |  |  |  | 418000 | 958800 | 555500 | 228000 | 236000 | 920300 | 300000 | 358000 | 420500 | 228000 | 168000 | 293000 | 5084100
4.1 | Inputs to the mahila kisan Grant for preparation of (Annapoorana crop model) | No.of mahila kisan | 1000 | 10800 | Financial Outlay M3: 5400000; Financial Outlay M7: 5400000 | 10800000 | Land Preparation including ploughing,digging,planting bedding puncing 5500 Seeds 2500 Accessories 2800 (Tulf,sprayal,power weeder etc)
4.2 | Small equipment for Cluster Federations | Lumpsum | 4 | 50000 | Financial Outlay M5: 200000 | 200000
4.4 | Revolving fund to MACS | Lumpsum | 1 | 1000000 | Financial Outlay M6: 1000000 | 1000000
4.4b | Establishment of organic out lets | No..6 | 3 | 100000 | Financial Outlay M5: 100000; Financial Outlay M8: 100000; Financial Outlay M10: 100000 | 300000
C | Sub total |  |  |  | Financial Outlay M6: 1000000; Financial Outlay M10: 100000 | 12300000
5 | Knowledge Management
5.2 | Publication of manadesam annapoorna monthly magazing including staff cost | Lumpsum | 25200 | 16.9 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 35490 | 425880
5.2b | Documentation on local healers knowledge including staff cost | Lumpsum | 0.5 | 500000 | Financial Outlay M7: 250000 | 250000
5.3 | Resource Persons fee, travel and accommodation (Kovel Foundation and other external and internal resource persons | Units | 70 | 4000 | Financial Outlay M6: 140000; Financial Outlay M10: 140000 | 280000
D | Subtotal |  |  |  | 35490 | 35490 | 35490 | 35490 | 35490 | 175490 | 285490 | 35490 | 35490 | 175490 | 35490 | 35490 | 955880
6 | Monitoring & Evaluation
6.1 | Baseline survey | Nos | 1000 | 40 | Financial Outlay M1: 20000; Financial Outlay M2: 20000 | 40000
6.2 | Endline survey | No. of HH to be covered | 1000 | 40 | Financial Outlay M12: 40000 | 40000
6.4a | Display boards for public disclosure | No.s | 50 | 1600 | Financial Outlay M7: 40000; Financial Outlay M9: 40000 | 80000
6.5 | Social Audit | No.of social audits | 1 | 25000 | Financial Outlay M12: 25000 | 25000
6.6 | Other (Specify)
s.No | Regular Programme Monitoring / attend meetings,reviews and exhibitions etc | Lumpsum | 1 | 200000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 |  |  | 200000
E | Sub total |  |  |  | 40000 | 40000 | 20000 | 20000 | 20000 | 20000 | 60000 | 20000 | 60000 | 20000 | 0 | 65000 | 385000
| Total |  |  |  | 505990 | 1046790 | 623490 | 295990 | 291490 | 2115790 | 645490 | 413490 | 515990 | 523490 | 203490 | 393490 | 18774980
7 | Administration Expenditure (Maximum 5% of total project cost)
7.1 | Staff salaries
7.1a | District Co-ordinator | Months | 12 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 216000
7.1b | Finance Manager 50% | Months | 12 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 102000
7.1c | CEO Part Remuneration | Months | 12 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000
7.1d | Admin Assistant | Months | 12 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
7.1e | Office Assistant | Months | 12 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 48000
7.2 | Travel & conveyance | Months | 12 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 182400
7.3 | Office needs Stationary and Communication | Lumpsum | 12 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 72000
7.4 | Office rent | Months | 12 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
7.5 | Other Miscelleneous | Months | 12 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 1680 | 20160
F | Sub total |  |  |  | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 75380 | 904560
G | Grand Total (A+B+C+D+E+F) |  |  |  | 581370 | 1122170 | 698870 | 371370 | 366870 | 2191170 | 720870 | 488870 | 591370 | 598870 | 278870 | 468870 | 19779540
0

## Sheet1
JATTU - MKSP Month wise expenditure plan 2013 - 14
S.No | Component | Unit Description | Physical Outlay (No.of units planned) | Unit Cost | Financial Outlay | [11 empty] | Total Amount | Remarks
| Project Cost |  | Yr1 |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1 | Project Inception
a | Project orientation to community | Groups/Habitations(150) | 50 | 1000 | Financial Outlay M1: 12500; Financial Outlay M2: 12500; Financial Outlay M3: 12500; Financial Outlay M4: 12500 | 50000
A | Subtotal |  |  |  | Financial Outlay M1: 12500; Financial Outlay M2: 12500; Financial Outlay M3: 12500; Financial Outlay M4: 12500 | 50000
2 | Capacity Building | [15 empty] | 0
2.1 | Training module development : Print | No.of training modules | 2 | 125000 | Financial Outlay M1: 250000 | 250000
2.2 | Training module development : audio-visual | No.of training modules | 2 | 150000 | Financial Outlay M2: 300000 | 300000
2.3 | Tool kits for annapoorna and NTFP / MAPS | Nos 3000 | 1000 | 500 | Financial Outlay M3: 125000; Financial Outlay M6: 125000; Financial Outlay M9: 125000; Financial Outlay M12: 125000 | 500000
2.4a | Training to CRP's+CC'son Annapoorna crop model preparation (Lodging, boarding, travel) | Per Batch(38) | 1 | 91200 | Financial Outlay M2: 91200 | 91200 | 6 days
2.5 | Training to Farmers on Annapoorna crop model including meels, snacks, accommodation,stationery, travel and resource feese. | Per Batch(50) | 20 | 60000 | Financial Outlay M2: 480000; Financial Outlay M3: 240000; Financial Outlay M6: 480000 | 1200000 | 3days @Rs 60000/- per batch of beneficiaries at project level
2.6a | Training to farmers on pre and Post harvesting Management at cluster level | Per Batch(30) | 20 | 6000 | Financial Outlay M6: 40000; Financial Outlay M7: 40000; Financial Outlay M8: 40000 | 120000 | 2 days at cluster level
2.6b | Food & Nutrition security to CIG/Community leaders | Per Batch(50) | 3 | 15000 | Financial Outlay M8: 45000 | 45000 | 1 day
2.6c | Training to local healers on Aurvedic medicine | Nos (120) | 1 | 96000 | Financial Outlay M6: 48000; Financial Outlay M7: 48000 | 96000 | 6days training / batch of 40. Rs 400/- per day excluding external resource person fee
2.7a | Training to Cluster Federations(CIG leaders) | Per Batch(50) | 3 | 30000 | Financial Outlay M8: 30000; Financial Outlay M9: 30000; Financial Outlay M10: 30000 | 90000 | 2days
2.7b | Training to PRI representatives | Per Batch (50) | 2 | 15000 | Financial Outlay M10: 15000; Financial Outlay M11: 15000 | 30000 | 1 day
2.8 | Exposure to CRPs / para proffessoinals on NTFPs / MAPs | Per Batch(38) | 1 | 38000 | Financial Outlay M2: 38000 | 38000 | 3 days
2.9 | Exposure visit of cluster federations/MACS leaders to immersion sites | No.of Leaders Per Batch (30) | 1 | 150000 | Financial Outlay M8: 150000 | 150000 | 4 days
2.9a | Exposure to community on NTFPs/MAPs | Per Batch(35) | 3 | 35000 | Financial Outlay M9: 105000 | 105000 | 2 days
2.10. | CRPs Honorarium (village Annapoorna crop co-ordinator) | Months | 360 | 4000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000 | 30 CRPs working for 12 months @Rs. 4000 per month
2.11 | Service charge to para-professionals | No.of para-professionals (8) | 96 | 6000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 576000
2.12 | Development of Tribal crop models | No. of models(4) | 4 | 25000 | Financial Outlay M1: 50000; Financial Outlay M2: 50000 | 100000
B | Sub total |  |  |  | 468000 | 1127200 | 533000 | 168000 | 168000 | 861000 | 256000 | 433000 | 428000 | 213000 | 183000 | 293000 | 5131200
3.1 | Inputs to the mahila kisan Grant for preparation of (Annapoorana crop model) | No.of mahila kisan | 1000 | 10800 | Financial Outlay M6: 5400000; Financial Outlay M10: 5400000 | 10800000 | Land Preparation including ploughing,digging,planting bedding puncing 5500 Seeds 2500 Accessories 2800 (Tulf,sprayal,power weeder etc)
3.2 | Small equipment for Cluster Federations | Lumpsum | 4 | 50000 | Financial Outlay M12: 200000 | 200000
3.3 | Establishment of organic out lets | No..6 | 1 | 100000 | Financial Outlay M12: 100000 | 100000
C | Sub total |  |  |  | Financial Outlay M6: 5400000; Financial Outlay M10: 5400000; Financial Outlay M12: 300000 | 11100000
4 | Knowledge Management | [15 empty] | 0
4.1 | Publication of manadesam annapoorna monthly magazing including staff cost | Lumpsum | 13200 | 16.9 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 18590 | 223080
4.1a | Documentation of /locally available leafy vegetables and tubers and its nutritional values with NIN support | Lumpsum | 1 | 600000 | Financial Outlay M9: 600000 | 600000
4.1b | Documentation on local healers knowledge including staff cost | Lumpsum | 0.5 | 500000 | Financial Outlay M7: 250000 | 250000
4.2 | Resource Persons fee, travel and accommodation (Kovel Foundation and other external and internal resource persons | Units | 70 | 3000 to 4000 | Financial Outlay M6: 105000; Financial Outlay M10: 105000 | 210000
D | Subtotal |  |  |  | 18590 | 18590 | 18590 | 18590 | 18590 | 123590 | 268590 | 18590 | 618590 | 123590 | 18590 | 18590 | 1283080
5 | Monitoring & Evaluation | [15 empty] | 0
5.1 | Baseline survey | Nos | 1000 | 40 | Financial Outlay M1: 40000 | 40000
5.2 | Endline survey | No. of HH to be covered | 1000 | 40 | Financial Outlay M12: 40000 | 40000
5.3 | Display boards for public disclosure | No.s | 25 | 2000 | Financial Outlay M7: 50000 | 50000
5.4 | Social Audit | No.of social audits | 1 | 50000 | Financial Outlay M12: 50000 | 50000
5.5 | Other (Specify) | [15 empty] | 0
| Regular Programme Monitoring / attend meetings,reviews and exhibitions etc | Lumpsum | 1 |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
E | Sub total |  |  |  | 65000 | 25000 | 25000 | 25000 | 25000 | 25000 | 75000 | 25000 | 25000 | 25000 | 25000 | 115000 | 480000
| Total |  |  |  | 564090 | 1183290 | 589090 | 224090 | 211590 | 6409590 | 599590 | 476590 | 1071590 | 5761590 | 226590 | 726590 | 18044280
6 | Administration Expenditure (Maximum 5% of total project cost) | [15 empty] | 0
6.1 | Staff salaries | [15 empty] | 0
6.1a | District Co-ordinator | Months | 12 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 216000
6.1b | Finance Manager 50% | Months | 12 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
6.1c | CEO Part Remuneration | Months | 12 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000
6.1d | Admin Assistant | Months | 12 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
6.1e | Office Assistant | Months | 12 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 48000
6.2 | Travel & conveyance | Months | 12 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 182400
6.3 | Office needs Stationary and Communication | Lumpsum | 12 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | 132000
6.4 | Office rent | Months | 12 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
6.5 | Other Miscelleneous | Months | 12 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 744 | 8928
F | Sub total |  |  |  | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 75944 | 911328
G | Grand Total (A+B+C+D+E+F) |  |  |  | 640034 | 1259234 | 665034 | 300034 | 287534 | 6485534 | 675534 | 552534 | 1147534 | 5837534 | 302534 | 802534 | 18955608