## Financial Progress
| Name of PIA: | JATTU TRUST
| Year of Project Aproval: | 2013
B. | FINANCIAL PROGRESS | Amount received (Year I) | Expenditure (Year I) | % Expenditure (Year I) | Amount received (YearI I) | Expenditure (Year II) | % Expenditure (Year II) | Amount received (Year III) | Expenditure (Year III) | % Expenditure (Year III)
1 | Central share | 7786750 | 10960833 | 100%
2 | State share | 3142270
3 | Beneficiary contribution
4 | PIA contribution
5 | Others(Pls. specify) Bank interest | 31813
| Total | 10960833 | 10960833 | 100%

## Physical Progress
| Year of Project Aproval: | 2013 |  | Project: MKSP-NTFP/ 1/2 Acre Annapurna model of Agricultural practices
| PIA | Jattu Trust
S.No | PHYSICAL PROGRESS | Total Target as per sanction order/DPR | Target (Year I) | Achievement (Year I) | % Achievement (Year I) | Target for Year II | Achievement Year II | % Achievement (Year II) | Target for Year III | Achievement Year III | % Achievement (Year III)
1 | No. of Mahila Kisan covered-SA/NTFP/Livestock activities | 3000 | 500 | 608 | 121% | 1500 | 855 | 57% | 1000
2 | No. of Mahila Kisan in NRLM compliant SHGs | 3000 | 500 | 500 | 100% | 1500 | 1104 | 74% | 1000
3 | No. of trainee days completed on SA/NTFP/Livestock for Mahila Kisan | 9000 | 1500 | 2841 | 189% | 4500 | 1011 | 23% | 3000
4 | No. of Producer groups formed (Village level) | 150 | 50 | 48 | 96% | 75 | 28 | 38% | 25
5 | No. of Mahila Kisan in the fold of PGs | 3000 | 500 | 608 | 121% | 1500 | 855 | 57% | 1000
6 | Total No. of HHs adopting SA/NTFP/livestock practices | 3000 | 500 | 608 | 121% | 1500 | 855 | 57% | 1000
7 | No. of training modules developed-SA/NTFP/livestock
| Print | 4 | 2 | 3 | 150% | 2
| AV | 4 | 2 | 2 | 100% | 2
8 | No. of training modules used for training-SA/NTFP/Livestock
| Print | 4 | 2 | 3 | 150%
| AV | 4 | 2 | 2 | 100%
9 | No. of CRPs identified | 500 |  | 85
10 | No. of CRPs trained and deployed | 30 | 30 | 24 | 80%
11 | No. of training modules developed for CRP training
| Print | 4 | 2 | 3 | 150%
| AV | 4 | 2 | 2 | 100%
12 | No. of trainee days of training for CRPs | 180 | 144 | 144 | 100% | 36
13 | Net cropped area (Acres) under SA for Kharif season crops | 3000 models | 500 | 608 | 121% | 1500 | 855 | 57% | 1000
14 | Net cropped area (Acres) under SA practices for Rabi crops | 3000 models | 500 | 608 | 121% | 1500 | 855 | 57% | 1000